## Sheet1
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  | Original | Actual | Remaining | Start | Finish | Total Float |  |  |  |  | 2025 | [11 empty] | 2026 | [8 empty] | 2027
|  |  | Duration | Duration | Duration
[8 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | AM
| USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power logic_fireproofin |  | 1695 | 1325 | 370 | 20-Nov-19 A | 15-Jul-26 | J: -169
MILESTONES |  |  | 1695 | 1325 | 370 | 20-Nov-19 A | 15-Jul-26 | J: -169
PROJECT MILESTONES |  |  | 2430 | 1900 | 530 | 20-Nov-19 A | 15-Jul-26 | J: -244
MS1040 | DURATION OF PROJECT CALENDAR DAYS |  | 1452 | 1900 | 530 | 20-Nov-19 A | 15-Jul-26 | J: -244; D: DURATION OF PROJECT CALE
MS2850 | LOADING DOCK SUBSTANTIALLY COMPLETE |  | 0 | 0 | 0 |  | 17-Apr-25 | J: 180; D: LOADING DOCK SUBSTANTIALLY COMPLETE
MS2930 | WALKWAY(S) 1, 2, 3, 4, BUILDING L SUBSTANTIAL COMPLETION |  | 0 | 0 | 0 |  | 30-Sep-25 | J: 44; A: WALKWAY(S) 1, 2, 3, 4, BUILDING L SUBSTANTIAL COMPLETIO
MS2830 | CD COTTAGES SUBSTANTIAL COMPLETION |  | 0 | 0 | 0 |  | 06-Oct-25 | J: 8; M: CD COTTAGES SUBSTANTIAL COMPLETION
MS2810 | HIJ COTTAGES SUBSTANTIAL COMPLETION |  | 0 | 0 | 0 |  | 13-Oct-25 | J: 1; M: HIJ COTTAGES SUBSTANTIAL COMPLETION
MS2820 | EFG COTTAGES SUBSTANTIAL COMPLETION |  | 0 | 0 | 0 |  | 13-Oct-25 | J: 1; J: EFG COTTAGES SUBSTANTIAL COMPLETION
MS2760 | COMMUNITY CENTER SUBSTANTIALLY COMPLETE |  | 0 | 0 | 0 |  | 27-Oct-25 | J: -13; J: COMMUNITY CENTER SUBSTANTIALLY COMPLETE
MS2770 | BUILDING 9 SUBSTANTIALLY COMPLETE |  | 0 | 0 | 0 |  | 19-Mar-26 | J: -243; O: BUILDING 9 SUBSTANTIALLY COMPLETE
MS1050 | START LAST OWNER MOVE |  | 0 | 0 | 0 | 20-Mar-26 |  | J: -126; A: START LAST OWNER MOVE
MS2860 | BUILDING 3 SUBSTANTIALLY COMPLETE |  | 0 | 0 | 0 |  | 20-May-26 | J: -231; N: BUILDING 3 SUBSTANTIALLY COMPL
MS1010 | PROJECT SUBSTANTIALLY COMPLETE - READY FOR OCCUPANCY |  | 0 | 0 | 0 |  | 15-Jun-26 | J: -214; D: PROJECT SUBSTANTIALLY COMP
MS2000 | SITE SUBSTANTIAL COMPLETION (Target = 11/10/23 |  | 0 | 0 | 0 |  | 15-Jun-26 | J: -244; D: SITE SUBSTANTIAL COMPLETION
MS1020 | OVERALL PROJECT COMPLETION & CLOSEOUT DOCS (Target = 11/10/23, revised 11/13/25) |  | 0 | 0 | 0 |  | 15-Jul-26* | J: -244; D: OVERALL PROJECT COMPLETI
PROGRESS MILESTONES |  |  | 1404 | 1073 | 332 | 16-Nov-20 A | 20-May-26 | J: -131
NEW CONSTRUCTION/RENOVATIONS |  |  | 1404 | 1073 | 332 | 16-Nov-20 A | 20-May-26 | J: -131
LOADING DOCK |  |  | 35 | 0 | 35 | 27-Feb-25 | 17-Apr-25 | J: 125
MS2740 | LOAD Finishes Complete |  | 0 | 0 | 0 |  | 27-Feb-25 | J: 160; J: LOAD Finishes Complete
MS2750 | LOAD Construction Complete |  | 0 | 0 | 0 |  | 17-Apr-25 | J: 125; S: LOAD Construction Complete
COTTAGES |  |  | 1250 | 1073 | 178 | 16-Nov-20 A | 13-Oct-25 | J: 23
COTTAGE HIJ |  |  | 1250 | 1073 | 178 | 16-Nov-20 A | 13-Oct-25 | bar: J
LOE-120 | LEVEL-OF-EFFORT: Cottage- H/I/J |  | 739 | 1073 | 178 | 16-Nov-20 A | 13-Oct-25 | J: 1; M: LEVEL-OF-EFFORT: Cottage- H/I/J
MS2490 | HIJ Finishes Complete |  | 0 | 0 | 0 |  | 24-Apr-25 | J: 95; A: HIJ Finishes Complete
MS2500 | HIJ Construction Complete |  | 0 | 0 | 0 |  | 13-Oct-25 | J: 1; F: HIJ Construction Complete
COTTAGE EFG |  |  | 1199 | 1016 | 178 | 08-Feb-21 A | 13-Oct-25 | bar: J
LOE-130 | LEVEL-OF-EFFORT: Cottage- E/F/G |  | 636 | 1016 | 178 | 08-Feb-21 A | 13-Oct-25 | J: 1; M: LEVEL-OF-EFFORT: Cottage- E/F/G
MS2530 | EFG Rough In's Complete |  | 0 | 0 | 0 |  | 06-Feb-25 | J: 150; J: EFG Rough In's Complete
MS2540 | EFG Finishes Complete |  | 0 | 0 | 0 |  | 10-Jun-25 | J: 63; S: EFG Finishes Complete
MS2550 | EFG Construction Complete |  | 0 | 0 | 0 |  | 13-Oct-25 | J: 1; F: EFG Construction Complete
COTTAGE CD |  |  | 873 | 844 | 173 | 11-Oct-21 A | 06-Oct-25 | J: 28
LOE-150 | LEVEL-OF-EFFORT: Cottage- C/D |  | 379 | 844 | 173 | 11-Oct-21 A | 06-Oct-25 | J: 6; M: LEVEL-OF-EFFORT: Cottage- C/D
MS2580 | CD Rough In's Complete |  | 0 | 0 | 0 |  | 21-Feb-25 | J: 139; J: CD Rough In's Complete
MS2590 | CD Finishes Complete |  | 0 | 0 | 0 |  | 16-Jun-25 | J: 106; S: CD Finishes Complete
MS2600 | CD Construction Complete |  | 0 | 0 | 0 |  | 06-Oct-25 | J: 6; F: CD Construction Complete
BUILDING 9 |  |  | 736 | 468 | 288 | 03-Apr-23 A | 19-Mar-26 | J: -170
LOE-160 | LEVEL-OF-EFFORT: Building-9 Ren ovations |  | 415 | 468 | 288 | 03-Apr-23 A | 19-Mar-26 | J: -170; O: LEVEL-OF-EFFORT: Building-9 Ren ovations
MS2620 | Bldg 9 Dry In |  | 0 | 0 | 0 |  | 20-Mar-25 | J: 79; M: Bldg 9 Dry In
MS2630 | Bldg 9 Rough In's Complete |  | 0 | 0 | 0 |  | 14-Aug-25 | J: -24; D: Bldg 9 Rough In's Complete
MS2640 | Bldg 9 Finishes Complete |  | 0 | 0 | 0 |  | 29-Dec-25 | J: -118; M: Bldg 9 Finishes Complete
MS2650 | Bldg 9 Construction Complete |  | 0 | 0 | 0 |  | 19-Mar-26 | J: -170; A: Bldg 9 Construction Complete
COMMUNITY CENTER |  |  | 934 | 785 | 188 | 05-Jan-22 A | 27-Oct-25 | bar: J
LOE-140 | LEVEL-OF-EFFORT: CLC C ommunity Build ing |  | 386 | 785 | 188 | 05-Jan-22 A | 27-Oct-25 | J: -9; J: LEVEL-OF-EFFORT: CLC C ommunity Building
MS2680 | COMM Rough In's Complete |  | 0 | 0 | 0 |  | 20-Feb-25 | J: 142; J: COMM Rough In's Complete
MS2690 | COMM Finishes Complete |  | 0 | 0 | 0 |  | 01-Jul-25 | J: 50; N: COMM Finishes Complete
MS2700 | COMM Construction Complete |  | 0 | 0 | 0 |  | 27-Oct-25 | J: -9; M: COMM Construction Complete
BUILDING 3 |  |  | 693 | 369 | 332 | 22-Aug-23 A | 20-May-26 | J: -131
LOE-190 | LEVEL-OF-EFFORT: Building-3 Ren ovations |  | 453 | 369 | 332 | 22-Aug-23 A | 20-May-26 | J: -162; N: LEVEL-OF-EFFORT: Building-3 Ren ova
Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 1 of 46 |  | J: TASK filter: Activity Status.
Actual Level of Effort | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  | Original | Actual | Remaining | Start | J: Finish; F: Total Float; A: 2025; A: 2026; AM: 2027
|  |  |  | Duration | Duration | Duration
[9 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | AM
MS2890 | Bldg 3 Rough In's Complete |  |  | 0 | 0 | 0 |  | 27-Oct-25 | J: -23; M: Bldg 3 Rough In's Complete
MS2880 | Bldg 3 Dry In |  |  | 0 | 0 | 0 |  | 26-Jan-26 | J: -85; A: Bldg 3 Dry In
MS2900 | Bldg 3 Finishes Complete |  |  | 0 | 0 | 0 |  | 27-Jan-26 | J: -86; J: Bldg 3 Finishes Complete
MS2910 | Bldg 3 Construction Complete |  |  | 0 | 0 | 0 |  | 20-May-26 | J: -131; O: Bldg 3 Construction Complete
| CAVA PHASE-2 PROJECT - TEMP KITCHEN |  |  | 2342 | 1900 | 442 | 20-Nov-19 A | 18-Apr-26 | J: -243
LOE-180 | Maintain Funct of Temp Kitchen |  |  | 1318 | 1900 | 395 | 20-Nov-19 A | 02-Mar-26 | J: -234; A: Maintain Funct of Temp Kitchen
BLDG2-1020 | OWNER: Building 9 / Kitchen Space Move-in |  |  | 30 | 0 | 30 | 20-Mar-26 | 18-Apr-26 | J: -243; N: OWNER: Building 9 / Kitchen Space Move-i
| BUYOUT / PROCUREMENT |  |  | 1344 | 1107 | 245 | 29-Sep-20 A | 19-Jan-26 | J: -106
IMPACTS |  |  |  | 1164 | 871 | 370 | 01-Sep-21 A | 15-Jul-26 | J: -169
| RFP-0003 PHARMACY PARKING LOT |  |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: 136
RFP-0003bb | Bring Back To psoil |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 136; M: Bring Back Topsoil
RFP-0003cc | Restore Site |  |  | 1 | 0 | 1 | 04-Feb-25 | 04-Feb-25 | J: 136; A: Restore Site
| RFP-0007 BLDG 9 STORAGE TANK |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: -80
RFP-0007d | Bldg 9 Storage Tank I ns tall |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: -80; J: Bldg 9 Storage Tank I ns tall
RFP-0001 BLDG K |  |  |  | 4 | 0 | 4 | 03-Feb-25 | 06-Feb-25 | J: 142
RFP-0001f | Bldg K CP-7 & 8 |  |  | 4 | 0 | 4 | 03-Feb-25 | 06-Feb-25 | J: 142; M: Bldg K CP-7 & 8
| RFP-0016 CHANGE WALKWAY FCU |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 171
RFP-0016e | Install FCU from L-2 |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 171; M: Install FCU from L-2
| RFP-0026 ADD INSULATION FOR GLYCOL PIPING |  |  | 10 | 0 | 10 | 24-Mar-25 | 04-Apr-25 | J: -111
RFP-0026d | Insulate Glycol Piping B9 |  |  | 10 | 0 | 10 | 24-Mar-25 | 04-Apr-25 | J: -111; A: Insulate Glycol Piping B9
| RFP-0020 CLCS AND BUILDING 9 ELEC PANEL CHANGE |  |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: -82
RFP-0020g | Add 2nd Section Panel Bldg 9 |  |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: -82; J: Add 2nd Section Panel Bldg 9
| RFP-0043 ADD FAR 52.204-24 & 52.204-25 |  |  | 330 | 214 | 138 | 01-Apr-24 A | 15-Aug-25 | J: 6
RFP-0043j | Install Cameras Cott H/I/J |  |  | 3 | 214 | 1 | 01-Apr-24 A | 03-Feb-25 | J: 107; J: Install Cameras Cott H/I/J
RFP-0043i | Install Cameras Cott E/F/G |  |  | 3 | 0 | 3 | 03-Feb-25 | 05-Feb-25 | J: 141; J: Install Cameras Cott E/F/G
RFP-0043h | Install Cameras Cott C/D |  |  | 2 | 0 | 2 | 04-Feb-25 | 05-Feb-25 | J: 109; J: Install Cameras Cott C/D
RFP-0043k | Install Cameras Bldg K |  |  | 3 | 0 | 3 | 05-Feb-25 | 07-Feb-25 | J: 122; J: Install Cameras Bldg K
RFP-0043l | Install Cameras Bldg L & Walkways |  |  | 2 | 0 | 2 | 05-Mar-25 | 06-Mar-25 | J: 92; A: Install Cameras Bldg L & Walkways
RFP-0043m | Install Cameras Bldg 9G |  |  | 2 | 0 | 2 | 21-May-25 | 22-May-25 | J: -28; S: Install Cameras Bldg 9G
RFP-0043n | Install Cameras Bldg 9 1st Floor |  |  | 2 | 0 | 2 | 22-May-25 | 23-May-25 | J: 0; O: Install Cameras Bldg 9 1st Floor
RFP-0043o | Install Cameras Bldg 9 2nd Floor |  |  | 2 | 0 | 2 | 01-Jul-25 | 02-Jul-25 | J: -71; D: Install Cameras Bldg 9 2nd Floor
RFP-0043p | Install Cameras Bldg 9 3rd Floor |  |  | 2 | 0 | 2 | 14-Aug-25 | 15-Aug-25 | J: -79; J: Install Cameras Bldg 9 3rd Floor
| RFP-0045 COTTAGE DATA ROOM SIZES |  |  | 84 | 508 | 5 | 06-Feb-23 A | 07-Feb-25 | J: 78
RFP-0045k |  | Run New Cable Tray from Cott E to Cott F Data Rooms |  | 7 | 508 | 1 | 06-Feb-23 A | 03-Feb-25 | J: 74; O: Run New Cable Tray from Cott E to Cott F Data Rooms
RFP-0045l |  | Run New Cable Tray from Cott C to Cott D Data Rooms |  | 7 | 396 | 5 | 14-Jul-23 A | 07-Feb-25 | J: 78; O: Run New Cable Tray from Cott C to Cott D Data Rooms
| RFP-0041 BLDG 9 STEAM CONDENSATE PUMP PANEL TERM |  |  | 2 | 0 | 2 | 15-Aug-25 | 18-Aug-25 | J: -103
RFP-0041e | Wire Pump 9-CP-2 |  |  | 2 | 0 | 2 | 15-Aug-25 | 18-Aug-25 | J: -103; N: Wire Pump 9-CP-2
RFP-0041f | Wire Pump 9-CP-3 |  |  | 2 | 0 | 2 | 15-Aug-25 | 18-Aug-25 | J: -103; N: Wire Pump 9-CP-3
RFP-0041d | Wire Pump 9-CP-1 |  |  | 2 | 0 | 2 | 15-Aug-25 | 18-Aug-25 | J: -103; N: Wire Pump 9-CP-1
RFP-0041g | Wire Pump 9-CP-4 |  |  | 2 | 0 | 2 | 15-Aug-25 | 18-Aug-25 | J: -103; N: Wire Pump 9-CP-4
RFP-0041h | Wire Pump 9-CP-5 |  |  | 2 | 0 | 2 | 15-Aug-25 | 18-Aug-25 | J: -103; N: Wire Pump 9-CP-5
| RFP-0042 BLDG 9 & K ADD TEMPERING VALVE |  |  | 638 | 607 | 60 | 15-Sep-22 A | 25-Apr-25 | J: 141
RFP-0042d | Add Tempering Valve to K-CSG-1 |  |  | 8 | 607 | 1 | 15-Sep-22 A | 03-Feb-25 | J: 71; J: Add Tempering Valve to K-CSG-1
RFP-0042e | Add Tempering Valve to 9-CSG-1 |  |  | 8 | 0 | 8 | 16-Apr-25 | 25-Apr-25 | J: 141; S: Add Tempe ring Valve to 9-CSG-1
| RFP-0066 BLDG 9, K, AN D L DOOR HARDWARE CHANGES |  |  | 152 | 0 | 152 | 03-Feb-25 | 05-Sep-25 | J: -50
RFP-0066e | Modify Bldg K Door Hardware |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: 84; J: Modify Bldg K Door Hardware
RFP-0066d | Modify Bldg L Door Hardware |  |  | 5 | 0 | 5 | 04-Feb-25 | 10-Feb-25 | J: 96; J: Modify Bldg L Door Hardware
RFP-0066f | Modify Bldg 9 Door Hardware |  |  | 10 | 0 | 10 | 22-Aug-25 | 05-Sep-25 | J: -87; J: Modify Bldg 9 Door Hardware
| Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 2 of 46 |  | J: TASK filter: Activity Status.
| Actual Level of Effort | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  | Original | Actual | Remaining | Start | Finish | J: Total Float; J: 2025; J: 2026; AM: 2027
|  |  |  | Duration | Duration | Duration | [30 empty] | M
[9 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
| RFP-0047 BLDG POWER CONDUIT ROUTING |  |  | 4 | 0 | 4 | 03-Feb-25 | 06-Feb-25 | J: -102
RFP-0047f | Electrical OH Rough for New Routing @ Bldg 9 Lvl G |  |  | 4 | 0 | 4 | 03-Feb-25 | 06-Feb-25 | J: -102; O: Electrical OH Rough for New Routing @ Bldg 9 Lvl G
| CASE-00130 ANTI SCALD MIXING VALVES FOR SINKS |  |  | 138 | 104 | 55 | 05-Sep-24 A | 18-Apr-25 | J: 91
C-00130j | Install 3 Anti Scald Valves @ COMM |  |  | 2 | 104 | 1 | 05-Sep-24 A | 03-Feb-25 | J: 145; J: Install 3 Anti Scald Valves @ COMM
C-00130h | Install 10 Anti Scald Valves @ 9 |  |  | 2 | 0 | 2 | 17-Apr-25 | 18-Apr-25 | J: -4; S: Install 10 Anti Scald Valves @ 9
| RFP-0084 COTTAGES DRAIN PIPE MISC CHANGES |  |  | 53 | 0 | 53 | 10-Feb-25 | 23-Apr-25 | J: 81
RFP-0084d | Install Sink Drain Concealment @ Ctg H |  |  | 2 | 0 | 2 | 10-Feb-25 | 11-Feb-25 | J: 127; A: Install Sink Drain Concealment @ Ctg H
RFP-0084e | Install Sink Drain Concealment @ Ctg EFG |  |  | 5 | 0 | 5 | 05-Mar-25 | 11-Mar-25 | J: 112; O: Install Sink Drain Concealment @ Ctg EFG
RFP-0084f | Install Sink Drain Concealment @ Ctg CD |  |  | 3 | 0 | 3 | 21-Apr-25 | 23-Apr-25 | J: 81; N: Install Sink Drain Concealment @ Ctg CD
| RFP-0051 TEMP KITCHEN HALLWAY DOOR INFILL |  |  | 2 | 0 | 2 | 20-Apr-26 | 21-Apr-26 | J: -132
RFP-0051d | Infill Door in Vestibule @ Loading Dock |  |  | 2 | 0 | 2 | 20-Apr-26 | 21-Apr-26 | J: -132; O: Infill Door in Vestibule @ Loading Dock
| RFP-0069 COTTAGE J-K ELIMINATE 2" PC LINE |  |  | 12 | 871 | 3 | 01-Sep-21 A | 27-Mar-25 | J: 65
RFP-0069f | Resize/Reroute MP from Bldg 9 to Bldg K |  |  | 12 | 871 | 3 | 01-Sep-21 A | 27-Mar-25 | J: 65; O: Resize/Reroute MP from Bldg 9 to Bldg K
| S-0231 ADDED SOFFIT WORK IN B LDG 9 |  |  | 15 | 0 | 15 | 10-Jun-25 | 30-Jun-25 | J: -154
S-0231c |  | Install Soffits @ Exterior Windows without Radiant Panels @ Bldg 9G |  | 15 | 0 | 15 | 10-Jun-25 | 30-Jun-25 | J: -154; M: Install Soffits @ Exterior Windows without Radiant Panels @ Bldg 9G
| RFP-0101 9G - DELETE SINK P-505 IN ROOM B9072 |  |  | 1 | 0 | 1 | 06-Oct-25 | 06-Oct-25 | J: -93
RFP-0101d | Delete Sink in Soiled Utility Room B9072 |  |  | 1 | 0 | 1 | 06-Oct-25 | 06-Oct-25 | J: -93; A: Delete Sink in Soiled Utility Room B9072
| CASE-00117 P-609 WATER COOLER CHANGE |  |  | 1 | 0 | 1 | 17-Apr-25 | 17-Apr-25 | bar: J
C-00117d |  | Modify P-609 to Bottle Filling Stations in 3 Locations @ B9 |  | 1 | 0 | 1 | 17-Apr-25 | 17-Apr-25 | J: -3; J: Modify P-609 to Bottle Filling Stations in 3 Locations @ B9
| CASE-00128 RELOCATE COTTAGE OA DAMPERS TO ATTIC |  |  | 4 | 0 | 4 | 03-Feb-25 | 06-Feb-25 | J: 140
C-00128e |  | Extend Sheathing Over Attic Floor for Maint. Access to AHU Dampers |  | 4 | 0 | 4 | 03-Feb-25 | 06-Feb-25 | J: 140; D: Extend Sheathing Over Attic Floor for Maint. Access to AHU Dampers
| CASE-00164 LADDER CABLE TRAY TO WIRE BASKET |  |  | 387 | 370 | 49 | 21-Aug-23 A | 10-Apr-25 | J: 95
C-00164i | Install Wire Basket Trays @ Bldg K |  |  | 2 | 370 | 1 | 21-Aug-23 A | 03-Feb-25 | J: 86; J: Install Wire Basket Trays @ Bldg K
C-00164h | Install Wire Basket Trays @ WW |  |  | 2 | 0 | 2 | 28-Feb-25 | 03-Mar-25 | J: 123; A: Install Wire Basket Trays @ WW
C-00164j | Install Wire Basket Trays @ Bldg 9 |  |  | 2 | 0 | 2 | 09-Apr-25 | 10-Apr-25 | J: -98; S: Install Wire Basket Trays @ Bldg 9
BLDG 3 OPTION |  |  |  | 14 | 802 | 370 | 09-Dec-21 A | 15-Jul-26 | J: -169
BLDG3-180 | LOE Building 3 Renovations |  |  | 14 | 802 | 370 | 09-Dec-21 A | 15-Jul-26 | J: -169; N: LOE Building 3 Renovations
| CASE-00095 CLC/COTTAGE WALL & CEILING CHANGES |  |  | 121 | 126 | 15 | 05-Aug-24 A | 21-Feb-25 | J: 115
C-00095f | Install Soffit to Conceal Plbg/Cable Tray @ 1K025 |  |  | 4 | 126 | 1 | 05-Aug-24 A | 03-Feb-25 | J: 86; S: Install Soffit to Conceal Plbg/Cable Tray @ 1K025
C-00095g | Lower Ceiling to 8 ft @ 1K001 |  |  | 3 | 0 | 3 | 19-Feb-25 | 21-Feb-25 | J: 115; J: Lower Ceiling to 8 ft @ 1K001
| CASE-00183 1K004 CHAPEL SCULPTURAL WALL SUPPORTS |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 73
C-00183i | Extend Wood Linear Ceiling @ Bldg K Chapel |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 73; S: Extend Wood Linear Ceiling @ Bldg K Chapel
| CASE-00108 BLDG 9 RADIANT PANEL CONTROLS |  |  | 58 | 107 | 24 | 30-Aug-24 A | 06-Mar-25 | J: -100
C-00108g |  | Install Additional Branch Piping and Control Valves for RP @ B9 2 |  | 10 | 107 | 9 | 30-Aug-24 A | 13-Feb-25 | J: -85; D: Install Additional Branch Piping and Control Va lves for RP @ B9 2
C-00108e |  | Install Additional Branch Piping and Control Valves for RP @ B9 G |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: -89; D: Install Additional Branch Piping and Control Valves for RP @ B9 G
C-00108f |  | Install Additional Branch Piping and Control Valves for RP @ B9 1 |  | 10 | 0 | 10 | 21-Feb-25 | 06-Mar-25 | J: -115; D: Install Additional Branch Piping and Control Valves for RP @ B9 1
| CASE-00161 BLDG 9 - INSTALL ANTI LIGATURE SYSTEM |  |  | 137 | 0 | 137 | 17-Mar-25 | 26-Sep-25 | J: -87
C-00161e |  | Install Controller and Wiring for ALAS @ Bldg 9 1st Floor |  | 12 | 0 | 12 | 17-Mar-25 | 01-Apr-25 | J: 10; D: Install Controller and Wiring for ALAS @ Bldg 9 1st Floor
C-00161f |  | Install Controller and Wiring for ALAS @ Bldg 9 2nd Floor |  | 12 | 0 | 12 | 28-Apr-25 | 13-May-25 | J: -148; J: Install Controller and Wiring for ALAS @ Bldg 9 2nd Floor
C-00161c | Install Door Hardware for ALAS @ Bldg 9 1st Floor |  |  | 10 | 0 | 10 | 11-Sep-25 | 24-Sep-25 | J: -85; M: Install Door Hardware for ALAS @ Bldg 9 1st Floor
C-00161d | Install Door Hardware for ALAS @ Bldg 9 2nd Floor |  |  | 10 | 0 | 10 | 15-Sep-25 | 26-Sep-25 | J: -87; M: Install Door Hardware for ALAS @ Bldg 9 2nd Floor
| CASE-00155 COTTAGE & CLC TOILET, BATHROOM ACCESSORIES |  |  | 78 | 0 | 78 | 10-Feb-25 | 29-May-25 | J: 63
C-00155g | Install VA Toilet Ac ces sories @ Bldg HIJ |  |  | 11 | 0 | 11 | 10-Feb-25 | 24-Feb-25 | J: 123; S: Install VA Toilet Ac ces sories @ Bldg HIJ
C-00155f | Install VA Toilet Ac ces sories @ Bldg EFG |  |  | 11 | 0 | 11 | 06-Mar-25 | 20-Mar-25 | J: 105; O: Install VA Toilet Ac ces sories @ Bldg EFG
C-00155e | Install VA Toilet Ac ces sories @ Bldg CD |  |  | 8 | 0 | 8 | 28-Apr-25 | 07-May-25 | J: 71; N: Install VA Toilet Ac ces sories @ Bldg CD
C-00155d | Install VA Toilet Ac ces sories @ Bldg K |  |  | 2 | 0 | 2 | 28-May-25 | 29-May-25 | J: 63; N: Install VA Toilet Ac ces sories @ Bldg K
| CASE-00195 COTTAGE LADDER DEFLECTOR PLATES |  |  | 4 | 0 | 4 | 03-Feb-25 | 06-Feb-25 | J: 135
C-00195e | Install Ladder Deflector Plates @ 1H031/1l030 |  |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: 137; S: Install Ladder Deflector Plates @ 1H031/1l030
| Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 3 of 46 |  | J: TASK filter: Activity Status.
| Actual Level of Effort | Remaining Work | Milestone | [5 empty] | D: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  | Original | Actual | Remaining | Start | Finish | J: Total Float; J: 2025; J: 2026; M: 2027
|  |  |  | Duration | Duration | Duration | [30 empty] | M
[9 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
C-00195d | Install Ladder Deflector Plate @ 1G031 |  |  | 2 | 0 | 2 | 05-Feb-25 | 06-Feb-25 | J: 135; A: Install Ladder Deflector Plate @ 1G031
| CASE-00226 BLDG K & 9 DELETE PROJECTORS & SCREENS |  |  | 81 | 0 | 81 | 31-Mar-25 | 23-Jul-25 | J: 4
C-00226d | Delete Projectors & Screens @ Bldg K |  |  | 1 | 0 | 1 | 31-Mar-25 | 31-Mar-25 | J: 84; O: Delete Projectors & Screens @ Bldg K
C-00226e | Delete Projectors & Screens @ Bldg 9 |  |  | 1 | 0 | 1 | 23-Jul-25 | 23-Jul-25 | J: -70; J: Delete Projectors & Screens @ Bldg 9
| REVERSE OSMOSIS WATER EQUIPMENT CHANGES |  |  | 4 | 433 | 1 | 22-May-23 A | 03-Feb-25 | J: 124
C-00045d | Install Water Softener @ 1K069 |  |  | 4 | 433 | 1 | 22-May-23 A | 03-Feb-25 | J: 124; J: Install Water Softener @ 1K069
| WALKWAY PIPING CHANGES |  |  | 5 | 402 | 2 | 06-Jul-23 A | 04-Feb-25 | J: 69
C-00174f | Modify Pump Condensate Line Size @ CD |  |  | 5 | 402 | 2 | 06-Jul-23 A | 04-Feb-25 | J: 69; A: Modify Pump Condensate Line Size @ CD
| EFG WALKWAY SOFFIT |  |  | 5 | 437 | 4 | 16-May-23 A | 10-Feb-25 | J: 64
C-00184d |  | Build Soffit in Walkways 10,11,12 for Pipe Cros sings @ EFG |  | 5 | 437 | 4 | 16-May-23 A | 10-Feb-25 | J: 64; N: Build Soffit in Walkways 10,11,12 for Pipe Cros sings @ EFG
| BLDG 3 STEAM CONDENSATE PUMP TERMINATION |  |  | 3 | 0 | 3 | 27-Mar-25 | 31-Mar-25 | J: 11
C-00207d |  | Pull Power from Panel GPE43G1 for Pump 3-SCP-4 @ Bldg 3 |  | 3 | 0 | 3 | 27-Mar-25 | 31-Mar-25 | J: 11; J: Pull Power from Panel GPE43G1 for Pump 3-SCP-4 @ Bldg 3
| BLDG 3 ELEVATOR HOIST BEAM |  |  | 7 | 0 | 7 | 03-Feb-25 | 11-Feb-25 | bar: J
C-00229d |  | Provide New Support Steel for Elevator Hoist Beam @ Bldg 3 |  | 7 | 0 | 7 | 03-Feb-25 | 11-Feb-25 | J: -8; N: Provide New Support Steel for Elevator Hoist Beam @ Bldg 3
| BLDG 3 DUCT BANK CHANGES |  |  | 4 | 0 | 4 | 03-Feb-25 | 06-Feb-25 | J: 135
C-00216f | Restore Site |  |  | 4 | 0 | 4 | 03-Feb-25 | 06-Feb-25 | J: 135; A: Restore Site
| CTG/WALKWAY ADD EXP JOINT INSULATION |  |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: 147
C-00236d | Add Insulation to Expansion Joint Covers @ HIJ |  |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: 122; S: Add Insulation to Expansion Joint Covers @ HIJ
C-00236e | Add Insulation to Expansion Joint Covers @ EFG |  |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: 147; S: Add Insulation to Expansion Joint Covers @ EFG
C-00236f | Add Insulation to Expansion Joint Covers @ CD |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 148; S: Add Insulation to Expansion Joint Covers @ CD
| WALKWAY STEAM PIPE CHANGES |  |  | 256 | 621 | 1 | 25-Aug-22 A | 03-Feb-25 | J: 168
C-00239f | Install MPS in Attic from D to E |  |  | 15 | 621 | 1 | 25-Aug-22 A | 03-Feb-25 | J: 168; J: Install MPS in Attic from D to E
C-00239e | Install MPS and LPS in Attic from WW458 to CD |  |  | 15 | 511 | 1 | 01-Feb-23 A | 03-Feb-25 | J: 168; S: Install MPS and LPS in Attic from WW458 to CD
C-00239d | Move HPS into Attic and Resize LPS Lines @ WW231 |  |  | 15 | 446 | 1 | 03-May-23 A | 03-Feb-25 | J: 51; O: Move HPS into Attic and Resize LPS Lines @ WW231
| CASE-00150 BLDGS 9 & K FRAMING TO CONCEAL PIPES |  |  | 385 | 302 | 66 | 27-Nov-23 A | 05-May-25 | J: 8
C-00150e | Add Soffit to Conceal Pipes @ 1K003 |  |  | 2 | 302 | 1 | 27-Nov-23 A | 03-Feb-25 | J: 73; J: Add Soffit to Conceal Pipes @ 1K003
C-00150d | Fur Out Columns for P-531 Fixtures @ Bldg 9G |  |  | 2 | 0 | 2 | 02-May-25 | 05-May-25 | J: -20; D: Fur Out Columns for P-531 Fixtures @ Bldg 9G
| CASE-00221 BLDG 3 HW UNIT HEATER CHANGE |  |  | 1 | 0 | 1 | 22-Apr-25 | 22-Apr-25 | J: 5
C-00221d | Install Cabinet Unit Heater 3-CUH-5 @ Bldg 3 03065 |  |  | 1 | 0 | 1 | 22-Apr-25 | 22-Apr-25 | J: 5; D: Install Cabinet Unit Heater 3-CUH-5 @ Bldg 3 03065
| CASE-00256 DATA RACK POWER & PDUS, CTGS, K, 3, 9 |  |  | 17 | 0 | 17 | 18-Mar-25 | 09-Apr-25 | J: -61
C-00256i | Upgrade Data Rack and PDU @ Bldg 3 |  |  | 1 | 0 | 1 | 18-Mar-25 | 18-Mar-25 | J: -45; S: Upgrade Data Rack and PDU @ Bldg 3
C-00256h | Upgrade Data Rack and PDU @ Bldg 9 |  |  | 1 | 0 | 1 | 09-Apr-25 | 09-Apr-25 | J: -97; O: Upgrade Data Rack and PDU @ Bldg 9
| CASE 00166 BLDG 9 FINISH CHANGES |  |  | 27 | 0 | 27 | 03-Jul-25 | 11-Aug-25 | J: -126
C-00166d | Wall and F looring Finish C hang es @ Bldg 9 G |  |  | 10 | 0 | 10 | 03-Jul-25 | 17-Jul-25 | J: -109; F: Wall a nd F looring Finish C ha nges @ Bldg 9 G
C-00166e | Wall and F looring Finish C hang es @ Bldg 9 1 |  |  | 10 | 0 | 10 | 11-Jul-25 | 24-Jul-25 | J: -135; F: Wall a nd F looring Finish C ha nges @ Bldg 9 1
C-00166f | Wall and F looring Finish C hang es @ Bldg 9 2 |  |  | 10 | 0 | 10 | 29-Jul-25 | 11-Aug-25 | J: -147; M: Wall a nd F looring Finish C ha nges @ Bldg 9 2
| CASE 00255 ADD BRICK FOR BUILDING 3 |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 101
C-00255d | Purchase New Brick for Openings @ Bldg 3 |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 101; A: Purchase New Brick for Openings @ Bldg 3
| CASE 00181 PYXIS UNIT ROOM CHANGES |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 149
C-00181e | Pyxis Unit Room Door Hardware Material Changes CD |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 74; O: Pyxis Unit Room Door Hardware Material Changes CD
C-00181h | Pyxis Unit Room Door Hardware Material Changes EFG |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 150; O: Pyxis Unit Room Door Hardware Material Changes EFG
C-00181k | Pyxis Unit Room Door Hardware Material Changes HIJ |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 96; O: Pyxis Unit Room Door Hardware Material Changes HIJ
C-00181m | Pyxis Unit Room Electrical Changes Bldg K |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 131; A: Pyxis Unit Room Electrical Changes Bldg K
C-00181f | Pyxis Unit Room Door Hardware Labor Changes CD |  |  | 3 | 0 | 3 | 04-Feb-25 | 06-Feb-25 | J: 74; O: Pyxis Unit Room Door Hardware Labor Changes CD
C-00181l | Pyxis Unit Room Door Hardware Labor Changes HIJ |  |  | 3 | 0 | 3 | 04-Feb-25 | 06-Feb-25 | J: 96; O: Pyxis Unit Room Door Hardware Labor Changes HIJ
C-00181i | Pyxis Unit Room Door Hardware Labor Changes EFG |  |  | 3 | 0 | 3 | 05-Feb-25 | 07-Feb-25 | J: 149; O: Pyxis Unit Room Door Hardware Labor Changes EFG
| CASE 00251 BLDG K EUCHARIST ROOM SINK |  |  | 2 | 400 | 1 | 10-Jul-23 A | 03-Feb-25 | J: 128
C-00251c | Bldg K Eucharist Sink |  |  | 2 | 400 | 1 | 10-Jul-23 A | 03-Feb-25 | J: 128; M: Bldg K Eucharist Sink
| Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 4 of 46 |  | J: TASK filter: Activity Status.
| Actual Level of Effort | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  | Original | Actual | Remaining | Start | Finish | Total Float | M: 2025; J: 2026; F: 2027
|  |  | Duration | Duration | Duration | bar: A
[8 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
| CASE 00259 BLDG K DOOR, HW & CARED READER CHANGES |  | 3 | 278 | 1 | 02-Jan-24 A | 19-Feb-25 | J: 123
C-00259d | Bldg K Door, HW & Card Reader Changes |  | 3 | 278 | 1 | 02-Jan-24 A | 19-Feb-25 | J: 123; S: Bldg K Door, HW & Card Reader Changes
| CASE 00281 BLDG 9 & 50 STEAM CONDENSATE METERS |  | 129 | 150 | 1 | 01-Jul-24 A | 03-Feb-25 | J: 148
C-00281d | Building 50 Steam Condensate Meters |  | 1 | 150 | 1 | 01-Jul-24 A | 03-Feb-25 | J: 148; A: Building 50 Steam Condensate Meters
C-00281c | Building 9 Steam Condensate Meters |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: -83; J: Building 9 Steam Condensate Meters
| CASE 00190 BLDG 9 LAUNDRY & DISHWASHER CHANGES |  | 19 | 52 | 5 | 18-Nov-24 A | 04-Mar-25 | J: 29
C-00190e | Building 9 Added Water Softner at Dishwasher |  | 1 | 52 | 1 | 18-Nov-24 A | 26-Feb-25 | J: 33; O: Building 9 Added Water Softner at Dishwasher
C-00190d | Building 9 Laundry Room Changes |  | 5 | 0 | 5 | 26-Feb-25 | 04-Mar-25 | J: 29; A: Building 9 Laundry Room Changes
| CASE 00212 BLDG K DOWNSPOUT TIE-IN TO STORM SYSTEM |  | 2 | 81 | 1 | 08-Oct-24 A | 13-Mar-25 | J: 127
C-00212d | Bldg K Added Downspout Boots |  | 2 | 81 | 1 | 08-Oct-24 A | 13-Mar-25 | J: 127; A: Bldg K Added Downspout Boots
| CASE 00232 BLDG 3 - CHW & PC METERS |  | 5 | 0 | 5 | 04-Feb-25 | 10-Feb-25 | J: 56
C-00232d | Installed Chilled Water and D P Sensor in Bldg 3 |  | 5 | 0 | 5 | 04-Feb-25 | 10-Feb-25 | J: 56; S: Installed Chilled Water and D P Sensor in Bldg 3
| CASE 00246 BLDG K REMOVE PV SYSTEM |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 178
C-00246d | Bldg K Remove PV System |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 178; J: Bldg K Remove PV System
| CASE 00265 BLDG L & EXISTING WKWYS HVAC CHANGES |  | 2 | 0 | 2 | 12-Feb-25 | 13-Feb-25 | J: 90
C-00265d | Bldg L & Existing Wkwys HVAC Changes |  | 2 | 0 | 2 | 12-Feb-25 | 13-Feb-25 | J: 90; S: Bldg L & Existing Wkwys HVAC Changes
CASE 00297 BLDG 3 ASI-002 |  |  | 165 | 81 | 138 | 08-Oct-24 A | 15-Aug-25 | J: -56
C-00297d | Installed Chilled Water Lines @ Bldg 3 G |  | 30 | 81 | 19 | 08-Oct-24 A | 27-Feb-25 | J: -115; S: Installed Chilled Water L in es @ Bldg 3 G
C-00297f | Install Fire Alarm Annunciator @ Bldg 3 03054 |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 57; S: Install Fire Alarm Annunciator @ Bldg 3 03054
C-00297g | Telecom Changes @ Bldg 3 |  | 15 | 0 | 15 | 03-Feb-25 | 21-Feb-25 | J: -111; J: Telecom Changes @ Bldg 3
C-00297e | Door Hardware Changes @ Bldg 3 |  | 3 | 0 | 3 | 13-Aug-25 | 15-Aug-25 | J: -56; J: Door Hardware Changes @ Bldg 3
| CASE 00094 BLDG 9 PORCELAIN TILE FINISH CHANGES |  | 58 | 0 | 58 | 02-May-25 | 24-Jul-25 | J: -114
C-00094f | Install Gyp Board @ B9045C, B9045D |  | 2 | 0 | 2 | 02-May-25 | 05-May-25 | J: -115; N: Install Gyp Board @ B9045C, B9045D
C-00094d | Install Full Height Wall Tile @ B9012, B9045, B9045A, B9031, B9033, B9035, B9035A |  | 7 | 0 | 7 | 02-Jun-25 | 10-Jun-25 | J: -83; J: Install Full Height Wall Tile @ B9012, B9045, B9045A, B9031, B9033, B9035, B9
C-00094e | Install Stainless Steel Corner Guards at Kitchen Area Rooms |  | 5 | 0 | 5 | 18-Jul-25 | 24-Jul-25 | J: -126; A: Install Stainless Steel Corner Guards at Kitchen Area Rooms
| CASE 00231 BLDG K BOTTLELESS WATER FILLER |  | 4 | 431 | 1 | 24-May-23 A | 03-Feb-25 | J: 124
C-00231d | Install In-Wall Bottle F iller @ 1K036 |  | 4 | 431 | 1 | 24-May-23 A | 03-Feb-25 | J: 124; J: Install In-Wall Bottle F iller @ 1K036
| CASE 00293 BLDG 9 ELECTRICAL CHANGES |  | 339 | 446 | 125 | 03-May-23 A | 29-Jul-25 | J: -89
C-00293d | Adjust Light Fixtures and Circuits @ Bldg 9 |  | 15 | 446 | 1 | 03-May-23 A | 03-Feb-25 | J: -156; A: Adjust Light Fixtures and Circuits @ Bldg 9
C-00293h | Adjust Cable Tray Routing @ Bldg 9 |  | 15 | 0 | 15 | 26-Feb-25 | 18-Mar-25 | J: -91; S: Adjust Cable Tray Routing @ Bldg 9
C-00293i | Increase Disconnect Size for 9-AHU-3 |  | 5 | 0 | 5 | 23-Jul-25 | 29-Jul-25 | J: -89; J: Increase Disconnect Size for 9-AHU-3
| CASE 00295 BLDG 9 ASI-001 PHYSICAL CHANGES |  | 162 | 188 | 122 | 07-May-24 A | 24-Jul-25 | J: -71
C-00295j | Install Automatic Pump Traps for AHUs @ Bldg 9 |  | 12 | 188 | 1 | 07-May-24 A | 22-Jul-25 | J: -119; M: Install Automatic Pump Traps for AHUs @ Bldg 9
C-00295f | Widen Walls to Accommodate Plumbing Fixtures @ Bldg 9 |  | 5 | 72 | 4 | 21-Oct-24 A | 06-Feb-25 | J: -97; N: Widen Walls to Accommodate Plumbing Fixtures @ Bldg 9
C-00295g | Upsize Exhaust Fan 9 EF-4 @ Bldg 9 |  | 2 | 30 | 1 | 19-Dec-24 A | 12-Mar-25 | J: -52; S: Upsize Exhaust Fan 9 EF-4 @ Bldg 9
C-00295e | Modify Laundry Sink, Handwashing Sinks and Showers per RFIs |  | 5 | 0 | 5 | 26-Feb-25 | 04-Mar-25 | J: 29; D: Modify Laundry Sink, Handwashing Sinks and Showers per RFIs
C-00295l | Provide/Install Additional Fire/Smoke Dampers per ASI @ Bldg 9 |  | 20 | 0 | 20 | 26-Feb-25 | 25-Mar-25 | J: -141; J: Provide/Install Additional Fire/Smoke Dampers per ASI @ Bldg 9
C-00295h | Offset Cable Tray Where in Conflict with Beams @ Bldg 9 |  | 10 | 0 | 10 | 09-Apr-25 | 22-Apr-25 | J: -93; J: Offset Cable Tray Where in Conflict with Beams @ Bldg 9
C-00295k | Modify Chilled Water Piping on 3rd F loor and Pro vide Heat Trace @ Bldg 9 |  | 20 | 0 | 20 | 26-Jun-25 | 24-Jul-25 | J: -119; J: Modify Chilled Water Piping on 3rd F loor and Provide Heat Trace @ Bldg 9
| CASE 00301 BLDG 9 ASI-001 PHYSICAL CHANGES |  | 3 | 0 | 3 | 03-Feb-25 | 05-Feb-25 | J: 13
C-00301c | Expand B9012 to Include B9012D, Relocate Kitchen Equipment |  | 3 | 0 | 3 | 03-Feb-25 | 05-Feb-25 | J: 13; N: Expand B9012 to Include B9012D, Relocate Kitchen Equipment
| CASE 00312 PH1 TO PH2 - CONSTRUCTION FENCING & HAUL |  | 356 | 361 | 341 | 01-Sep-23 A | 03-Jun-26 | J: -161
C-00312o | Bldg 3 Access Inefficiencies |  | 100 | 361 | 25 | 01-Sep-23 A | 07-Mar-25 | J: 155; J: Bldg 3 Access Inefficiencies
C-00312i | Restore Bldg 2 Laydown Area |  | 3 | 0 | 3 | 03-Feb-25 | 05-Feb-25 | J: 168; J: Restore Bldg 2 Laydown Area
C-00312q | Restore Bldg 3 Access Point |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: 155; J: Restore Bldg 3 Access Point
C-00312j | Remove Bldg 2 Laydown Fencing |  | 8 | 0 | 8 | 06-Feb-25 | 17-Feb-25 | J: 168; J: Remove Bldg 2 Laydown Fencing
C-00312k | Replace Sidewalks Impacted by Laydown East of Bldg 3 |  | 3 | 0 | 3 | 21-May-26 | 26-May-26 | J: -162; N: Replace Sidewalks Impacted by Laydow
C-00312l | Restore Bldg 3 Laydown Area |  | 3 | 0 | 3 | 27-May-26 | 29-May-26 | J: -162; O: Restore Bldg 3 Laydown Area
Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 5 of 46 |  | J: TASK filter: Activity Status.
Actual Level of Effort | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  | Original | Actual | Remaining | Start | Finish | J: Total Float; J: 2025; J: 2026; M: 2027
|  |  | Duration | Duration | Duration | [30 empty] | M
[8 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
C-00312m | Remove Bldg 3 Laydown Fencing |  | 3 | 0 | 3 | 01-Jun-26 | 03-Jun-26 | J: -162; N: Remove Bldg 3 Laydown Fencing
| CASE 00313 PH1 TO PH2 - LANDSCAPING IN COURTYARD #1 |  | 134 | 135 | 6 | 23-Jul-24 A | 10-Feb-25 | J: 173
C-00313h | Form and Pour Patio/Sidewalk |  | 3 | 135 | 1 | 23-Jul-24 A | 03-Feb-25 | J: 173; J: Form and Pour Patio/Sidewalk
C-00313i | Install Sidewalk Expansion Joints |  | 3 | 135 | 1 | 23-Jul-24 A | 03-Feb-25 | J: 173; J: Install Sidewalk Expansion Joints
C-00313j | Fine Grade/Landscape Courtyard |  | 5 | 0 | 5 | 04-Feb-25 | 10-Feb-25 | J: 173; J: Fine Grade/Landscape Courtyard
| CASE 00315 PH1 TO PH2 - TRAILERS AND LAYDOWN |  | 473 | 481 | 25 | 15-Mar-23 A | 07-Mar-25 | J: 154
C-00315c | Trailer Rental and Maintenance |  | 100 | 481 | 10 | 15-Mar-23 A | 14-Feb-25 | J: 169; J: Trailer Rental and Maintenance
C-00315d | Mowing and Snow Removal |  | 100 | 448 | 10 | 01-May-23 A | 14-Feb-25 | J: 169; J: Mowing and Snow Removal
C-00315f | Laydown Restoration |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: 169; J: Laydown Restoration
C-00315i | Trailer Rental and Maintenance Part 2 |  | 25 | 0 | 25 | 03-Feb-25 | 07-Mar-25 | J: 154; S: Trailer Rental and Maintenance Part 2
| CASE 00335 BLDG 9 UNIT 2A SOFFIT |  | 20 | 0 | 20 | 09-Apr-25 | 06-May-25 | J: -130
C-00335c | Install Soffit to Conceal Duct @ 19003 and 19082 |  | 1 | 0 | 1 | 09-Apr-25 | 09-Apr-25 | J: -126; N: Install Soffit to Conceal Duct @ 19003 and 19082
C-00335d | Install Soffit to Conceal Duct @ 29003 and 29082 |  | 1 | 0 | 1 | 06-May-25 | 06-May-25 | J: -130; D: Install Soffit to Conceal Duct @ 29003 and 29082
| CASE 00328 BUILDING 3 ATS CREDIT |  | 1 | 0 | 1 | 04-Feb-25 | 04-Feb-25 | J: -66
C-00328d | Use Phase 1 Material for Bldg 3 ATS |  | 1 | 0 | 1 | 04-Feb-25 | 04-Feb-25 | J: -66; A: Use Phase 1 Material for Bldg 3 ATS
| CASE 00308 BLDG 3 DELETE PROJECTORS & SCREENS |  | 1 | 0 | 1 | 15-Oct-25 | 15-Oct-25 | J: -48
C-00308d | Delete Projectors and Screens @ Bldg 3 |  | 1 | 0 | 1 | 15-Oct-25 | 15-Oct-25 | J: -48; A: Delete Projectors and Screens @ Bldg 3
| CASE 00320 BLDG K STOREFRONT AT WATER ROOM 1K069 |  | 1 | 0 | 1 | 04-Feb-25 | 04-Feb-25 | J: 144
C-00320e | Install Additional Fire Standpipes @ 1K069 |  | 1 | 0 | 1 | 04-Feb-25 | 04-Feb-25 | J: 144; A: Install Additional Fire Standpipes @ 1K069
| CASE 00327 COTTAGES & BLDG K DRAIN BACKWATER VALVES |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 145
C-00327g | Install Backwater Valves for Exterior Pipes @ Bldg K |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 145; O: Install Backwater Valves for Exterior Pipes @ Bldg K
| CASE 00332 BLDG 3 INCREASE ELEVATOR 3-2 FEEDER SIZE |  | 1 | 0 | 1 | 11-Feb-25 | 11-Feb-25 | J: 123
C-00332d | Install Larger Feeder for Elevator 3-2 @ Bldg 3 |  | 1 | 0 | 1 | 11-Feb-25 | 11-Feb-25 | J: 123; S: Install Larger Feeder for Elevator 3-2 @ Bldg 3
| CASE 00348 ADDITIONAL ASBESTOS QUANTITIES |  | 474 | 404 | 370 | 01-Jul-23 A | 15-Jul-26 | J: -169
C-00348e | Additional Abatement Funding LOE |  | 474 | 404 | 370 | 01-Jul-23 A | 15-Jul-26 | J: -169; D: Additional Abatement Funding LO
| CASE 00151 BLDG 9 WINDOW TYPE 92 & EXISTING FRAMES |  | 7 | 73 | 3 | 18-Oct-24 A | 17-Feb-25 | J: 43
C-00151f | Install New Windows for Type 92 Change on Bldg 9 |  | 7 | 73 | 3 | 18-Oct-24 A | 17-Feb-25 | J: 43; O: Install New Windows for Type 92 Change on Bldg 9
| CASE 00317 BLDG 9 P-101 FLUSH VALVE |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 45
C-00317d | Provide Exposed Flush Valve for P-101 Water Closets @ Bldg 9 |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 45; N: Provide Exposed Flush Valve for P-101 Water Closets @ Bldg 9
| CASE 00326 BLDG 3 ADD FAR 52.204-24 & 52.204-25 |  | 1 | 287 | 1 | 18-Dec-23 A | 03-Feb-25 | J: 51
C-00326d | Purchase Cameras for Bldg 3 that Comply with Updated FARS |  | 1 | 287 | 1 | 18-Dec-23 A | 03-Feb-25 | J: 51; N: Purchase Cameras for Bldg 3 that Comply with Updated FARS
| CASE 00351 BLDG 9 LOUVER 44 MASONRY INFILL |  | 1 | 55 | 1 | 13-Nov-24 A | 13-Feb-25 | J: 71
C-00351c | Infill Opening 44 with Brick @ Bldg 9 |  | 1 | 55 | 1 | 13-Nov-24 A | 13-Feb-25 | J: 71; A: Infill Opening 44 with Brick @ Bldg 9
| CASE 00187 COTTAGE CD DOOR HARDWARE & WANDERGUARD |  | 4 | 344 | 1 | 27-Sep-23 A | 03-Feb-25 | J: 89
C-00187d | Add Wanderguard Panel for Door s 1 C019 and 1D019 |  | 4 | 344 | 1 | 27-Sep-23 A | 03-Feb-25 | J: 89; O: Add Wanderguard Panel for Do or s 1C019 and 1D019
| CASE 00263 BLDG K, L & WALKWAYS DOOR HARDWARE |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 165
C-00263d | Modify Gaskets and Hinges for Aluminum Frames @ Walkways |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 165; N: Modify Gaskets and Hinges for Aluminum Frames @ Walkways
C-00263e | Modify Gaskets and Hinges for Aluminum Frames @ Bldg K |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 86; N: Modify Gaskets and Hinges for Aluminum Frames @ Bldg K
| CASE 00304 BLDG L FOUNDATION WALL |  | 16 | 0 | 16 | 03-Feb-25 | 24-Feb-25 | J: 100
C-00304g | Install New Rafters for Connections @ L |  | 3 | 0 | 3 | 03-Feb-25 | 05-Feb-25 | J: 100; A: Install New Rafters for Connections @ L
C-00304h | Replace Roof for Connections @ L |  | 3 | 0 | 3 | 06-Feb-25 | 10-Feb-25 | J: 100; A: Replace Roof for Connections @ L
C-00304i | Install New Arches Ceiling for Connections @ L |  | 10 | 0 | 10 | 11-Feb-25 | 24-Feb-25 | J: 100; O: Install New Arches Ceiling for Connections @ L
| CASE 00341 SITEWORK - ADDITIONAL SWPP |  | 365 | 360 | 146 | 05-Sep-23 A | 27-Aug-25 | J: 33
C-00341d | Inlet Protection and Maint from Phase 1 |  | 365 | 360 | 146 | 05-Sep-23 A | 27-Aug-25 | J: 33; F: Inlet Protection and Maint from Phase 1
| CASE 00362 NEW WALKWAYS PIPE EXPANSION JOINTS |  | 10 | 274 | 4 | 08-Jan-24 A | 28-Mar-25 | J: 66
C-00362f | Install Metragator Expansion Joints in Walk ways |  | 10 | 274 | 4 | 08-Jan-24 A | 28-Mar-25 | J: 66; N: Install Metragator Expansion Joints in Walk ways
| CASE 00329 BLDG 9 BEAM FLANGE HOLES FOR DRAIN PIPES |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: -119
C-00329d | Core Drill Overhang Flange for Sanitary Drain Lines @ Bldg 9 |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: -119; N: Core Drill Overhang Flange for Sanitary Drain Lines @ Bldg 9
Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 6 of 46 |  | J: TASK filter: Activity Status.
Actual Level of Effort | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  | Original | Actual | Remaining | Start | J: Finish; F: Total Float; J: 2025; A: 2026; A: 2027
|  |  |  | Duration | Duration | Duration | [30 empty] | M
[9 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
| CASE 00330 BLDG 9 DELETE ROOM B9076 & ENGLARGE B9078 |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 178
C-00330d | Delete Room B9076 @ Bldg 9 |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 178; J: Delete Room B9076 @ Bldg 9
| CASE 00337 BLDG 9 DOOR HARDWARE CHANGES |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 64
C-00337d | Supply Additional Door Closers for 7 Doors in Bldg 9 |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 64; S: Supply Additional Door Closers for 7 Doors in Bldg 9
| CASE 00354 BLDG 9 SHOWER & KITCHEN PLUMBING CHANGES |  |  | 1 | 0 | 1 | 26-Feb-25 | 26-Feb-25 | J: 33
C-00354f |  | Adjust Kitchen Domestic Routing and Fixture Type @ Bldg 9 |  | 1 | 0 | 1 | 26-Feb-25 | 26-Feb-25 | J: 33; N: Adjust Kitchen Domestic Routing and Fixture Type @ Bldg 9
| CASE 00309 BUILDING 9 TRAINING KITCHEN CHANGES |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 112
C-00309d |  | Delete Electrical Work Associated with Training Kitchen @ Bldg 9 |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 112; N: Delete Electrical Work Associated with Training Kitchen @ Bldg 9
| CASE 00310 CONCRETE MOWING STRIP CHANGES |  |  | 15 | 211 | 7 | 04-Apr-24 A | 11-Feb-25 | J: 172
C-00310d | Replace Concrete Mow Strips with Gravel |  |  | 15 | 211 | 7 | 04-Apr-24 A | 11-Feb-25 | J: 172; A: Replace Concrete Mow Strips with Gravel
| CASE 00347 BLDG 9 ELEC/DATA RM REFRIGERANT RISERS |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: -66
C-00347d |  | Conceal Pipe Risers Inside a Chase for Teledata Roooms @ Bldg 9 |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: -66; D: Conceal Pipe Risers Inside a Chase for Teledata Roooms @ Bldg 9
| CASE 00359 BLDG 3 RM 33010 DEMO ADD'L SLAB |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: 120
C-00359d |  | Sawcut and Remove Slab from Elevator Lobby @ Bldg 3 33010 |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: 120; D: Sawcut and Remove Slab from Elevator Lobby @ Bldg 3 33010
| CASE 00321 BLDG 9 - LEVEL 3 PEAK FIRE SUPPRESSION |  |  | 7 | 0 | 7 | 03-Feb-25 | 11-Feb-25 | J: 70
C-00321d |  | Install GWB Lid Under Steel Above AHU-2 @ Bldg 9 Lvl 3 |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 70; O: Install GWB Lid Under Steel Above AHU-2 @ Bldg 9 Lvl 3
C-00321e | Install Sprinklers Under GWB Lid @ Bldg 9 Lvl 3 |  |  | 2 | 0 | 2 | 10-Feb-25 | 11-Feb-25 | J: 70; S: Install Sprinklers Under GWB Lid @ Bldg 9 Lvl 3
| CASE 00336 BLDG K, 3, 9 HHW SYSTEMS HEAT EXCHANGER |  |  | 3 | 0 | 3 | 03-Feb-25 | 05-Feb-25 | J: -104
C-00336e | Install Isolation Valves on Heat Exchangers @ Bldg 9 |  |  | 3 | 0 | 3 | 03-Feb-25 | 05-Feb-25 | J: -113; S: Install Isolation Valves on Heat Exchangers @ Bldg 9
C-00336f | Install Isolation Valves on Heat Exchangers @ Bldg 3 |  |  | 3 | 0 | 3 | 03-Feb-25 | 05-Feb-25 | J: -104; S: Install Isolation Valves on Heat Exchangers @ Bldg 3
| CASE 00353 BLDG 9 & K STEAM CHANGES |  |  | 6 | 0 | 6 | 03-Feb-25 | 10-Feb-25 | J: -116
C-00353e | Add Pump Trap for Heat Exchangers and CSG @ Bldg 9 |  |  | 6 | 0 | 6 | 03-Feb-25 | 10-Feb-25 | J: -116; O: Add Pump Trap for Heat Exchangers and CSG @ Bldg 9
| CASE 00397 BLDG 9 & 3 MEP HANGER LOADS & STEEL |  |  | 24 | 0 | 24 | 03-Feb-25 | 06-Mar-25 | J: -129
| CASE 00397 - BUILDING 9 |  |  | 24 | 0 | 24 | 03-Feb-25 | 06-Mar-25 | J: -169
| BUILDING 9 - 1ST FLOOR |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: -169
C-00397bj | Install Additional Hangers - Plumbing @ Bldg 9 1st |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: -169; S: Install Additional Hangers - Plumbing @ Bldg 9 1st
C-00397bk | Install Additional Hangers - HVAC Piping @ Bldg 9 1st |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: -169; O: Install Additional Hangers - HVAC Piping @ Bld g 9 1st
C-00397bl | Install Additional Hangers - HVAC Duct @ Bldg 9 1st |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: -169; O: Install Additional Hangers - HVAC Duct @ Bldg 9 1 st
C-00397bm | Install Additional Hangers - Electrical @ Bldg 9 1st |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: -169; S: Install Additional Hangers - Electrical @ Bldg 9 1st
C-00397bn |  | Install Additional Hangers - Fire Suppression @ Bldg 9 1st |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: -169; N: Install Additional Hangers - Fire Suppression @ Bldg 9 1st
| BUILDING 9 - 2ND FLOOR |  |  | 10 | 0 | 10 | 21-Feb-25 | 06-Mar-25 | J: -169
C-00397bo | Install Additional Hangers - Plumbing @ Bldg 9 2nd |  |  | 10 | 0 | 10 | 21-Feb-25 | 06-Mar-25 | J: -169; O: Install Additional Hangers - Plumbing @ Bldg 9 2nd
C-00397bp | Install Additional Hangers - HVAC Piping @ Bldg 9 2nd |  |  | 10 | 0 | 10 | 21-Feb-25 | 06-Mar-25 | J: -169; N: Install Additional Hangers - HVAC Piping @ Bldg 9 2nd
C-00397bq | Install Additional Hangers - HVAC Duct @ Bldg 9 2nd |  |  | 10 | 0 | 10 | 21-Feb-25 | 06-Mar-25 | J: -169; N: Install Additional Hangers - HVAC Duct @ Bldg 9 2nd
C-00397br | Install Additional Hangers - Electrical @ Bldg 9 2nd |  |  | 10 | 0 | 10 | 21-Feb-25 | 06-Mar-25 | J: -169; O: Install Additional Hangers - Electrical @ Bldg 9 2nd
C-00397bs |  | Install Additional Hangers - Fire Suppression @ Bldg 9 2nd |  | 10 | 0 | 10 | 21-Feb-25 | 06-Mar-25 | J: -169; N: Install Additional Hangers - Fire Suppression @ Bldg 9 2nd
| CASE 00397 - BUILDING 3 |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: -115
| BUILDING 3 - 2ND FLOOR |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: -115
C-00397ch |  | Install Additional Hangers - Fire Suppression @ Bldg 3 2nd |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: -115; N: Install Additional Hangers - Fire Suppression @ Bldg 3 2nd
| CASE 00350 BUILDING 3 & 9 EXTERIOR LIGHTING |  |  | 8 | 56 | 2 | 12-Nov-24 A | 21-Mar-25 | J: 45
C-00350d | Remove and Replace Exterior Lights @ Bldg 9 |  |  | 4 | 56 | 1 | 12-Nov-24 A | 20-Mar-25 | J: 45; O: Remove and Replace Exterior Lights @ Bldg 9
C-00350e | Remove and Replace Exterior Lights @ Bldg 3 |  |  | 4 | 51 | 1 | 19-Nov-24 A | 21-Mar-25 | J: 45; O: Remove and Replace Exterior Lights @ Bldg 3
| CASE 00367 BLDG 3 TU CHANGES |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 139
C-00367d | Delete or Modify TU's @ Bldg 3 |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 139; J: Delete or Modify TU's @ Bldg 3
| CASE 00380 BLDG 3 EM SUBSTATION CREDIT |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 178
C-00380d |  | Use 500kVA Emergency Substation from Phas e 1 Turnover Material |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 178; D: Use 500kVA Emergency Substation from Phase 1 Turnover Material
| CASE 00381 BLDG 9 ATTIC 2 X 6 COLLAR BEAMS VS DUCT |  |  | 6 | 0 | 6 | 03-Mar-25 | 10-Mar-25 | J: 4
C-00381c |  | Adjust 2x6 Wood Collar Ties in Attic at 3 Locations @ Bldg 9 |  | 6 | 0 | 6 | 03-Mar-25 | 10-Mar-25 | J: 4; D: Adjust 2x6 Wood Collar Ties in Attic at 3 Locat ions @ Bldg 9
| CASE 00387 BLDG K, 3, 9 MISC ARCH CHANGES |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 160
| Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 7 of 46 |  | J: TASK filter: Activity Status.
| Actual Level of Effort | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  | Original | Actual | Remaining | Start | Finish | J: Total Float; M: 2025; J: 2026; M: 2027
|  |  |  | Duration | Duration | Duration | [30 empty] | M
[9 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
C-00387d |  | Misc Arch Changes in Bldg 9 (RFI 1425, 1428, 1430, 1462, 1463) |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 108; D: Misc Arch Changes in Bldg 9 (RFI 1425, 1428, 1430, 1462, 1463)
C-00387e | Misc Arch Changes in Bldg 3 (RFI 1367, 1455, 1510) |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 160; O: Misc Arch Changes in Bldg 3 (RFI 1367, 1455, 1510)
| CASE 00358 BLDG 9 LAUNDRY CHUTE INFILL |  |  | 3 | 0 | 3 | 03-Feb-25 | 05-Feb-25 | J: 77
C-00358g | Repair Slate Roof at Vent Openings @ Bldg 9 |  |  | 3 | 0 | 3 | 03-Feb-25 | 05-Feb-25 | J: 77; S: Repair Slate Roof at Vent Openings @ Bldg 9
| CASE 00379 COTTAGE E SOILED UTILITY ROOM 1E031 |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 138
C-00379d | Install Custom Sink Basin @ 1E031 |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 138; J: Install Custom Sink Basin @ 1E031
| CASE 00384 BLDG 3 DESCOPE WIRELESS DURESS SYSTEM |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 178
C-00384d | Delete Wireless Durress Scope for Bldg 3 |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 178; A: Delete Wireless Durress Scope for Bldg 3
| CASE 00402 BLDG 9 FACILITY STORM DRAINAGE PIPING |  |  | 7 | 0 | 7 | 26-Feb-25 | 06-Mar-25 | bar: J
C-00402f |  | Replace Roof Drains on Flat Roofs and Interior Storm Pipe @ Bldg 9 |  | 7 | 0 | 7 | 26-Feb-25 | 06-Mar-25 | J: -3; J: Replace Roof Drains on Flat Roofs and Interior Storm Pipe @ Bldg 9
| CASE 00416 BLDG K, 9, 3 - ADD FIRE PUMPS |  |  | 457 | 249 | 139 | 12-Feb-24 A | 18-Aug-25 | J: 12
C-00416c | PHB Prepare and Submit Pricing CASE-00416 |  |  | 10 | 249 | 1 | 12-Feb-24 A | 03-Feb-25 | J: 2; S: PHB Prepare and Submit Pricing CASE-00416
C-00416x | USACE R/A Fire Pump Submittal |  |  | 30 | 110 | 12 | 14-Oct-24 A | 14-Feb-25 | J: 2; J: USACE R/A Fire Pump Submittal
C-00416n |  | Install Fire Pumps Bldg 3 (Mod P00047 Removed Scope) |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: 60; N: Install Fire Pumps Bldg 3 (Mod P00047 Removed Scope)
C-00416o |  | Install Fire Pumps Bldg 9 (Mod P00047 Removed Scope) |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: 26; N: Install Fire Pumps Bldg 9 (Mod P00047 Removed Scope)
C-00416y | PHB Prepare/Submit Elec Equipment |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: -10; A: PHB Prepare/Submit Elec Equipment
C-00416ab | PHB Prepare/Submit Cooling Equipment |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: -10; A: PHB Prepare/Submit Cooling Equipment
C-00416ba | PHB Prepare/Submit Doors/Hardware/Frame |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: 45; S: PHB Prepare/Submit Doors/Hardware/Frame
C-00416z | USACE R/A Elec Equipment Submittal |  |  | 30 | 0 | 30 | 15-Feb-25 | 16-Mar-25 | J: -13; S: USACE R/A Elec Equipment Submittal
C-00416ac | USACE R/A Cooling Equipment Submittal |  |  | 30 | 0 | 30 | 15-Feb-25 | 16-Mar-25 | J: -13; O: USACE R/A Cooling Equipment Submittal
C-00416bb | USACE R/A Doors/Hardware/Frame Submittal |  |  | 30 | 0 | 30 | 15-Feb-25 | 16-Mar-25 | J: 63; O: USACE R/A Doors/Hardware/Frame Submittal
C-00416k | Fab/Deliver Fire Pumps Bldg K |  |  | 80 | 0 | 80 | 17-Feb-25 | 09-Jun-25 | J: 0; N: Fab/Deliver Fire Pumps Bldg K
C-00416aa | Fab/Deliver Elec Equipment |  |  | 40 | 0 | 40 | 17-Mar-25 | 09-May-25 | J: 40; O: Fab/Deliver Elec Equipment
C-00416ad | Fab/Deliver Cooling Equipment |  |  | 40 | 0 | 40 | 17-Mar-25 | 09-May-25 | J: 45; O: Fab/Deliver Cooling Equipment
C-00416ae | Recoordinate MEPs for Fire Pump Room @ Bldg K |  |  | 20 | 0 | 20 | 17-Mar-25 | 11-Apr-25 | J: -9; D: Recoordinate MEPs for Fire Pump Room @ Bldg K
C-00416bc | Fab/Deliver Doors/Hardware/Frame Case 00416 |  |  | 40 | 0 | 40 | 17-Mar-25 | 09-May-25 | J: 45; J: Fab/Deliver Doors/Hardware/Frame Case 00416
C-00416af |  | Install New Fire Service from Bldg K to Bldg 9 and Bldg 3 |  | 30 | 0 | 30 | 14-Apr-25 | 23-May-25 | J: 50; F: Install New Fire Service from Bldg K to Bldg 9 and Bldg 3
C-00416ah | Demo Wall @ Mec h 1K016 for Trench |  |  | 2 | 0 | 2 | 14-Apr-25 | 15-Apr-25 | J: 4; O: Demo Wall @ Mec h 1K016 for Trench
C-00416am |  | Relocate and Repipe Steam Condensate Equip to 1K016 |  | 10 | 0 | 10 | 14-Apr-25 | 25-Apr-25 | J: 18; J: Relocate and Repipe Steam Condensate Equip to 1K016
C-00416ap |  | New Elec Service from 9 Transformer to 1K069 (under slab) |  | 25 | 0 | 25 | 14-Apr-25 | 16-May-25 | J: -9; F: New Elec Service from 9 Transformer to 1K069 (under slab)
C-00416al | Install New UG Piping to Water Softner Room |  |  | 10 | 0 | 10 | 16-Apr-25 | 29-Apr-25 | J: 4; D: Install New UG Piping to Water Softner Room
C-00416ag | Pour New Equip Pad and Infill Floor Drains @ 1K069 |  |  | 5 | 0 | 5 | 19-May-25 | 23-May-25 | J: -9; J: Pour New Equip Pad and Infill Floor Drains @ 1K069
C-00416ai |  | Pour New Equip Pad and Infill Drain Trench @ Mech 1K016 |  | 5 | 0 | 5 | 19-May-25 | 23-May-25 | J: -9; F: Pour New Equip Pad and Infill Drain Trench @ Mech 1K016
C-00416at | Run Normal and Emergency Feeders to 1K069 |  |  | 15 | 0 | 15 | 19-May-25 | 09-Jun-25 | J: 5; J: Run Normal and Emergency Feeders to 1K069
C-00416aj | Concrete Cure |  |  | 28 | 0 | 28 | 24-May-25 | 20-Jun-25 | J: -11; S: Concrete Cure
C-00416an | Complete New Fire Rating @ 1K069 |  |  | 10 | 0 | 10 | 27-May-25 | 09-Jun-25 | J: -2; D: Complete New Fire Rating @ 1K069
C-00416ar | Shutdown for MI Cable Install |  |  | 5 | 0 | 5 | 10-Jun-25 | 16-Jun-25 | J: 5; N: Shutdown for MI Cable Install
C-00416ax | Paint @ 1K069 |  |  | 1 | 0 | 1 | 10-Jun-25 | 10-Jun-25 | J: -2; S: Paint @ 1K069
C-00416ay | Firestopping @ 1K069 |  |  | 1 | 0 | 1 | 11-Jun-25 | 11-Jun-25 | J: -2; O: Firestopping @ 1K069
C-00416aq | Install Cooling Equipment @ 1K069 |  |  | 10 | 0 | 10 | 12-Jun-25 | 25-Jun-25 | J: 23; D: Install Cooling Equipment @ 1K069
C-00416aw | Install Elec Equipment |  |  | 5 | 0 | 5 | 12-Jun-25 | 18-Jun-25 | J: 18; O: Install Elec Equipment
C-00416p | Install Fire Pumps Bldg K |  |  | 10 | 0 | 10 | 23-Jun-25 | 07-Jul-25 | J: -9; N: Install Fire Pumps Bldg K
C-00416ak | Relocate Water Softner s t o Mec h 1K016 |  |  | 20 | 0 | 20 | 23-Jun-25 | 21-Jul-25 | J: -4; F: Relocate Water Softner s t o Mec h 1K016
C-00416av | Flooring Mitigation |  |  | 5 | 0 | 5 | 23-Jun-25 | 27-Jun-25 | J: 47; O: Flooring Mitigation
C-00416as | New Fire Alarm Connections for Pump Room |  |  | 15 | 0 | 15 | 08-Jul-25 | 28-Jul-25 | J: -9; F: New Fire Alarm Connections for Pump Room
C-00416ao | Build Back Walls @ 1K016 and Vending |  |  | 10 | 0 | 10 | 22-Jul-25 | 04-Aug-25 | J: -4; F: Build Back Walls @ 1 K016 a nd Vending
C-00416au | Make Final Connections for Fire Pump |  |  | 10 | 0 | 10 | 29-Jul-25 | 11-Aug-25 | J: -9; F: Make Final Connections for Fire Pump
C-00416bd | Fire Pump Test & Commission |  |  | 5 | 0 | 5 | 12-Aug-25 | 18-Aug-25 | J: -9; J: Fire Pump Test & Commission
| Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 8 of 46 |  | J: TASK filter: Activity Status.
| Actual Level of Effort | Remaining Work | Milestone | [5 empty] | D: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  | Original | Actual | Remaining | Start | Finish | J: Total Float; J: 2025; J: 2026; M: 2027
|  |  |  | Duration | Duration | Duration | [30 empty] | M
[9 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
| CASE 00339 BUILDING 9 ASBESTOS DELAY |  |  | 14 | 344 | 7 | 23-Feb-24 A | 07-Feb-25 | J: 279
C-00339e | USACE Issue Mod XXXX |  |  | 14 | 344 | 7 | 23-Feb-24 A | 07-Feb-25 | J: 279; J: USACE Issue Mod XXXX
| CASE 00368 BLDG 9 COLLAPSED ROOF REPAIR |  |  | 16 | 0 | 16 | 03-Feb-25 | 24-Feb-25 | J: 64
C-00368d | Build New Beam Pockets @ Bldg 9 |  |  | 6 | 0 | 6 | 03-Feb-25 | 10-Feb-25 | J: 64; J: Build New Beam Pockets @ Bldg 9
C-00368e | Install New Beam for Roof Repair @ Bldg 9 |  |  | 4 | 0 | 4 | 11-Feb-25 | 14-Feb-25 | J: 64; S: Install New Beam for Roof Repair @ Bldg 9
C-00368f | Replace Collapsed Roof @ Bldg 9 |  |  | 6 | 0 | 6 | 17-Feb-25 | 24-Feb-25 | J: 64; A: Replace Collapsed Roof @ Bldg 9
| CASE 00376 COTTAGE ENTRY SIDEWALK |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: 169
C-00376d | Prep for Additional Sidewalks to Cottage Porches |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 169; S: Prep for Additional Sidewalks to Cottage Porches
C-00376e | Pour Additional Sidewalks to Cottage Porches |  |  | 5 | 0 | 5 | 10-Feb-25 | 14-Feb-25 | J: 169; S: Pour Additional Sidewalks to Cottage Porches
| CASE 00398 COTTAGE P1D PENDANT LIGHT CHANGES |  |  | 10 | 214 | 1 | 01-Apr-24 A | 03-Feb-25 | J: 143
C-00398d |  | Purchase and Install New P1D Light Fixtures @ Cottages HIJ |  | 5 | 214 | 1 | 01-Apr-24 A | 03-Feb-25 | J: 143; N: Purchase and Install New P1D Light Fixtures @ Cottages HIJ
C-00398e |  | Purchase and Install New P1D Light Fixtures @ Cottages EFG |  | 5 | 214 | 1 | 01-Apr-24 A | 03-Feb-25 | J: 143; N: Purchase and Install New P1D Light Fixtures @ Cottages EFG
C-00398f |  | Purchase and Install New P1D Light Fixtures @ Cottages CD |  | 5 | 214 | 1 | 01-Apr-24 A | 03-Feb-25 | J: 143; N: Purchase and Install New P1D Light Fixtures @ Cottages CD
| CASE 00407 SITE - BLDG 3 UNDERGROUND STORM CHANGES |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 117
C-00407c | Install Additional Storm Lateral @ Bldg 3 |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 117; A: Install Additional Storm Lateral @ Bldg 3
| CASE 00365 CTG - RESIDENT ROOM CARPET TO LVT URC-19 |  |  | 70 | 116 | 34 | 19-Aug-24 A | 26-Mar-25 | J: 101
C-00365f | Install LVT in Bedrooms @ HIJ |  |  | 15 | 116 | 5 | 19-Aug-24 A | 13-Feb-25 | J: 130; J: Install LVT in Bedrooms @ HIJ
C-00365d | Install LVT in Bedrooms @ CD |  |  | 15 | 0 | 15 | 06-Mar-25 | 26-Mar-25 | J: 101; A: Install LVT in Bedrooms @ CD
C-00365e | Install LVT in Bedrooms @ EFG |  |  | 15 | 0 | 15 | 06-Mar-25 | 26-Mar-25 | J: 101; A: Install LVT in Bedrooms @ EFG
| CASE 00369 BLDG 3 PT CEILING CHANGES |  |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | bar: J
C-00369f | Install ACT Ceiling Step Above Treadmill @ 03008 |  |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: -5; S: Install ACT Ceiling Step Above Treadmill @ 03008
| CASE 00357 BUILDING NUMBER EQUIPMENT CHANGES |  |  | 96 | 106 | 10 | 03-Sep-24 A | 14-Feb-25 | J: 169
C-00357f | Modify Shop Drawings for Number Changes @ HIJ |  |  | 10 | 106 | 3 | 03-Sep-24 A | 05-Feb-25 | J: 176; O: Modify Shop Drawings for Number Changes @ HIJ
C-00357i |  | Modify Shop Drawings for Number Changes @ Loading Dock |  | 10 | 106 | 1 | 03-Sep-24 A | 03-Feb-25 | J: 178; N: Modify Shop Drawings for Number Changes @ Loading Dock
C-00357d | Modify Shop Drawings for Number Changes @ CD |  |  | 10 | 56 | 3 | 12-Nov-24 A | 05-Feb-25 | J: 176; O: Modify Shop Drawings for Number Changes @ CD
C-00357e | Modify Shop Drawings for Number Changes @ EFG |  |  | 10 | 56 | 3 | 12-Nov-24 A | 05-Feb-25 | J: 176; O: Modify Shop Drawings for Number Changes @ EFG
C-00357h | Modify Shop Drawings for Number Changes @ K |  |  | 10 | 43 | 3 | 02-Dec-24 A | 05-Feb-25 | J: 176; S: Modify Shop Drawings for Number Changes @ K
C-00357g | Modify Shop Drawings for Number Changes @ L |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: 169; O: Modify Shop Drawings for Number Changes @ L
| CASE 00419 BLDG 9 EXIT SIGN DISCREPANCIES |  |  | 10 | 0 | 10 | 13-Oct-25 | 24-Oct-25 | J: -74
C-00419c | Install 5 Additional Exit Signs @ Bldg 9 |  |  | 10 | 0 | 10 | 13-Oct-25 | 24-Oct-25 | J: -74; A: Install 5 Additional Exit Signs @ Bldg 9
| CASE 00372 FRAMING AT BLDG 3 EM |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 127
C-00372d |  | Fabricate and Install Supplemental Steel under Elec RM 23064 |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 127; N: Fabricate and Install Supplemental Steel under Elec RM 23064
| CASE 00444 BLDG 9 TRAINING KITCHEN ISLAND |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 27
C-00444c | Fabricate New Custom Island for 19054A |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 27; A: Fabricate New Custom Island for 19054A
| CASE 00405 BLDG K AND BLDG 3 FDC LOCATIONS |  |  | 3 | 0 | 3 | 03-Feb-25 | 05-Feb-25 | J: 162
C-00405d |  | Install 2 Permanent Bollards on the Emergency Access Drive |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 155; N: Install 2 Permanent Bollards on the Emergency Access Drive
C-00405e | Relocate FDC to West Side of Building @ Bldg 3 |  |  | 3 | 0 | 3 | 03-Feb-25 | 05-Feb-25 | J: 162; S: Relocate FDC to West Side of Building @ Bldg 3
| CASE 00418 GRADING AT BLDG L & EXISTING WALKWAYS |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 111
C-00418e | Add Drain Inlet D3-17.1 East of WW1 and Adjust Grade |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 111; O: Add Drain Inlet D3-17.1 East of WW1 and Adjust Grade
| CASE 00434 BLDG 3 CHW FLOWMETERS |  |  | 2 | 0 | 2 | 10-Mar-25 | 11-Mar-25 | J: 35
C-00434d | Provide Electromagnetic CHW Flowmeters for Bldg 3 |  |  | 2 | 0 | 2 | 10-Mar-25 | 11-Mar-25 | J: 35; N: Provide Electromagnetic CHW Flowmeters for Bldg 3
| CASE 00438 BLDG 3 STEAM CHANGES |  |  | 7 | 0 | 7 | 03-Mar-25 | 11-Mar-25 | J: 0
C-00438d | Add Condensate Pump Trap @ Bldg 3 |  |  | 7 | 0 | 7 | 03-Mar-25 | 11-Mar-25 | J: 0; S: Add Condensate Pump Trap @ Bldg 3
| CASE 00440 COTTAGE MEDICINE CABINET TRIM CHANGE |  |  | 175 | 173 | 5 | 29-May-24 A | 07-Feb-25 | J: 108
C-00440d |  | Install Chair Rail Trim Around Nurse Servery @ Cottage EFG |  | 5 | 173 | 2 | 29-May-24 A | 04-Feb-25 | J: 92; N: Install Chair Rail Trim Around Nurse Servery @ Cottage EFG
C-00440e |  | Install Chair Rail Trim Around Nurse Servery @ Cottage CD |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 108; N: Install Chair Rail Trim Around Nurse Servery @ Cottage CD
| CASE 00455 COTTAGE H ROOF TANSITION TO WALKWAY 14 |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 149
C-00455c | Overframe Roof at Cottage H/WW14 |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 149; A: Overframe Roof at Cottage H/WW14
| Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 9 of 46 |  | J: TASK filter: Activity Status.
| Actual Level of Effort | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  | Original | Actual | Remaining | Start | Finish | J: Total Float; J: 2025; J: 2026; M: 2027
|  |  |  | Duration | Duration | Duration | [30 empty] | M
[9 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
| CASE 00411 EXISTING WALKWAY LIGHTING AND FINISHES |  |  | 130 | 150 | 101 | 29-Jun-24 A | 24-Jun-25 | J: 78
C-00411h | USACE Issue Mod XXXX |  |  | 14 | 217 | 12 | 29-Jun-24 A | 12-Feb-25 | J: 244; J: USACE Issue Mod XXXX
C-00411d | Install Finishes from L to 3 |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: 91; J: Install Finishes from L to 3
C-00411e | Install Finishes from L to 9 |  |  | 10 | 0 | 10 | 17-Feb-25 | 28-Feb-25 | J: 91; J: Install Finishes from L to 9
C-00411f | Change Floor Finishes in L |  |  | 5 | 0 | 5 | 18-Jun-25 | 24-Jun-25 | J: 6; N: Change Floor Finishes in L
| CASE 00382 BLDGS 3 & 9 STEAM FLOWMETERS |  |  | 35 | 0 | 35 | 04-Feb-25 | 24-Mar-25 | J: 82
C-00382f | Provide differential 6" Pressure Flow Meter in B3 |  |  | 1 | 0 | 1 | 04-Feb-25 | 04-Feb-25 | J: 116; S: Provide differential 6" Pressure Flow Meter in B3
C-00382d | Provide differential 6" Pressure Flow Meter in B9 |  |  | 1 | 0 | 1 | 26-Feb-25 | 26-Feb-25 | J: 41; O: Provide differential 6" Pressure Flow Meter in B9
C-00382e | Provide differential 8" Pressure Flow Meter in B9 |  |  | 1 | 0 | 1 | 24-Mar-25 | 24-Mar-25 | J: 23; N: Provide differential 8" Pressure Flow Meter in B9
| CASE 00390 PHASE 2 SIGNAGE - MATCH PHASE 1 |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 178
C-00390d | Cottage C/D Utilize Signage Systems |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 178; J: Cottage C/D Utilize Signage Systems
C-00390e | Cottage E/F/G Utilize Signage Systems |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 178; A: Cottage E/F/G Utilize Signage Systems
C-00390f | Cottage H/I/J Utilize Signage Systems |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 178; J: Cottage H/I/J Utilize Signage Systems
C-00390g | Bldg L & Walkways Utilize Signage Systems |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 178; A: Bldg L & Walkways Utilize Signage Systems
C-00390h | Bldg K Utilize Signage Systems |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 178; J: Bldg K Utilize Signage Systems
C-00390i | Bldg 9 Utilize Signage Systems |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 178; J: Bldg 9 Utilize Signage Systems
C-00390j | Bldg 3 Utilize Signage Systems |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 178; J: Bldg 3 Utilize Signage Systems
C-00390k | Loading Dock Utilize Signage Systems |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 178; J: Loading Dock Utilize Signage Systems
C-00390l | Site Restoration |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 178; A: Site Restoration
| CASE 00391 BLDG 3 & K PLUMBING CHANGES |  |  | 46 | 48 | 3 | 22-Nov-24 A | 05-Feb-25 | J: 134
C-00391d | Reroute Domestic Cold Water (RFI- 1502) @ Bldg 3 |  |  | 1 | 48 | 1 | 22-Nov-24 A | 03-Feb-25 | J: -97; S: Reroute Domestic Cold Water (RFI- 15 02) @ Bldg 3
C-00391e | Update Roof Drains (RFI-1554) (RFI-1696) @ Bldg K |  |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: 81; O: Update Roof Drains (RFI-1554) (RFI-1696) @ Bldg K
C-00391f | Extend Storm Drain (RFI-1688) @ Bldg 3 |  |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: 81; A: Extend Storm Drain (RFI-1688) @ Bldg 3
C-00391g | Provide Thermostatic Mixing Valves @ Bldg 3 |  |  | 3 | 0 | 3 | 03-Feb-25 | 05-Feb-25 | J: 115; S: Provide Thermostatic Mixing Valves @ Bldg 3
C-00391h |  | Excavate for the Extension of Storm Drain (RFI-1688) @ Bldg 3 |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 136; N: Excavate for the Extension of Storm Drain (RFI-1688) @ Bldg 3
| CASE 00412 BLDG 3 ACCESS HATCH |  |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: 135
C-00412d | Increase Size of the Fire Fighter Access @ Bldg 3 |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 135; S: Increase Size of the Fire Fighter Access @ Bldg 3
C-00412e | Furnish and Install a Larger Hatch @ Bldg 3 |  |  | 1 | 0 | 1 | 04-Feb-25 | 04-Feb-25 | J: 135; A: Furnish and Install a Larger Hatch @ Bldg 3
| CASE 00420 BLDG 3 ADDED STEEL |  |  | 6 | 0 | 6 | 03-Feb-25 | 10-Feb-25 | J: -102
C-00420d | Add Steel from RFI's 1429 and 1608 @ Bldg 3 |  |  | 6 | 0 | 6 | 03-Feb-25 | 10-Feb-25 | J: -102; S: Add Steel from RFI's 1429 and 1608 @ Bldg 3
| CASE 00426 BLDG 3 USE CPT-1 CARPET FROM COTTAGES |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 96
C-00426d |  | Use CPT-1 from Cottages in Lieu of CPT-2,3 & 4 @ Bldg 3 |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 96; N: Use CPT-1 from Cottages in Lieu of CPT-2,3 & 4 @ Bldg 3
| CASE 00458 COTTAGE BATHROOM WALL TILE CHANGES |  |  | 48 | 61 | 5 | 05-Nov-24 A | 07-Feb-25 | J: 76
C-00458e |  | Provide PT-2 Cove Base and Full Size Wall Tile Less than 42" AFF @ EFG |  | 5 | 61 | 4 | 05-Nov-24 A | 06-Feb-25 | J: 77; J: Provide PT-2 Cove Base and Full Size Wall Tile Less than 42" AFF @ EFG
C-00458d |  | Provide PT-2 Cove Base and Full Size Wall Tile Less than 42" AFF @ CD |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 76; J: Provide PT-2 Cove Base and Full Size Wall Tile Less than 42" AFF @ CD
| CASE 00474 WALKWAYS PHENOLIC PANEL AT BRICK |  |  | 5 | 91 | 1 | 24-Sep-24 A | 03-Feb-25 | J: 122
C-00474d |  | Provide and Caulk in Place 2x2 Alum Sheet Metal Angle @ Walkways |  | 5 | 91 | 1 | 24-Sep-24 A | 03-Feb-25 | J: 122; D: Provide and Caulk in Place 2x2 Alum Sheet Metal Angle @ Walkways
| CASE 00363 BLDG 3 HPS MAIN & TRAP RELOCATION |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 117
C-00363e | Create Mechanical Closet in Locker Room @ Bldg 3 |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 28; O: Create Mechanical Closet in Locker Room @ Bldg 3
C-00363f |  | Add Isolation Valve to Pumped Condensate Line @ Bldg 3 |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 117; O: Add Isolation Valve to Pumped Condensate Line @ Bldg 3
| CASE 00396 TABLETS & CONTRACTOR SOFTWARE FOR GOVERNMENT USE |  |  | 1 | 150 | 1 | 01-Jul-24 A | 03-Feb-25 | J: 178
C-00396d |  | Provide and Maintain Seven Table ts for CFM & USACE use |  | 1 | 150 | 1 | 01-Jul-24 A | 03-Feb-25 | J: 178; N: Provide and Maintain Seven Tablets for CFM & USACE use
| CASE 00431 BLDG 3 ADD ELECTRICAL OUTLETS TO 03043 |  |  | 4 | 0 | 4 | 03-Feb-25 | 06-Feb-25 | J: 25
C-00431d | Install Four GFI's in Mechanical Room @ Bldg 3 |  |  | 4 | 0 | 4 | 03-Feb-25 | 06-Feb-25 | J: 25; S: Install Four GFI's in Mechanical Room @ Bldg 3
| CASE 00452 COTT OUTDOOR STORAGE DOOR JAMB |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 77
C-00452e |  | Furnish and Install Base Plate for Bistro Wall @ Bldg K per R FI-1617 |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 77; D: Furnish and Install Base Plate for Bistro Wall @ Bldg K per R FI-1617
| CASE 00456 BLDG 3 DRYER EXHAUST FAN |  |  | 15 | 88 | 8 | 27-Sep-24 A | 12-Feb-25 | J: 89
C-00456e |  | Furnish and Install a Booster Fan for Bldg 3 Dryer Vent @ Bldg 3 |  | 1 | 88 | 1 | 27-Sep-24 A | 03-Feb-25 | J: 26; D: Furnish and Install a Booster Fan for Bldg 3 Dryer Vent @ Bldg 3
| Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 10 of 46 |  | J: TASK filter: Activity Status.
| Actual Level of Effort | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  | Original | Actual | Remaining | Start | Finish | Total Float | M: 2025; J: 2026; F: 2027
|  |  | Duration | Duration | Duration | bar: A
[8 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
C-00456d | Provide a Duplex Outlet for New Fan @ Bldg 3 |  | 2 | 0 | 2 | 11-Feb-25 | 12-Feb-25 | J: 89; S: Provide a Duplex Outlet for New Fan @ Bldg 3
| CASE 00468 BLDG 9 LEVEL 3 SLAB INFILL FRAMING |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 58
C-00468d | Provide and Install New C8x11.5 Channel @ Bldg 9 |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 58; O: Provide and Install New C8x11.5 Channel @ Bldg 9
| CASE 00477 COTTAGE CORNER GUARDS |  | 46 | 56 | 3 | 12-Nov-24 A | 05-Feb-25 | J: 151
C-00477f | Cottages H/I/J Add Corner Guards |  | 3 | 56 | 1 | 12-Nov-24 A | 03-Feb-25 | J: 107; J: Cottages H/I/J Add Corner Guards
C-00477d | Cottages C/D Add Corner Guards |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: 152; J: Cottages C/D Add Corner Guards
C-00477e | Cottages E/F/G Add Corner Guards |  | 3 | 0 | 3 | 03-Feb-25 | 05-Feb-25 | J: 136; J: Cottages E/F/G Add Corner Guards
| CASE 00484-1 BLDG 118 ROOF DRAIN CONNECTION |  | 14 | 0 | 14 | 03-Feb-25 | 20-Feb-25 | J: 165
C-00484d | Scopre and Trace Roof Leader @ Bldg 118 |  | 14 | 0 | 14 | 03-Feb-25 | 20-Feb-25 | J: 165; S: Scopre and Trace Roof Leader @ Bldg 118
| CASE 00415 BLDG 3 VESTIBULE 03054 CHANGES |  | 48 | 48 | 5 | 22-Nov-24 A | 07-Feb-25 | J: 110
C-00415e | Construct New Partition Walls @ Bldg 3 |  | 6 | 48 | 4 | 22-Nov-24 A | 06-Feb-25 | J: 110; A: Construct New Partition Walls @ Bldg 3
C-00415f | Reinstall Storefront and New Door Operators @ Bldg 3 |  | 1 | 0 | 1 | 07-Feb-25 | 07-Feb-25 | J: 110; O: Reinstall Storefront and New Door Operators @ Bldg 3
| CASE 00421 SITE 118 AVB CARD READER RELOCATION |  | 69 | 67 | 6 | 28-Oct-24 A | 10-Feb-25 | J: 173
C-00421d | Relocate AVB Card Reader |  | 1 | 67 | 1 | 28-Oct-24 A | 03-Feb-25 | J: 173; J: Relocate AVB Card Reader
C-00421e | Retest and Certify AVB Connec tions and Functio nality |  | 5 | 0 | 5 | 04-Feb-25 | 10-Feb-25 | J: 173; O: Retest and Certify AVB Connec tions and Functionalit y
| CASE 00422 SITE INFILTRATION BASINS |  | 4 | 0 | 4 | 03-Feb-25 | 06-Feb-25 | J: 175
C-00422d | Make Adjustments to Basins 1, 2, 3 & 4 |  | 3 | 0 | 3 | 03-Feb-25 | 05-Feb-25 | J: 175; A: Make Adjustments to Basins 1, 2, 3 & 4
C-00422e | Restoration of Areas Around Basins |  | 1 | 0 | 1 | 06-Feb-25 | 06-Feb-25 | J: 175; J: Restoration of Areas Around Basins
| CASE 00475 BLDG 3 REMOVAL OF STEEL CASINGS AT RADIATOR INFILLS |  | 6 | 0 | 6 | 03-Feb-25 | 10-Feb-25 | J: 159
C-00475d | Removal of Metal Sills at Radiator Infills @ Bldg 3 |  | 6 | 0 | 6 | 03-Feb-25 | 10-Feb-25 | J: 159; O: Removal of Metal Sills at Radiator Infills @ Bldg 3
| CASE 00499 COTTAGES CLOSET DOOR FRAMES |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 153
C-00499d | Change the Door Frame Material for Cottages E, F, G |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 153; O: Change the Door Frame Material for Cottages E, F, G
| CASE 00469 WALKWAY EXPANSION JOINT CHANGES |  | 103 | 74 | 40 | 17-Oct-24 A | 28-Mar-25 | J: 19
C-00469d | Modify Roof and Phenolic Panels @ Walk ways |  | 20 | 74 | 15 | 17-Oct-24 A | 21-Feb-25 | J: 19; O: Modify Roof and Phenolic Panels @ Walk ways
C-00469e | Install Expansion Joints in Lid and ACT @ Walkways |  | 5 | 0 | 5 | 24-Feb-25 | 28-Feb-25 | J: 19; N: Install Expansion Joints in Lid and ACT @ Walkways
C-00469f | Modify Steel Support Rail for Handrails @ Walkways |  | 20 | 0 | 20 | 03-Mar-25 | 28-Mar-25 | J: 19; N: Modify Steel Support Rail for Handrails @ Walkways
| CASE 00483 BLDG 9 DEMO BRICK CHASE WALLS |  | 5 | 70 | 2 | 23-Oct-24 A | 04-Feb-25 | J: 111
C-00483d | Remove Chase Walls @ C ols A/2, A/5, A/20 & A/23 @ Bldg 9 |  | 5 | 70 | 2 | 23-Oct-24 A | 04-Feb-25 | J: 111; N: Remove Chase Walls @ C ols A/2, A/5, A/20 & A/23 @ Bldg 9
| CASE 00496 BLDG 9 FLAT ROOF DECK REPLACEMENT |  | 9 | 0 | 9 | 03-Feb-25 | 13-Feb-25 | J: 16
C-00496d | Remove Loose Brick and Infill Beam Pockets @ Bldg 9 |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 16; O: Remove Loose Brick and Infill Beam Pockets @ Bldg 9
C-00496e | Install Angle, Beam and Replace Decking @ Bldg 9 |  | 4 | 0 | 4 | 10-Feb-25 | 13-Feb-25 | J: 16; O: Install Angle, Beam and Replace Decking @ Bldg 9
| CASE 00410 BLDG 9 ADDITIONAL DOOR HARDWARE CHANGES |  | 96 | 114 | 10 | 21-Aug-24 A | 14-Feb-25 | J: 169
C-00410b | PHB Prepare and Submit Pricing CASE-00410 |  | 10 | 114 | 0 | 21-Aug-24 A | 03-Feb-25 | J: 49; S: PHB Prepare and Submit Pricing CASE-00410
C-00410d | Change Doors, Glazing, Hardware, Fire Alarm & Security @ Bldg 9 |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: 49; D: Change Doors, Glazing, Hardware, Fire Alarm & Security @ Bldg 9
C-00410e | Add Auto Operators @ Bldg 9 |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 54; J: Add Auto Operators @ Bldg 9
C-00410f | Delete Pressure Sensors and Anti-Ligature System @ Bldg 9 |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 178; N: Delete Pressure Sensors and Anti-Ligature System @ Bldg 9
C-00410g | Infill Door Opening B9050A @ Bldg 9 |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: 78; J: Infill Door Opening B9050A @ Bldg 9
| CASE 00501 BLDG 3 FDC LOCATIONS (501) |  | 89 | 92 | 3 | 23-Sep-24 A | 05-Feb-25 | J: 162
C-00501b | PHB Prepare and Submit Pricing CASE-00501 |  | 10 | 92 | 0 | 23-Sep-24 A | 03-Feb-25 | J: 162; S: PHB Prepare and Submit Pricing CASE-00501
C-00501d | Relocate FDC from 03008A to 03042 in Bldg. 3 |  | 3 | 0 | 3 | 03-Feb-25 | 05-Feb-25 | J: 162; S: Relocate FDC from 03008A to 03042 in Bldg. 3
| CASE 00436-1 BLDG 3 RAMP AND SITE WORK |  | 10 | 72 | 1 | 21-Oct-24 A | 03-Feb-25 | J: 136
C-00436d | Remove Ramp, Stairs, Planter, Sidewalk & Railing @ Bldg 3 |  | 10 | 72 | 1 | 21-Oct-24 A | 03-Feb-25 | J: 136; N: Remove Ramp, Stairs, Planter, Sidewalk & Railing @ Bldg 3
| CASE 00493-1 BLDG 9 VESTIBULE FLOORING CHANGE |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: 70
C-00493d | Change Flooring Finishes in B9100A, B9100AA, B900AA, B9075A @ Bldg 9 |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: 70; J: Change Flooring Finishes in B9100A, B9100AA, B900AA, B9075A @ Bldg 9
| CASE 00521-1 EXISTING WALKWAY FOUNDATION WALL REPAIRS |  | 10 | 83 | 0 | 04-Oct-24 A | 03-Feb-25 | J: 179
C-00521b | PHB Prepare and Submit Pricing CASE-00521 |  | 10 | 83 | 0 | 04-Oct-24 A | 03-Feb-25 | J: 179; S: PHB Prepare and Submit Pricing CASE-00521
| CASE 00409 SMALL CHANGES FROM RFI CLARIFICATIONS |  | 48 | 52 | 5 | 18-Nov-24 A | 07-Feb-25 | J: 151
C-00409g | Adjust Framing per FRI 1556, 1567 & 1661 @ Bldg 3 |  | 5 | 52 | 2 | 18-Nov-24 A | 04-Feb-25 | J: -27; O: Adjust Framing per FRI 1556, 1567 & 1661 @ Bldg 3
Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 11 of 46 |  | J: TASK filter: Activity Status.
Actual Level of Effort | Remaining Work | Milestone | [5 empty] | D: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  | Original | Actual | Remaining | Start | J: Finish; F: Total Float; J: 2025; A: 2026; A: 2027
|  |  |  | Duration | Duration | Duration
[9 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | AM
C-00409d | Install Threshold at 1W053 per RFI 1701 @ Walkway 7 |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 155; O: Install Threshold at 1W053 per RFI 1701 @ Walkway 7
C-00409f | Adjust Framing per RFI 1550, 1565 & 1657 @ Bldg 9 |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: -105; O: Adjust Framing per RFI 1550, 1565 & 1657 @ Bldg 9
| CASE 00478 COTTAGE SHOWER CURTAIN TRACK |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 134
C-00478d | Suspend Shower Curtain Track @ CD |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 134; A: Suspend Shower Curtain Track @ CD
C-00478e | Suspend Shower Curtain Track @ EFG |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 114; A: Suspend Shower Curtain Track @ EFG
C-00478f | Suspend Shower Curtain Track @ HIJ |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 131; A: Suspend Shower Curtain Track @ HIJ
| CASE 00479 WALKWAY DOOR 1W010 CHANGES |  |  | 4 | 0 | 4 | 03-Feb-25 | 06-Feb-25 | J: 162
C-00479d |  | Remove Card Reader and Closer, Add Operator @ Walkway |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: 162; N: Remove Card Reader and Closer, Add Operator @ Walkway
C-00479e |  | Increase Door Size to 42" and Adjust Storefront @ Walkway |  | 2 | 0 | 2 | 05-Feb-25 | 06-Feb-25 | J: 162; N: Increase Door Size to 42" and Adjust Storefront @ Walkway
| CASE 00507 BLDG K DELETE 1K001 & 1K020 CARD READERS |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 178
C-00507d | Delete Card Readers at Doors 1K001 & 1K020 @ Bldg K |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 178; O: Delete Card Readers at Doors 1K001 & 1K020 @ Bldg K
| CASE 00512 BLDG 50 (N) DOOR B9110A CHANGE |  |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: 147
C-00512d | Change Door From HM to Solid Wood @ Bldg 50 |  |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: 147; S: Change Door From HM to Solid Wood @ Bldg 50
| CASE 00513 BLDG 50 (N) DEHYDRATOR/CAN WASH ELECTRICAL CHANGE |  |  | 3 | 47 | 2 | 25-Nov-24 A | 04-Feb-25 | J: 147
C-00513d |  | Provide Disconnects, Twist Lock Receptacles and Plug Ends @ Bldg 50 |  | 3 | 47 | 2 | 25-Nov-24 A | 04-Feb-25 | J: 147; D: Provide Disconnects, Twist Lock Receptacles and Plug Ends @ Bldg 50
| CASE 00533 BLDG 9 B9100A, B9075A - EXISTING ROOF DRAINS |  |  | 3 | 0 | 3 | 03-Feb-25 | 05-Feb-25 | J: 14
C-00533d | Add Roof Drain Extensions @ Bldg 9 |  |  | 3 | 0 | 3 | 03-Feb-25 | 05-Feb-25 | J: 14; J: Add Roof Drain Extensions @ Bldg 9
| CASE 00377-1 BLDG 3 & 9 MASONRY ENVELOPE |  |  | 239 | 120 | 176 | 13-Aug-24 A | 09-Oct-25 | J: -39
C-00377b | PHB Prepare and Submit Pricing CASE-00377 |  |  | 10 | 120 | 0 | 13-Aug-24 A | 03-Feb-25 | J: -96; S: PHB Prepare and Submit Pricing CASE-00377
C-00377d |  | Exterior Masonry Repair, Replacement & Raise Scuppers @ Bldg 3 |  | 176 | 0 | 176 | 03-Feb-25 | 09-Oct-25 | J: -39; J: Exterior Masonry Repair, Replacement & Raise Scuppers @ Bldg
C-00377e |  | Exterior Masonry Repair, Replacement & Raise Scuppers @ Bldg 9 |  | 176 | 0 | 176 | 03-Feb-25 | 09-Oct-25 | J: -96; J: Exterior Masonry Repair, Replacement & Raise Scuppers @ Bldg
| CASE 00459 BLDG 9 EXHAUST FAN 9-EF-3 RELOCATION |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 31
C-00459d |  | Replace Roof EF w/ Wall Mount EF, Install in Existing Window @ Bldg 9 |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 31; D: Replace Roof EF w/ Wall Moun t EF, Install in Existing Window @ Bldg 9
| CASE 00515 BLDG 3 PWC WALL COVERING CHANGE |  |  | 3 | 0 | 3 | 03-Feb-25 | 05-Feb-25 | J: 162
C-00515d | Add PWC to Walls in Rm 030 35 @ Bldg 3 |  |  | 3 | 0 | 3 | 03-Feb-25 | 05-Feb-25 | J: 162; A: Add PWC to Walls in Rm 03035 @ Bld g 3
| CASE 00519 BLDG 3 ATTIC FLOOR REPAIRS |  |  | 5 | 56 | 3 | 12-Nov-24 A | 05-Feb-25 | J: 49
C-00519d |  | Remove Concrete at 5 Locations, Provide Structural Infill @ Bldg 3 |  | 5 | 56 | 3 | 12-Nov-24 A | 05-Feb-25 | J: 49; D: Remove Concrete at 5 Locations, Provide Structural Infill @ Bldg 3
| CASE 00529 PARTNERING FACILITATOR |  |  | 3 | 66 | 0 | 29-Oct-24 A | 03-Feb-25 | J: 179
C-00529d |  | Provide Qualified Facilitator & Execute Partnering Workshops |  | 3 | 66 | 0 | 29-Oct-24 A | 03-Feb-25 | J: 179; N: Provide Qualified Facilitator & Execute Partnering Workshops
| CASE 00494 BLDG 3 & 9 FIREPROOFING BEAMS |  |  | 35 | 0 | 35 | 03-Feb-25 | 21-Mar-25 | J: -143
C-00494f | Apply Spray Fireproofing @ Bldg 3-2 |  |  | 7 | 0 | 7 | 03-Feb-25 | 11-Feb-25 | J: -115; J: Apply Spray Fireproofing @ Bldg 3-2
C-00494g | Apply Spray Fireproofing @ Bldg 9G |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: -164; J: Apply Spray Fireproofing @ Bldg 9G
C-00494h | Apply Spray Fireproofing @ Bldg 9-1 |  |  | 7 | 0 | 7 | 21-Feb-25 | 03-Mar-25 | J: -168; A: Apply Spray Fireproofing @ Bldg 9-1
C-00494i | Apply Spray Fireproofing @ Bldg 9-2 |  |  | 7 | 0 | 7 | 13-Mar-25 | 21-Mar-25 | J: -170; S: Apply Spray Fireproofing @ Bldg 9-2
| CASE 00520 BLDG 9 TEMPORARY COVERING OF FLAT ROOFS |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 20
C-00520d | Provide Temporary Covering Over Flat Roofs @ Bldg 9 |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 20; O: Provide Temporary Covering Over Flat Roofs @ Bldg 9
| CASE 00524 BLDG 50 EMERGENCY POWER |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 139
C-00524d |  | Provide EM Power Circuits for IT Rack and Split AC @ Bldg 50 |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 139; N: Provide EM Power Circuits for IT Rack and Split AC @ Bldg 50
| CASE 00389 BLDG 9 & 3 AV CHANGERS (URC-18) |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: 155
C-00389d | Additional Blocking @ Bldg 9 |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 108; J: Additional Blocking @ Bldg 9
C-00389e | Additional Blocking @ Bldg 3 |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: 155; J: Additional Blocking @ Bldg 3
C-00389f | Add Electrical, Data, and TV Outlets @ Bldg 9 |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 108; S: Add Electrical, Data, and TV Outlets @ Bldg 9
C-00389g | Add Electrical, Data, and TV Outlets @ Bldg 3 |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: 155; S: Add Electrical, Data, and TV Outlets @ Bldg 3
| CASE 00400 COTTAGE PATIENT LIFTS |  |  | 8 | 0 | 8 | 03-Feb-25 | 12-Feb-25 | J: 188
C-00400d | Layout Patient Lifts @ Cottages CD |  |  | 4 | 0 | 4 | 03-Feb-25 | 06-Feb-25 | J: 188; J: Layout Patient Lifts @ Cottages CD
C-00400e | Layout Patient Lifts @ Cottages EFG |  |  | 4 | 0 | 4 | 03-Feb-25 | 06-Feb-25 | J: 141; J: Layout Patient Lifts @ Cottages EFG
C-00400f | Layout Patient Lifts @ Cottages HIJ |  |  | 4 | 0 | 4 | 03-Feb-25 | 06-Feb-25 | J: 141; J: Layout Patient Lifts @ Cottages HIJ
C-00400g | Adjust Tile Around Support Posts @ Cottages CD |  |  | 4 | 0 | 4 | 07-Feb-25 | 12-Feb-25 | J: 188; O: Adjust Tile Around Support Posts @ Cottages CD
| Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 12 of 46 |  | J: TASK filter: Activity Status.
| Actual Level of Effort | Remaining Work | Milestone | [5 empty] | D: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  | Original | Actual | Remaining | Start | Finish | J: Total Float; J: 2025; J: 2026; M: 2027
|  |  |  | Duration | Duration | Duration | bar: AM
[9 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
C-00400h |  | Adjust Tile Around Support Posts @ Cottages EFG |  | 4 | 0 | 4 | 07-Feb-25 | 12-Feb-25 | J: 141; S: Adjust Tile Around Support Posts @ Cottages EFG
C-00400i |  | Adjust Tile Around Support Posts @ Cottages HIJ |  | 4 | 0 | 4 | 07-Feb-25 | 12-Feb-25 | J: 141; S: Adjust Tile Around Support Posts @ Cottages HIJ
| CASE 00430 BLDG 3 & K PATIENT LIFTS |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 32
C-00430d |  | Add Power for Patient LIfts @ Bldg 3 |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 32; A: Add Power for Patient LIfts @ Bldg 3
| CASE 00437 BLDG 9 CABINET UNIT HEATERS |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 41
C-00437d |  | Replace Cabinet Unit Heater 9-CUH-2 @ Bldg 9 |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 41; S: Replace Cabinet Unit Heater 9-CUH-2 @ Bldg 9
| CASE 00470 BLDG 9 WALL PARTITION CHANGES |  |  | 12 | 0 | 12 | 03-Feb-25 | 18-Feb-25 | J: 101
C-00470d |  | Remove Plaster on Exterior Columns for New Wall Types @ Bldg 9 |  | 12 | 0 | 12 | 03-Feb-25 | 18-Feb-25 | J: 101; D: Remove Plaster on Exterior Columns for New Wall Types @ Bldg 9
|  | CASE 00482 COTTAGE PERIMETER WALL GAP CORRECTION |  | 7 | 0 | 7 | 03-Feb-25 | 11-Feb-25 | J: 127
C-00482d |  | Additional Floor Prep to Cover the Exposed Slab Edge @ Cotts CD |  | 7 | 0 | 7 | 03-Feb-25 | 11-Feb-25 | J: 81; D: Additional Floor Prep to Cover the Exposed Slab Edge @ Cotts CD
C-00482e |  | Additional Floor Prep to Cover the Exposed Slab Edge @ Cotts EFG |  | 4 | 0 | 4 | 03-Feb-25 | 06-Feb-25 | J: 82; D: Additional Floor Prep to Cover the Exposed Slab Edge @ Cotts EFG
C-00482f |  | Additional Floor Prep to Cover the Exposed Slab Edge @ Cotts HIJ |  | 7 | 0 | 7 | 03-Feb-25 | 11-Feb-25 | J: 127; D: Additional Floor Prep to Cover the Exposed Slab Edge @ Cotts HIJ
| CASE 00495 COTTAGES UNDERCABINET F1F LIGHTS |  |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: 163
C-00495d |  | Replace Undercabinet Lights @ Cottages CD |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: 137; A: Replace Undercabinet Lights @ Cottages CD
C-00495e |  | Replace Undercabinet Lights @ Cottages EFG |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: 137; A: Replace Undercabinet Lights @ Cottages EFG
C-00495f |  | Replace Undercabinet Lights @ Cottages HIJ |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: 137; A: Replace Undercabinet Lights @ Cottages HIJ
C-00495g |  | Add Undercabinet Light @ Bldg 3 |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: 163; J: Add Undercabinet Light @ Bldg 3
| CASE 00514 COTTAGE DEN RETURN DIFFUSER |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 134
C-00514d |  | Change Return Diffusers in Den @ Cottages CD |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 134; S: Change Return Diffusers in Den @ Cottages CD
| CASE 00518-1 BLDG 1 EXTERIOR AND MISC CHANGES |  |  | 22 | 35 | 0 | 12-Dec-24 A | 03-Feb-25 | J: 179
C-00518b |  | PHB Prepare and Submit Pricing CASE-00518 |  | 0 | 35 | 0 | 12-Dec-24 A | 03-Feb-25 | J: 179; A: PHB Prepare and Submit Pricing CASE-00518
C-00518c | USACE Issue MOD XXXX |  |  | 0 | 0 | 0 | 03-Feb-25 | 03-Feb-25 | J: 254; J: USACE Issue MOD XXXX
C-00518d |  | Window Infills and Expansion Joints @ Bldg 1 |  | 0 | 0 | 0 | 03-Feb-25 | 03-Feb-25 | J: 179; A: Window Infills and Expansion Joints @ Bldg 1
C-00518e |  | Interior Courtyard Expansion Joints @ Bldg 2 |  | 0 | 0 | 0 | 03-Feb-25 | 03-Feb-25 | J: 179; A: Interior Courtyard Expansion Joints @ Bldg 2
C-00518f | Temp Tunnel Demo @ Bldg 1 |  |  | 0 | 0 | 0 | 03-Feb-25 | 03-Feb-25 | J: 179; J: Temp Tunnel Demo @ Bldg 1
C-00518g |  | Level 5 Skybridge Infill @ Bldg 2 |  | 0 | 0 | 0 | 03-Feb-25 | 03-Feb-25 | J: 179; J: Level 5 Skybridge Infill @ Bldg 2
C-00518h | Lower D7-14 @ Site |  |  | 0 | 0 | 0 | 03-Feb-25 | 03-Feb-25 | J: 179; M: Lower D7-14 @ Site
C-00518i |  | Add Automatic Valves @ Chiller Plant |  | 0 | 0 | 0 | 03-Feb-25 | 03-Feb-25 | J: 179; A: Add Automatic Valves @ Chiller Plant
| SUSPENSIONS OF WORK |  |  | 760 | 696 | 21 | 08-Mar-23 A | 21-Feb-25 | J: 265
SW0266 |  | Suspension of Work C-0266 - Installation of Network Cable (Case 319) |  | 30 | 696 | 1 | 08-Mar-23 A | 01-Feb-25 | J: 285; D: Suspension of Work C-0266 - Installation of Network Cable (Case 319)
SW0296 |  | Suspension of Work C-0296 - Nurse Call Spectralink Phones |  | 30 | 283 | 1 | 24-Apr-24 A | 01-Feb-25 | J: 205; N: Suspension of Work C-0296 - Nurse Call Spectralink Phones
SW0307 |  | Suspension of Work C-0307 - Bldg 3 & 9 Lightning Protection |  | 30 | 208 | 1 | 08-Jul-24 A | 01-Feb-25 | J: 114; N: Suspension of Work C-0307 - Bldg 3 & 9 Lightning Protection
SW0308 |  | Suspension of Work C-0308 - Bldg K Rooms Changing to Add Fire Pump (Case 428/416) |  | 30 | 196 | 1 | 20-Jul-24 A | 01-Feb-25 | J: 58; M: Suspension of Work C-0308 - Bldg K Rooms Changing to Add Fire Pump (Case 428/416)
SW0314 |  | Suspension of Work C-0314 - Bldg 3 & 9 Flat Roofs (Case 377) |  | 30 | 144 | 1 | 10-Sep-24 A | 01-Feb-25 | J: 36; N: Suspension of Work C-0314 - Bldg 3 & 9 Flat Roofs (Case 377)
SW0317 |  | Suspension of Work C-0317 - Bldg 3 Ground Floor Interior Framing |  | 30 | 103 | 1 | 21-Oct-24 A | 01-Feb-25 | J: 285; D: Suspension of Work C-0317 - Bldg 3 Ground Floor Interior Framing
SW0318 |  | Suspension of Work C-0318 - Bldg K Fire Pump Design |  | 30 | 101 | 1 | 23-Oct-24 A | 01-Feb-25 | J: 285; O: Suspension of Work C-0318 - Bldg K Fire Pump Design
SW0323 |  | Suspension of Work C-0323 - Resume Work for C-0319 and Revised Suspension for Case 00540 |  | 30 | 78 | 14 | 15-Nov-24 A | 14-Feb-25 | J: 272; A: Suspension of Work C-0323 - Resume Work for C-0319 and Revised Suspension for Case 0
SW0324 |  | Suspension of Work C-0324 - Bldg 3 Prosthetics Lab Case 532 |  | 30 | 71 | 21 | 22-Nov-24 A | 21-Feb-25 | J: 265; D: Suspension of Work C-0324 - Bldg 3 Prosthetics Lab Case 532
SW0325 |  | Suspension of Work C-0325 - Bolts in Steam and Hot Water Lines Case 534 |  | 30 | 71 | 21 | 22-Nov-24 A | 21-Feb-25 | J: 265; F: Suspension of Work C-0325 - Bolts in Steam and Hot Water Lines Case 534
| STORED MATERIALS |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 30
SM-1460 |  | Visual Display Units and Lockers - B9 - Stored Materials |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 30; O: Visual Display Units and Lockers - B9 - Stored Materials
| BIM COORDINATIONS |  |  | 478 | 488 | 31 | 06-Mar-23 A | 17-Mar-25 | J: 4
BIM BLDG 9 |  |  |  | 478 | 488 | 31 | 06-Mar-23 A | 17-Mar-25 | J: -31
| 1ST FL MEP COORDINATION |  |  | 170 | 229 | 26 | 11-Mar-24 A | 10-Mar-25 | J: -156
BM-B9-240 | A/E Approval | -1st Fl |  | 5 | 229 | 1 | 11-Mar-24 A | 03-Feb-25 | J: -156; A: A/E Approval; J: -1st Fl
BM-B9-250 |  | MEP shop drawings + R/A -1st Fl |  | 25 | 229 | 1 | 11-Mar-24 A | 03-Feb-25 | J: -156; J: MEP shop drawings + R/A -1st Fl
BM-B9-260 | MEP Fabrication | -1st Fl |  | 25 | 0 | 25 | 04-Feb-25 | 10-Mar-25 | J: -156; J: MEP Fabrication; S: -1st Fl
| 2ND FL MEP COORDINATION |  |  | 478 | 488 | 31 | 06-Mar-23 A | 17-Mar-25 | J: -154
| Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 13 of 46 |  | J: TASK filter: Activity Status.
| Actual Level of Effort | Remaining Work | Milestone | [5 empty] | D: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  | Original | Actual | Remaining | Start | Finish | J: Total Float; J: 2025; J: 2026; M: 2027
|  |  |  | Duration | Duration | Duration | [30 empty] | M
[9 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
BM-B9-310 | Conflict Resolution and Sign off | -2nd Fl |  | 5 | 488 | 1 | 06-Mar-23 A | 03-Feb-25 | J: -154; J: Conflict Resolution and Sign off; D: -2nd Fl
BM-B9-330 |  | MEP shop drawings + R/A -2nd Fl |  | 25 | 229 | 1 | 11-Mar-24 A | 10-Feb-25 | J: -154; A: MEP shop drawings + R/A -2nd Fl
BM-B9-320 | A/E Approval | -2nd Fl |  | 5 | 0 | 5 | 04-Feb-25 | 10-Feb-25 | J: -154; A: A/E Approval; A: -2nd Fl
BM-B9-340 | MEP Fabrication | -2nd Fl |  | 25 | 0 | 25 | 11-Feb-25 | 17-Mar-25 | J: -154; J: MEP Fabrication; O: -2nd Fl
| 3RD FL MEP COORDINATION |  |  | 175 | 214 | 26 | 01-Apr-24 A | 10-Mar-25 | J: -26
BM-B9-400 | A/E Approval | -3rd Fl |  | 5 | 214 | 1 | 01-Apr-24 A | 03-Feb-25 | J: -26; A: A/E Approval; J: -3rd Fl
BM-B9-410 |  | MEP shop drawings + R/A -3rd Fl |  | 25 | 214 | 1 | 01-Apr-24 A | 03-Feb-25 | J: -26; J: MEP shop drawings + R/A -3rd Fl
BM-B9-420 | MEP Fabrication | -3rd Fl |  | 25 | 0 | 25 | 04-Feb-25 | 10-Mar-25 | J: -26; J: MEP Fabrication; O: -3rd Fl
BIM BLDG 3 |  |  |  | 125 | 192 | 5 | 01-May-24 A | 07-Feb-25 | J: 30
BIM BLDG 3 |  |  |  | 125 | 192 | 5 | 01-May-24 A | 07-Feb-25 | J: 30
| 3RD FL MEP COORDINATION |  |  | 125 | 192 | 5 | 01-May-24 A | 07-Feb-25 | J: 30
BM-BL3-280 | MEP shop drawings -3rd Fl |  |  | 25 | 192 | 2 | 01-May-24 A | 04-Feb-25 | J: 30; J: MEP shop drawings -3rd Fl
BM-BL3-860 |  | MEP shop drawings - Review and Approve -3rd Fl |  | 29 | 156 | 1 | 29-Aug-24 A | 03-Feb-25 | J: 42; S: MEP shop drawings - Review and Approve -3rd Fl
BM-BL3-290 | A/E Approval | -3rd Fl |  | 7 | 156 | 1 | 29-Aug-24 A | 01-Feb-25 | J: 44; A: A/E Approval; J: -3rd Fl
BM-BL3-270 | MEP Fabrication | -3rd Fl |  | 25 | 105 | 5 | 04-Sep-24 A | 07-Feb-25 | J: 30; M: MEP Fabrication; S: -3rd Fl
PHASE-1 |  |  |  | 1103 | 922 | 210 | 21-Jun-21 A | 26-Nov-25 | bar: J
| PHASE-1: SVC LOADING DOCK |  |  | 609 | 576 | 54 | 28-Oct-22 A | 17-Apr-25 | J: 125
| PHASE-1: SVC LOADING DOCK: EXTERIOR BUILDING FINISHES |  |  | 5 | 419 | 1 | 28-Oct-22 A | 03-Feb-25 | J: 137
LOAD-1870 |  | Landscaping/Seed/ Sod @ Loading Dock |  | 5 | 419 | 1 | 28-Oct-22 A | 03-Feb-25 | J: 137; A: Landscaping/Seed/ Sod @ Loading Dock
| PHASE-1: SVC LOADING DOCK: FINAL FINISHES |  |  | 124 | 121 | 19 | 12-Aug-24 A | 27-Feb-25 | J: 130
LOAD-1570 | Install VCT & Base |  |  | 5 | 121 | 1 | 12-Aug-24 A | 03-Feb-25 | J: 148; M: Install VCT & Base
LOAD-2053 | Signage @ LOAD |  |  | 5 | 0 | 5 | 21-Feb-25 | 27-Feb-25 | J: 125; J: Signage @ LOAD
|  | PHASE-1: SVC LOADING DOCK: FINAL CLEAN / PUNCH / TURNOVER |  | 180 | 144 | 54 | 10-Jul-24 A | 17-Apr-25 | J: 125
LOAD-1710 |  | Test and Commission Loading Dock |  | 30 | 144 | 17 | 10-Jul-24 A | 25-Feb-25 | J: 139; A: Test and Commission Loading Dock
LOAD-1380 | Exterior Punchlist |  |  | 5 | 106 | 1 | 02-Sep-24 A | 03-Feb-25 | J: 178; M: Exterior Punchlist
LOAD-2160 | Rough Clean |  |  | 5 | 0 | 5 | 28-Feb-25 | 06-Mar-25 | J: 125; M: Rough Clean
LOAD-1720 | PHB Punchlist |  |  | 5 | 0 | 5 | 07-Mar-25 | 13-Mar-25 | J: 125; J: PHB Punchlist
LOAD-2170 | Subcontract Punch Work |  |  | 10 | 0 | 10 | 14-Mar-25 | 27-Mar-25 | J: 125; A: Subcontract Punch Work
LOAD-2190 | Owner / Architect Punch |  |  | 5 | 0 | 5 | 28-Mar-25 | 03-Apr-25 | J: 125; A: Owner / Architect Punch
LOAD-2200 |  | Subs Complete Owner / AE Punch |  | 5 | 0 | 5 | 04-Apr-25 | 10-Apr-25 | J: 125; S: Subs Complete Owner / AE Punch
LOAD-2180 | Final Clean |  |  | 5 | 0 | 5 | 11-Apr-25 | 17-Apr-25 | J: 125; J: Final Clean
LOAD-1820 |  | COMPLETE: SVC LOADING DOCK |  | 0 | 0 | 0 |  | 17-Apr-25 | J: 125; O: COMPLETE: SVC LOADING DOCK
| NEW UTILITY SERVICE FROM BLDG N TO L & BLDG 2 |  |  | 500 | 632 | 103 | 10-Aug-22 A | 26-Jun-25 | J: 98
|  | RUN NEW UTILITY SERVICES FROM BUILDING N to L (THROUGH BLDG 9) |  | 343 | 632 | 68 | 10-Aug-22 A | 07-May-25 | J: 108
UTIL-1010 | Distrib CHW Piping From N-L |  |  | 25 | 632 | 11 | 10-Aug-22 A | 26-Mar-25 | J: -109; A: Distrib CHW Piping From N-L
UTIL-1020 | Distr Stm & Conden Pipe N-L |  |  | 25 | 179 | 11 | 20-May-24 A | 26-Mar-25 | J: 98; A: Distr Stm & Conden Pipe N-L
UTIL-1030 | CHW Insulation From N-L |  |  | 20 | 179 | 13 | 20-May-24 A | 07-May-25 | J: 108; S: CHW Insulation From N-L
UTIL-1040 |  | Steam & Condensate Insulation From N-L |  | 20 | 179 | 13 | 20-May-24 A | 07-May-25 | J: 108; N: Steam & Condensate Insulation From N-L
UTIL-1035 | FMS Conduit |  |  | 10 | 176 | 8 | 23-May-24 A | 12-Feb-25 | J: 12; A: FMS Conduit
UTIL-1045 | OIT Conduit |  |  | 10 | 176 | 8 | 23-May-24 A | 12-Feb-25 | J: 12; A: OIT Conduit
|  | RUN NEW UTILITY SERVICES FROM BUILDING L to 2 (THROUGH BLDG 3) |  | 475 | 632 | 103 | 10-Aug-22 A | 26-Jun-25 | J: 98
UTIL-2010 | Distribute CHW Piping L-2 |  |  | 40 | 632 | 36 | 10-Aug-22 A | 15-May-25 | J: 98; S: Distribute CHW Piping L-2
UTIL-2035 | FMS Conduit |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: 186; M: FMS Conduit
UTIL-2045 | OIT Conduit |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: 186; A: OIT Conduit
UTIL-2020 | Distr Steam & Cond Pipe L-2 |  |  | 40 | 0 | 40 | 27-Mar-25 | 21-May-25 | J: 98; O: Distr Steam & Cond Pipe L-2
UTIL-2030 | CHW Insulation From L-2 |  |  | 20 | 0 | 20 | 16-May-25 | 13-Jun-25 | J: 102; O: CHW Insulation From L-2
UTIL-2040 |  | Steam & Condensate Insulation From L-2 |  | 20 | 0 | 20 | 22-May-25 | 19-Jun-25 | J: 98; J: Steam & Condensate Insulation From L-2
UTIL-2050 | Reinstall Ceil and Walls L-2 |  |  | 5 | 0 | 5 | 20-Jun-25 | 26-Jun-25 | J: 98; N: Reinstall Ceil and Walls L-2
|  | PHASE-1: SITEWORK & CRITICAL/TEMP UTILITIES AT (NEW BUILDS) |  | 895 | 922 | 2 | 21-Jun-21 A | 04-Feb-25 | J: 199
| Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 14 of 46 |  | J: TASK filter: Activity Status.
| Actual Level of Effort | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  | Original | Actual | Remaining | Start | Finish | J: Total Float; J: 2025; J: 2026; M: 2027
|  |  |  | Duration | Duration | Duration | [30 empty] | M
[9 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
| NORTH / EAST ROADWAY |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 137
SU-1120 | TOP COAT PAVEMENT- N/E ROAD |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 137; J: TOP COAT PAVEMENT- N/E ROAD
| SITEWORK & UTILITIES SOUTHWEST- TO BLDG PAD H/I/J |  |  | 8 | 682 | 1 | 21-Jun-21 A | 03-Feb-25 | J: 96
SU-1280 | SITE LIGHTING- S/W |  |  | 8 | 682 | 1 | 21-Jun-21 A | 03-Feb-25 | J: 96; M: SITE LIGHTING- S/W
| SITEWORK & UTILITIES NORTHWEST- TO BLDG PAD E/F/G |  |  | 8 | 682 | 1 | 21-Jun-21 A | 03-Feb-25 | J: 93
SU-1380 | SITE LIGHTING- N/W |  |  | 8 | 682 | 1 | 21-Jun-21 A | 03-Feb-25 | J: 93; M: SITE LIGHTING- N/W
| SITEWORK & UTILITIES SOUTHEAST- TO BLDG PAD COMMUNITY BLDG |  |  | 8 | 570 | 1 | 20-Jan-22 A | 03-Feb-25 | J: 41
SU-1580 | SITE LIGHTING- S/E |  |  | 8 | 570 | 1 | 20-Jan-22 A | 03-Feb-25 | J: 41; M: SITE LIGHTING- S/E
| SITEWORK & UTILITIES NORTHEAST- TO BLDG PAD C/D |  |  | 8 | 571 | 1 | 17-Jan-22 A | 03-Feb-25 | J: 96
SU-1480 | SITE LIGHTING- N/E |  |  | 8 | 571 | 1 | 17-Jan-22 A | 03-Feb-25 | J: 96; M: SITE LIGHTING- N/E
| PARKING LOT- SOUTH |  |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: 199
PL-1070 | SIDEWALK- PARKING LOT SOUTH |  |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: 136; J: SIDEWALK- PARKING LOT SOUTH
PL-1130 | PARKING LOT SOUTH COMPLETE |  |  | 0 | 0 | 0 |  | 03-Feb-25 | J: 201; J: PARKING LOT SOUTH COMPLETE
| PHASE-1: COTTAGE-H/I/J |  |  | 787 | 692 | 178 | 16-May-22 A | 13-Oct-25 | J: 23
| PHASE-1: COTTAGE-H/I/J_BUILDING ENCLOSURE / WATER TIGHT |  |  | 20 | 434 | 1 | 19-May-23 A | 03-Feb-25 | J: 134
HIJ-262 | Install Accordian Doors |  |  | 20 | 434 | 1 | 19-May-23 A | 03-Feb-25 | J: 134; M: Install Accordian Doors
| PHASE-1: COTTAGE-H/I/J_EXTERIOR BUILDING FINISHES |  |  | 8 | 0 | 8 | 05-Feb-25 | 14-Feb-25 | J: 122
HIJ-430 | Expansion Joint Installation |  |  | 8 | 0 | 8 | 05-Feb-25 | 14-Feb-25 | J: 122; J: Expansion Joint Installation
| PHASE-1: COTTAGE-H/I/J_HOUSEHOLD E: MEP/FP ROUGH-IN |  |  | 609 | 692 | 2 | 16-May-22 A | 04-Feb-25 | J: 142
HIJ-270 | Spray Foam/ Batt Insulation in Attic & Baffles |  |  | 10 | 692 | 1 | 16-May-22 A | 03-Feb-25 | J: 142; A: Spray Foam/ Batt Insulation in Attic & Baffles
HIJ-325 | Inspect Attic Insulation |  |  | 5 | 28 | 1 | 23-Dec-24 A | 04-Feb-25 | J: 142; M: Inspect Attic Insulation
HIJ-370 | INSPECTION - MEPs |  |  | 0 | 0 | 0 |  | 03-Feb-25 | J: 97; M: INSPECTION - MEPs
| PHASE-1: COTTAGE-H/I/J_DRYWALL / PRIME-PAINT / OVERHEAD FINISHES |  |  | 150 | 224 | 41 | 18-Mar-24 A | 31-Mar-25 | J: 72
HIJ-510 | Ceramic Tile @ (CORR/COM) |  |  | 20 | 224 | 6 | 18-Mar-24 A | 31-Mar-25 | J: 72; A: Ceramic Tile @ (CORR/COM)
HIJ-490 | Doors & Hardware @ (CORR/COM) |  |  | 12 | 61 | 8 | 05-Nov-24 A | 24-Mar-25 | J: 72; S: Doors & Hardware @ (CORR/COM)
HIJ-4444 | Seal Concrete Floor @ HIJ |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: 101; J: Seal Concrete Floor @ HIJ
| PHASE-1: COTTAGE-H/I/J_MILLWORK |  |  | 65 | 227 | 41 | 13-Mar-24 A | 31-Mar-25 | J: 72
HIJ-550 | Millwork / Vanities / Cabinets @ (UNITS) |  |  | 20 | 227 | 5 | 13-Mar-24 A | 07-Feb-25 | J: 100; A: Millwork / Vanities / Cabinets @ (UNITS)
HIJ-590 | Millwork / Casework @ (CORR/COM) |  |  | 25 | 213 | 6 | 02-Apr-24 A | 31-Mar-25 | J: 72; O: Millwork / Casework @ (CORR/COM)
| PHASE-1: COTTAGE-H/I/J_FINAL FINISHES |  |  | 415 | 607 | 59 | 15-Sep-22 A | 24-Apr-25 | J: 95
| PHASE-1: COTTAGE-H/I/J_HOUSEHOLD E: FINISHES - UNITS |  |  | 382 | 607 | 56 | 15-Sep-22 A | 21-Apr-25 | J: 98
HIJ-642 | HVAC Diffusers/ Devices @ (UNITS) |  |  | 20 | 607 | 1 | 15-Sep-22 A | 03-Feb-25 | J: 106; J: HVAC Diffusers/ Devices @ (UNITS)
HIJ-640 | Plumbing Fixtures @ (UNITS) |  |  | 20 | 220 | 6 | 22-Mar-24 A | 17-Feb-25 | J: 100; J: Plumbing Fixtures @ (UNITS)
HIJ-600 | Set Countertops @ (UNITS) |  |  | 10 | 208 | 6 | 09-Apr-24 A | 10-Feb-25 | J: 100; J: Set Countertops @ (UNITS)
HIJ-2123 | Window Shades |  |  | 5 | 199 | 2 | 22-Apr-24 A | 12-Feb-25 | J: 131; M: Window Shades
HIJ-610 | Bathroom - Accessories @ (UNITS) |  |  | 15 | 197 | 10 | 24-Apr-24 A | 21-Apr-25 | J: 80; O: Bathroom - Accessories @ (UNITS)
HIJ-580 | Final Paint @ (UNITS) |  |  | 15 | 133 | 1 | 25-Jul-24 A | 07-Feb-25 | J: 103; M: Final Paint @ (UNITS)
HIJ-650 | Carpet @ (UNITS) |  |  | 15 | 116 | 1 | 19-Aug-24 A | 11-Feb-25 | J: 127; M: Carpet @ (UNITS)
HIJ-2113 | Set Kitchen Equipment |  |  | 8 | 88 | 5 | 27-Sep-24 A | 14-Feb-25 | J: 101; J: Set Kitchen Equipment
HIJ-3113 | Install Owner provided lifts |  |  | 5 | 0 | 5 | 13-Feb-25 | 19-Feb-25 | J: 141; J: Install Owner provided lifts
|  | PHASE-1: COTTAGE-H/I/J_HOUSEHOLD E: FINISHES - CORRIDORS / COMMONS (CORR/COM) |  | 400 | 592 | 59 | 06-Oct-22 A | 24-Apr-25 | J: 81
HIJ-660 | Plumbing Fixtures @ (CORR/COM) |  |  | 20 | 592 | 1 | 06-Oct-22 A | 14-Feb-25 | J: 101; A: Plumbing Fixtures @ (CORR/COM)
HIJ-662 | HVAC Diffusers/ Devices @ (CORR/COM) |  |  | 20 | 447 | 1 | 01-May-23 A | 03-Feb-25 | J: 106; A: HVAC Diffusers/ Devices @ (CORR/COM)
HIJ-670 | Drop ACT Ceiling Tile @ (CO RR/COM) |  |  | 10 | 344 | 1 | 27-Sep-23 A | 24-Mar-25 | J: 72; S: Drop ACT Ceiling Tile @ (CORR/COM)
HIJ-630 | Wall Covering s @ (CORR/COM) |  |  | 20 | 150 | 1 | 01-Jul-24 A | 31-Mar-25 | J: 99; S: Wall Co verings @ (CORR/COM)
HIJ-620 | Final Paint @ (CORR/COM) |  |  | 15 | 108 | 1 | 29-Aug-24 A | 24-Mar-25 | J: 72; A: Final Paint @ (CORR/COM)
HIJ-676 | Install Specialty Doors |  |  | 2 | 106 | 1 | 02-Sep-24 A | 24-Mar-25 | J: 99; J: Install Specialty Doors
HIJ-680 | Bathroom - Accessories @ (CORR/COM) |  |  | 20 | 97 | 13 | 16-Sep-24 A | 24-Apr-25 | J: 80; N: Bathroom - Accessories @ (CORR/COM)
HIJ-792 | Inst Signage |  |  | 5 | 0 | 5 | 01-Apr-25 | 07-Apr-25 | J: 93; J: Inst Signage
| PHASE-1: SOUTHWEST_COURTYARD /LANDSCP/ HARDSCP |  |  | 270 | 370 | 32 | 21-Aug-23 A | 18-Mar-25 | J: 122
| Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 15 of 46 |  | J: TASK filter: Activity Status.
| Actual Level of Effort | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  | Original | Actual | Remaining | Start | Finish | J: Total Float; J: 2025; J: 2026; M: 2027
|  |  |  | Duration | Duration | Duration | [30 empty] | M
[9 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
HIJ-822 | Prep Concrete for Seat Walls |  |  | 10 | 271 | 1 | 21-Aug-23 A | 03-Feb-25 | J: 97; J: Prep Concrete for Seat Walls
HIJ-795 | Install Block/Brick/Framing for Interior HIJ Walk ways |  |  | 22 | 358 | 2 | 07-Sep-23 A | 04-Feb-25 | J: 129; O: Install Block/Brick/Framing for Interior HIJ Walk ways
HIJ-4484 | Rough Grade - Tou ch Up |  |  | 2 | 182 | 1 | 21-Feb-24 A | 03-Feb-25 | J: 96; J: Rough Grade - Touch Up
HIJ2-485 | Phenolic Panels |  |  | 3 | 101 | 1 | 10-Sep-24 A | 10-Feb-25 | J: 126; A: Phenolic Panels
HIJ-805 | Install HIJ Walkway W indows |  |  | 10 | 62 | 1 | 04-Nov-24 A | 10-Feb-25 | J: 126; J: Install HIJ Walkway W indows
HIJ2-495 | Expansion Joints |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: 126; M: Expansion Joints
HIJ-520 | Final Grade |  |  | 5 | 0 | 5 | 17-Feb-25 | 21-Feb-25 | J: 122; A: Final Grade
HIJ2-475 | Seeding |  |  | 1 | 0 | 1 | 24-Feb-25 | 24-Feb-25 | J: 138; A: Seeding
HIJ-540 | Plantings |  |  | 10 | 0 | 10 | 24-Feb-25 | 07-Mar-25 | J: 122; A: Plantings
HIJ2-455 | Weed Barrier |  |  | 3 | 0 | 3 | 10-Mar-25 | 12-Mar-25 | J: 122; M: Weed Barrier
HIJ2-435 | Mulch |  |  | 3 | 0 | 3 | 13-Mar-25 | 17-Mar-25 | J: 122; A: Mulch
HIJ2-825 | Grills |  |  | 1 | 0 | 1 | 18-Mar-25 | 18-Mar-25 | J: 122; A: Grills
HIJ-560 | COURTYARD-B COMPLETE |  |  | 0 | 0 | 0 |  | 18-Mar-25 | J: 122; A: COURTYARD-B COMPLETE
| PHASE-1: COTTAGE-H/I/J_FINAL CLEAN / PUNCH / TURNOVER |  |  | 144 | 75 | 144 | 16-Oct-24 A | 13-Oct-25 | J: 23
HIJ-735 | Sprinkler Systems Test |  |  | 5 | 75 | 2 | 16-Oct-24 A | 27-May-25 | J: 73; S: Sprinkler Systems Test
HIJ-715 | Submit Controls Testing Plan |  |  | 5 | 0 | 5 | 21-Mar-25 | 27-Mar-25 | J: 72; A: Submit Controls Testing Plan
HIJ-745 | Fire AlarmTest |  |  | 5 | 0 | 5 | 13-Jun-25 | 19-Jun-25 | J: 56; S: Fire AlarmTest
HIJ-4454 | Main Feeders Ready to Test - HIJ |  |  | 0 | 0 | 0 |  | 07-Jul-25 | J: 2; D: Main Feeders Ready to Test - HIJ
HIJ-695 | Air & Water Balancing |  |  | 10 | 0 | 10 | 08-Jul-25 | 21-Jul-25 | J: 28; N: Air & Water Balancing
HIJ-725 | Controls Test ing |  |  | 10 | 0 | 10 | 08-Jul-25 | 21-Jul-25 | J: 2; O: Controls Test ing
HIJ-705 | HVAC Commissioning |  |  | 15 | 0 | 15 | 22-Jul-25 | 11-Aug-25 | J: 2; D: HVAC Commissioning
HIJ-4534 | Rough Clean @ HIJ |  |  | 5 | 0 | 5 | 22-Jul-25 | 26-Jul-25 | J: 18; N: Rough Clean @ HIJ
HIJ-772 | Red Zone Meeting |  |  | 60 | 0 | 60 | 08-Aug-25 | 07-Oct-25 | J: 38; J: Red Zone Meeting
HIJ-775 | Performance Verification Testing |  |  | 10 | 0 | 10 | 12-Aug-25 | 25-Aug-25 | J: 20; J: Performance Verification Testing
HIJ-4494 | Government Furniture Installation @ HIJ |  |  | 5 | 0 | 5 | 12-Aug-25 | 16-Aug-25 | J: 2; F: Government Furniture Installation @ HIJ
HIJ-4504 |  | Pre-Final Data Room Inspection & Punchlist Generation |  | 2 | 0 | 2 | 12-Aug-25 | 13-Aug-25 | J: 13; A: Pre-Final Data Room Inspection & Punchlist Generation
HIJ-4514 | Data Room Punchlist Corrections |  |  | 5 | 0 | 5 | 14-Aug-25 | 20-Aug-25 | J: 13; J: Data Room Punchlist Corrections
HIJ-710 | Final Clean |  |  | 5 | 0 | 5 | 18-Aug-25 | 22-Aug-25 | J: 1; N: Final Clean
HIJ-4524 | IT Room(s) Ready for VA Move In |  |  | 0 | 0 | 0 |  | 20-Aug-25 | J: 20; J: IT Room(s) Ready for VA Move In
HIJ-720 | Contractor Pre-Final Inspections |  |  | 10 | 0 | 10 | 25-Aug-25 | 08-Sep-25 | J: 1; F: Contractor Pre-Final Inspections
HIJ-730 | SUBSTANTIAL COMPLETION |  |  | 0 | 0 | 0 |  | 08-Sep-25 | J: 1; J: SUBSTANTIAL COMPLETION
HIJ-755 | Contractor Pre-Final Punchlist Corrections |  |  | 10 | 0 | 10 | 09-Sep-25 | 22-Sep-25 | J: 1; A: Contractor Pre-Final Punchlist Corrections
HIJ-760 | Government Pre-Final Inspections |  |  | 5 | 0 | 5 | 23-Sep-25 | 29-Sep-25 | J: 1; M: Government Pre-Final Inspections
HIJ-765 |  | Corrections of Punchlist from Government Pre-Final Inspection |  | 5 | 0 | 5 | 30-Sep-25 | 06-Oct-25 | J: 1; J: Corrections of Punchlist from Government Pre-Final Inspection
HIJ-770 | Final Inspections |  |  | 5 | 0 | 5 | 07-Oct-25 | 13-Oct-25 | J: 1; J: Final Inspections
HIJ-750 | READY FOR OCCUPANCY |  |  | 0 | 0 | 0 |  | 13-Oct-25 | J: 1; F: READY FOR OCCUPANCY
| PHASE-1: COTTAGE-E/F/G |  |  | 789 | 638 | 178 | 02-Aug-22 A | 13-Oct-25 | J: 23
| PHASE-1: COTTAGE-E/F/G_STRUCTURAL & WOOD FRAMING |  |  | 5 | 326 | 1 | 12-May-23 A | 03-Feb-25 | J: 46
EFG-162 | Set Door Welded Frames |  |  | 5 | 326 | 1 | 12-May-23 A | 03-Feb-25 | J: 46; J: Set Door Welded Frames
| PHASE-1: COTTAGE-E/F/G_BUILDING ENCLOSURE / WATER TIGHT |  |  | 411 | 559 | 7 | 22-Nov-22 A | 11-Feb-25 | J: 147
EFG-262 | Install Accordian Doors |  |  | 20 | 559 | 7 | 22-Nov-22 A | 11-Feb-25 | J: 66; J: Install Accordian Doors
EFG-315 | Expansion Joint Installation |  |  | 5 | 0 | 5 | 05-Feb-25 | 11-Feb-25 | J: 147; J: Expansion Joint Installation
| PHASE-1: COTTAGE-E/F/G_HOUSEHOLD E: MEP/FP ROUGH-IN |  |  | 620 | 638 | 9 | 02-Aug-22 A | 13-Feb-25 | J: 135
EFG-245 | Attic MEP Inspection |  |  | 5 | 638 | 2 | 02-Aug-22 A | 06-Feb-25 | J: 64; M: Attic MEP Inspection
EFG-270 | Spray Foam/ Batt Insulation in Attic & Baffles |  |  | 10 | 610 | 4 | 12-Sep-22 A | 06-Feb-25 | J: 135; S: Spray Foam/ Batt Insulation in Attic & Baffles
EFG-255 | Install Hangers on Steel @ Walkway |  |  | 5 | 255 | 1 | 02-Feb-24 A | 03-Feb-25 | J: 66; J: Install Hangers on Steel @ Walkway
EFG-244 | Fire Suppression Attic Rough |  |  | 20 | 128 | 4 | 01-Aug-24 A | 06-Feb-25 | J: 64; J: Fire Suppression Attic Rough
EFG-370 | INSPECTION - MEPs |  |  | 0 | 0 | 0 |  | 05-Feb-25 | J: 64; M: INSPECTION - MEPs
EFG-325 | Inspect Attic Insulation |  |  | 5 | 0 | 5 | 07-Feb-25 | 13-Feb-25 | J: 135; J: Inspect Attic Insulation
| Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 16 of 46 |  | J: TASK filter: Activity Status.
| Actual Level of Effort | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  | Original | Actual | Remaining | Start | Finish | J: Total Float; J: 2025; J: 2026; M: 2027
|  |  |  | Duration | Duration | Duration | [30 empty] | M
[9 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
| PHASE-1: COTTAGE-E/F/G_DRYWALL / PRIME-PAINT / OVERHEAD FINISHES |  |  | 167 | 229 | 20 | 11-Mar-24 A | 04-Mar-25 | J: 78
EFG-490 | Doors / Running Trim @ (CORR/COM) |  |  | 12 | 229 | 2 | 11-Mar-24 A | 06-Feb-25 | J: 72; A: Doors / Running Trim @ (CORR/COM)
EFG-452 | Bathroom - Tile @ (UNITS) |  |  | 20 | 104 | 9 | 05-Sep-24 A | 17-Feb-25 | J: 70; J: Bathroom - Tile @ (UNITS)
EFG-510 | Ceramic Tile @ (CORR/COM) |  |  | 20 | 74 | 15 | 17-Oct-24 A | 25-Feb-25 | J: 72; J: Ceramic Tile @ (CORR/COM)
EFG-418 | Shower Wall Panels |  |  | 10 | 68 | 3 | 25-Oct-24 A | 07-Feb-25 | J: 70; M: Shower Wall Panels
EFG-480 | Kitchenette - Vinyl Sheeting @ (UNITS) |  |  | 20 | 0 | 20 | 05-Feb-25 | 04-Mar-25 | J: 64; A: Kitchenette - Vinyl Sheeting @ (UNITS)
EFG-4444 | Seal Concrete Floor @ EFG |  |  | 10 | 0 | 10 | 05-Feb-25 | 18-Feb-25 | J: 88; J: Seal Concrete Floor @ EFG
| PHASE-1: COTTAGE-E/F/G_MILLWORK |  |  | 45 | 154 | 17 | 25-Jun-24 A | 07-Mar-25 | J: 64
EFG-550 | Millwork / Vanities / Cabinets @ (UNITS) |  |  | 20 | 154 | 14 | 25-Jun-24 A | 04-Mar-25 | J: 64; A: Millwork / Vanities / Cabinets @ (UNITS)
EFG-590 | Millwork / Casework @ (CORR/COM) |  |  | 25 | 154 | 17 | 25-Jun-24 A | 07-Mar-25 | J: 64; A: Millwork / Casework @ (CORR/COM)
| PHASE-1: COTTAGE-E/F/G_FINAL FINISHES |  |  | 469 | 625 | 91 | 19-Aug-22 A | 10-Jun-25 | J: 63
| PHASE-1: COTTAGE-E/F/G_HOUSEHOLD E: FINISHES - UNITS |  |  | 449 | 625 | 63 | 19-Aug-22 A | 12-May-25 | J: 83
EFG-642 | HVAC Diffusers/ Devices @ (UNITS) |  |  | 20 | 625 | 1 | 19-Aug-22 A | 05-Mar-25 | J: 85; A: HVAC Diffusers/ Devices @ (UNITS)
EFG-640 | Plumbing Fixtures @ (UNITS) |  |  | 20 | 146 | 1 | 08-Jul-24 A | 04-Mar-25 | J: 85; J: Plumbing Fixtures @ (UNITS)
EFG-600 | Set Countertops @ (UNITS) |  |  | 10 | 116 | 9 | 19-Aug-24 A | 25-Feb-25 | J: 85; J: Set Countertops @ (UNITS)
EFG-580 | Final Paint @ (UNITS) |  |  | 15 | 108 | 4 | 29-Aug-24 A | 05-Mar-25 | J: 71; J: Final Paint @ (UNITS)
EFG-2093 | Set Kitchen Equipment |  |  | 8 | 0 | 8 | 19-Feb-25 | 28-Feb-25 | J: 88; J: Set Kitchen Equipment
EFG-2123 | Window Shades |  |  | 5 | 0 | 5 | 05-Mar-25 | 11-Mar-25 | J: 112; J: Window Shades
EFG-2113 | Install Owner provided lifts |  |  | 5 | 0 | 5 | 06-Mar-25 | 12-Mar-25 | J: 126; J: Install Owner provided lifts
EFG-610 | Bathroom - Accessories @ (UNITS) |  |  | 15 | 0 | 15 | 22-Apr-25 | 12-May-25 | J: 48; N: Bathroom - Accessories @ (UNITS)
|  | PHASE-1: COTTAGE-E/F/G_HOUSEHOLD E: FINISHES - CORRIDORS / COMMONS (CORR/COM) |  | 372 | 448 | 91 | 01-May-23 A | 10-Jun-25 | J: 48
EFG-662 | HVAC Diffusers/ Devices @ (CORR/COM) |  |  | 20 | 448 | 1 | 01-May-23 A | 05-Mar-25 | J: 85; S: HVAC Diffusers/ Devices @ (CORR/COM)
EFG-660 | Plumbing Fixtures @ (CORR/COM) |  |  | 20 | 448 | 2 | 01-May-23 A | 03-Apr-25 | J: 64; S: Plumbing Fixtures @ (CORR/COM)
EFG-674 | Sprinkler Devices @ (CORR/COM) |  |  | 20 | 384 | 2 | 01-Aug-23 A | 04-Feb-25 | J: 106; J: Sprinkler Devices @ (CORR/COM)
EFG-670 | Drop ACT Ceiling Tile @ (CO RR/COM) |  |  | 10 | 317 | 2 | 03-Nov-23 A | 03-Apr-25 | J: 64; O: Drop ACT Ceiling Tile @ (CORR/COM)
EFG-2250 | Wall Prot ec tion @ (CORR /COM) |  |  | 32 | 184 | 3 | 13-May-24 A | 27-Mar-25 | J: 100; A: Wall Prot ec tion @ (CORR /COM)
EFG-620 | Final Paint @ (CORR/COM) |  |  | 15 | 116 | 4 | 19-Aug-24 A | 14-Mar-25 | J: 64; J: Final Paint @ (CORR/COM)
EFG-630 | Wall Covering s @ (CORR/COM) |  |  | 20 | 60 | 13 | 06-Nov-24 A | 27-Mar-25 | J: 64; A: Wall Coverings @ (CORR/COM)
EFG-676 | Install Specialty Doors |  |  | 2 | 0 | 2 | 17-Mar-25 | 18-Mar-25 | J: 92; J: Install Specialty Doors
EFG-690 | Carpet @ (CORR/COM) |  |  | 15 | 0 | 15 | 04-Apr-25 | 24-Apr-25 | J: 80; A: Carpet @ (CORR/COM)
EFG-680 | Bathroom - Accessories @ (CORR/COM) |  |  | 20 | 0 | 20 | 13-May-25 | 10-Jun-25 | J: 48; D: Bathroom - Accessories @ (CORR/COM)
| PHASE-1: NORTHWEST_COURTYARD /LANDSCP/ HARDSCP |  |  | 216 | 235 | 32 | 01-Mar-24 A | 18-Mar-25 | J: 122
EFG-4464 | Rough Grade - Tou ch Up |  |  | 5 | 179 | 1 | 01-Mar-24 A | 03-Feb-25 | J: 93; J: Rough Grade - Touch Up
EFG-465 | Concrete Walk s & Concret e Paving |  |  | 15 | 163 | 1 | 12-Jun-24 A | 03-Feb-25 | J: 122; J: Concrete Walk s & Concrete Paving
EFG-485 | Phenolic Panels |  |  | 3 | 95 | 1 | 18-Sep-24 A | 24-Feb-25 | J: 122; M: Phenolic Panels
EFG-495 | Expansion Joints |  |  | 5 | 0 | 5 | 04-Feb-25 | 10-Feb-25 | J: 122; M: Expansion Joints
EFG-805 | Install EFG Walk way Windows |  |  | 10 | 0 | 10 | 11-Feb-25 | 24-Feb-25 | J: 122; J: Install EFG Walk way Windows
EFG-520 | Final Grade |  |  | 5 | 0 | 5 | 25-Feb-25 | 03-Mar-25 | J: 122; M: Final Grade
EFG-475 | Seeding |  |  | 1 | 0 | 1 | 04-Mar-25 | 04-Mar-25 | J: 132; A: Seeding
EFG-540 | Plantings |  |  | 5 | 0 | 5 | 04-Mar-25 | 10-Mar-25 | J: 122; M: Plantings
EFG-825 | Grills |  |  | 1 | 0 | 1 | 04-Mar-25 | 04-Mar-25 | J: 132; A: Grills
EFG-455 | Weed Barrier |  |  | 3 | 0 | 3 | 11-Mar-25 | 13-Mar-25 | J: 122; M: Weed Barrier
EFG-435 | Mulch |  |  | 3 | 0 | 3 | 14-Mar-25 | 18-Mar-25 | J: 122; A: Mulch
EFG-560 | COURTYARD-B COMPLETE |  |  | 0 | 0 | 0 |  | 18-Mar-25 | J: 122; A: COURTYARD-B COMPLETE
| PHASE-1: COTTAGE-E/F/G_FINAL CLEAN / PUNCH / TURNOVER |  |  | 136 | 0 | 136 | 02-Apr-25 | 13-Oct-25 | J: 23
EFG-715 | Submit Conrols Testing Plan |  |  | 5 | 0 | 5 | 02-Apr-25 | 08-Apr-25 | J: 64; A: Submit Conrols Testing Plan
EFG-795 | Inst Signage |  |  | 5 | 0 | 5 | 25-Apr-25 | 01-May-25 | J: 80; J: Inst Signage
EFG-735 | Sprinkler Systems Test |  |  | 5 | 0 | 5 | 23-May-25 | 30-May-25 | J: 70; S: Sprinkler Systems Test
EFG-745 | Fire AlarmTest |  |  | 5 | 0 | 5 | 13-Jun-25 | 19-Jun-25 | J: 56; A: Fire AlarmTest
| Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 17 of 46 |  | J: TASK filter: Activity Status.
| Actual Level of Effort | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  | Original | Actual | Remaining | Start | Finish | J: Total Float; J: 2025; J: 2026; M: 2027
|  |  |  | Duration | Duration | Duration | [30 empty] | M
[9 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
EFG-712 | Main Feeders Ready to Test - EF G |  |  | 0 | 0 | 0 |  | 07-Jul-25 | J: 2; D: Main Feeders Ready to Test - EF G
EFG-695 | Air & Water Balancing |  |  | 10 | 0 | 10 | 08-Jul-25 | 21-Jul-25 | J: 28; N: Air & Water Balancing
EFG-725 | Controls Test ing |  |  | 10 | 0 | 10 | 08-Jul-25 | 21-Jul-25 | J: 2; O: Controls Test ing
EFG-705 | HVAC Commissioning |  |  | 15 | 0 | 15 | 22-Jul-25 | 11-Aug-25 | J: 2; D: HVAC Commissioning
EFG-4514 | Rough Clean @ EFG |  |  | 5 | 0 | 5 | 22-Jul-25 | 28-Jul-25 | J: 12; N: Rough Clean @ EFG
EFG-772 | Red Zone Meeting |  |  | 60 | 0 | 60 | 08-Aug-25 | 07-Oct-25 | J: 38; J: Red Zone Meeting
EFG-775 | Performance Verification Testing |  |  | 10 | 0 | 10 | 12-Aug-25 | 25-Aug-25 | J: 20; J: Performance Verification Testing
EFG-4474 | Government Furniture Installation @ EFG |  |  | 5 | 0 | 5 | 12-Aug-25 | 16-Aug-25 | J: 2; M: Government Furniture Installation @ EFG
EFG-4484 | Pre-Final Data Room Inspection & Punchlist Generation |  |  | 2 | 0 | 2 | 12-Aug-25 | 13-Aug-25 | J: 13; M: Pre-Final Data Room Inspection & Punchlist Generation
EFG-4494 | Data Room Punchlist Corrections |  |  | 5 | 0 | 5 | 14-Aug-25 | 20-Aug-25 | J: 13; J: Data Room Punchlist Corrections
EFG-710 | Final Clean |  |  | 5 | 0 | 5 | 18-Aug-25 | 22-Aug-25 | J: 1; N: Final Clean
EFG-4504 | IT Room(s) Ready for VA Move In |  |  | 0 | 0 | 0 |  | 20-Aug-25 | J: 20; J: IT Room(s) Ready for VA Move In
EFG-720 | Contractor Pre-Final Inspections |  |  | 10 | 0 | 10 | 25-Aug-25 | 08-Sep-25 | J: 1; F: Contractor Pre-Final Inspections
EFG-730 | SUBSTANTIAL COMPLETION |  |  | 0 | 0 | 0 |  | 08-Sep-25 | J: 1; F: SUBSTANTIAL COMPLETION
EFG-755 | Contractor Pre-Final Punchlist Corrections |  |  | 10 | 0 | 10 | 09-Sep-25 | 22-Sep-25 | J: 1; A: Contractor Pre-Final Punchlist Corrections
EFG-760 | Government Pre-Final Inspections |  |  | 5 | 0 | 5 | 23-Sep-25 | 29-Sep-25 | J: 1; M: Government Pre-Final Inspections
EFG-765 |  | Corrections of Punchlist from Government Pre-Final Inspection |  | 5 | 0 | 5 | 30-Sep-25 | 06-Oct-25 | J: 1; J: Corrections of Punchlist from Government Pre-Final Inspection
EFG-770 | Final Inspections |  |  | 5 | 0 | 5 | 07-Oct-25 | 13-Oct-25 | J: 1; J: Final Inspections
EFG-750 | READY FOR OCCUPANCY |  |  | 0 | 0 | 0 |  | 13-Oct-25 | J: 1; M: READY FOR OCCUPANCY
| PHASE-1:COMMUNITY CENTER |  |  | 717 | 686 | 188 | 24-May-22 A | 27-Oct-25 | J: 13
| PHASE-1: BUILDING ENCLOSURE / WAT ER TIGH T |  |  | 69 | 353 | 1 | 14-Sep-23 A | 03-Feb-25 | J: 95
COM-1170 | Punched Openings (Window / Door Installation) |  |  | 15 | 353 | 1 | 14-Sep-23 A | 03-Feb-25 | J: 95; S: Punched Openings (Window / Door Installation)
COM-1150 | Roofing Shingles |  |  | 25 | 253 | 1 | 21-Sep-23 A | 03-Feb-25 | J: 70; A: Roofing Shingles
| PHASE-1: EXTERIOR BUILDING FINISHES COMMUNITY CNTR |  |  | 480 | 583 | 51 | 19-Oct-22 A | 14-Apr-25 | J: 95
COM-1220 | Siding / Alum. Fascia Comp Wall Panels |  |  | 20 | 583 | 3 | 19-Oct-22 A | 17-Mar-25 | J: 95; O: Siding / Alum. Fascia Comp Wall Panels
COM-2210 | Terra Cotta Rain Screens |  |  | 40 | 182 | 6 | 15-May-24 A | 10-Feb-25 | J: 95; J: Terra Cotta Rain Screens
COM-2240 | Expansion Joint Installation |  |  | 8 | 163 | 4 | 12-Jun-24 A | 06-Feb-25 | J: 122; J: Expansion Joint Installation
COM-2220 | Sun Shades |  |  | 20 | 0 | 20 | 18-Mar-25 | 14-Apr-25 | J: 95; J: Sun Shades
| PHASE-1: PENTHOUSE - MEP/FP ROUGH |  |  | 554 | 546 | 25 | 12-Dec-22 A | 07-Mar-25 | J: 86
COM-4230 | Set MEP Units |  |  | 10 | 546 | 1 | 12-Dec-22 A | 03-Feb-25 | J: 71; A: Set MEP Units
COM-4200 | MEP Firestopping |  |  | 2 | 265 | 1 | 19-Jan-24 A | 03-Feb-25 | J: 71; A: MEP Firestopping
COM-1232 | HVAC Duct & Piping Insulation |  |  | 20 | 264 | 12 | 22-Jan-24 A | 18-Feb-25 | J: 60; J: HVAC Duct & Piping Insulation
COM-1250 | Sprinkler Rough |  |  | 10 | 196 | 1 | 25-Apr-24 A | 03-Feb-25 | J: 71; A: Sprinkler Rough
| PHASE-1: MECH ROOM: HOT WATER SYSTEM |  |  | 477 | 503 | 25 | 13-Feb-23 A | 07-Mar-25 | J: 86
COM-4220 | Instal Boiler Sys Equip |  |  | 10 | 503 | 9 | 13-Feb-23 A | 13-Feb-25 | J: 86; M: Instal Boiler Sys Equip
COM-4240 | Install HW Syst Sup/Ret Lines |  |  | 10 | 191 | 6 | 02-May-24 A | 10-Feb-25 | J: 86; J: Install HW Syst Sup/Ret Lines
COM-4250 | Test HW Syst Sup/Ret Lines |  |  | 10 | 191 | 6 | 02-May-24 A | 11-Feb-25 | J: 86; J: Test HW Syst Sup/Ret Lines
COM-4270 | Instal Elec for Boiler Sys Equip |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: 92; J: Instal Elec for Boiler Sys Equip
COM-4260 | Insulate HW Syst Sup/Ret Lines |  |  | 9 | 0 | 9 | 12-Feb-25 | 24-Feb-25 | J: 86; J: Insulate HW Syst Sup/Ret Lines
COM-4280 | Start-up Boiler Sys Equip |  |  | 9 | 0 | 9 | 25-Feb-25 | 07-Mar-25 | J: 86; J: Start-up Boiler Sys Equip
| PHASE-1: GROUND LEVEL - MEP/FP ROUGH |  |  | 418 | 649 | 12 | 18-Jul-22 A | 18-Feb-25 | J: 75
COM-2130 | Plumbing Rough / Insulation |  |  | 20 | 649 | 1 | 18-Jul-22 A | 03-Feb-25 | J: 71; J: Plumbing Rough / Insulation
COM-2142 | OH Rough Electrical/ Security/ AV Systems |  |  | 20 | 520 | 2 | 19-Jan-23 A | 04-Feb-25 | J: 70; A: OH Rough Electrical/ Security/ AV Systems
COM-2122 | HVAC Duct & Piping Insulation |  |  | 20 | 509 | 2 | 03-Feb-23 A | 04-Feb-25 | J: 85; J: HVAC Duct & Piping Insulation
COM-2154 | Install Fire Alarm Cable |  |  | 10 | 292 | 1 | 11-Dec-23 A | 03-Feb-25 | J: 86; M: Install Fire Alarm Cable
COM-2162 | MEP Firestopping |  |  | 2 | 265 | 1 | 19-Jan-24 A | 04-Feb-25 | J: 70; A: MEP Firestopping
COM-2152 | Install Data/ Security/ Nurse/ TV/ PA Cable |  |  | 10 | 199 | 1 | 22-Apr-24 A | 03-Feb-25 | J: 86; A: Install Data/ Security/ Nurse/ TV/ PA Cable
COM-2160 | INSPECTION - MEPs |  |  | 0 | 0 | 0 |  | 18-Feb-25 | J: 60; J: INSPECTION - MEPs
| PHASE-1: GROUND LEVEL - INTERIOR WALL & CEILING FRAMING |  |  | 30 | 523 | 6 | 16-Jan-23 A | 10-Feb-25 | J: 72
| Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 18 of 46 |  | J: TASK filter: Activity Status.
| Actual Level of Effort | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  | Original | Actual | Remaining | Start | Finish | J: Total Float; J: 2025; J: 2026; M: 2027
|  |  |  | Duration | Duration | Duration | [30 empty] | M
[9 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
COM-2000 | Framing - Ceilings / Soffits - Gnd Lvl |  |  | 30 | 523 | 6 | 16-Jan-23 A | 10-Feb-25 | J: 72; J: Framing - Ceilings / Soffits - Gnd Lvl
| PHASE-1: DRYWALL / PRIME-PAINT @ (GROUND LEVEL & PENTHOUSE) |  |  | 134 | 468 | 7 | 03-Apr-23 A | 27-Feb-25 | J: 60
COM-1310 | Drywall - Walls / Ceilings / Soffits @ (ENTIRE FACILITY) |  |  | 20 | 468 | 1 | 03-Apr-23 A | 19-Feb-25 | J: 61; N: Drywall - Walls / Ceilings / Soffits @ (ENTIRE FACILITY)
COM-1320 | Drywall - Tape / Finish @ (ENTIRE FACILITY) |  |  | 25 | 462 | 2 | 11-Apr-23 A | 20-Feb-25 | J: 61; S: Drywall - Tape / Finish @ (ENTIRE FACILITY)
COM-1340 | Prime / 1st Coat Paint @ (ENTIRE FACILITY) |  |  | 15 | 261 | 7 | 25-Jan-24 A | 27-Feb-25 | J: 60; S: Prime / 1st Coat Paint @ (ENTIRE FACILITY)
|  | PHASE-1: OVERHEAD FINISHES / FIXTURES / DEVICES @ (GROUND LEVEL & PENTHOUSE) |  | 403 | 493 | 73 | 27-Feb-23 A | 02-Jun-25 | J: 58
COM-1890 | Paint Exposed Ceilings |  |  | 10 | 493 | 1 | 27-Feb-23 A | 27-Feb-25 | J: 68; J: Paint Exposed Ceilings
COM-2180 | Overhead HVAC Finishes/ Devices @ (CORR/COM) |  |  | 30 | 264 | 1 | 22-Jan-24 A | 19-May-25 | J: 29; J: Overhead HVAC Finishes/ Devices @ (CORR/COM)
COM-2182 | Overhead Light Fixtures @ (CORR/COM) |  |  | 20 | 202 | 2 | 17-Apr-24 A | 19-May-25 | J: 30; D: Overhead Light Fixtures @ (CORR/COM)
COM-2184 | Overhead Sprinkler Heads @ (CORR/COM) |  |  | 20 | 145 | 12 | 09-Jul-24 A | 19-May-25 | J: 40; D: Overhead Sprinkler Heads @ (CORR/COM)
COM-1360 | ACT Ceiling Grid @ (CORR/COM) |  |  | 12 | 24 | 11 | 30-Dec-24 A | 05-Mar-25 | J: 75; A: ACT Ceiling Grid @ (CORR/COM)
COM-2170 | Suspended Wood Ceilings @ (CORR/COM) |  |  | 15 | 0 | 15 | 10-Mar-25 | 28-Mar-25 | J: 47; O: Suspended Wood Ceilings @ (CORR/COM)
COM-2200 | Privacy Curtains & Tracks |  |  | 15 | 0 | 15 | 22-Apr-25 | 12-May-25 | J: 29; S: Privacy Curtains & Tracks
COM-2194 | Inst Ceiling Tiles for OH Devices |  |  | 10 | 0 | 10 | 19-May-25 | 02-Jun-25 | J: 58; N: Inst Ceiling Tiles for OH Devices
| PHASE-1: TRIM / MILLWORK / COUNTERTOPS |  |  | 50 | 0 | 50 | 21-Feb-25 | 01-May-25 | J: 87
COM-1350 | Bistro / Severy Fitout @ (CAFÉ) |  |  | 15 | 0 | 15 | 21-Feb-25 | 13-Mar-25 | J: 112; A: Bistro / Severy Fitout @ (CAFÉ)
COM-1440 | Doors / Running Trim @ (SUPPORT) |  |  | 10 | 0 | 10 | 13-Mar-25 | 26-Mar-25 | J: 56; S: Doors / Running Trim @ (SUPPORT)
COM-1500 | Doors / Running Trim @ (CORR/COM) |  |  | 10 | 0 | 10 | 31-Mar-25 | 11-Apr-25 | J: 47; O: Doors / Running Trim @ (CORR/COM)
COM-1390 | Millwork / Vanities / Cabinets @ (SUPPORT) |  |  | 10 | 0 | 10 | 02-Apr-25 | 15-Apr-25 | J: 47; N: Millwork / Vanities / Cabinets @ (SUPPORT)
COM-1410 | Template Countertops @ (SUPPORT) |  |  | 7 | 0 | 7 | 16-Apr-25 | 24-Apr-25 | J: 58; O: Template Countertops @ (SUPPORT)
COM-1570 | Millwork / Casework @ (CORR/COM) |  |  | 10 | 0 | 10 | 16-Apr-25 | 29-Apr-25 | J: 47; N: Millwork / Casework @ (CORR/COM)
COM-1430 | Millwork / Casework @ (CAFÉ) |  |  | 5 | 0 | 5 | 16-Apr-25 | 22-Apr-25 | J: 89; S: Millwork / Casework @ (CAFÉ)
COM-1470 | Set Countertops @ (SUPPORT) |  |  | 3 | 0 | 3 | 25-Apr-25 | 29-Apr-25 | J: 58; O: Set Countertops @ (SUPPORT)
COM-2123 | Window Shades |  |  | 5 | 0 | 5 | 25-Apr-25 | 01-May-25 | J: 87; J: Window Shades
| PHASE-1: FINAL FINISHES (GROUND LEVEL & PENTHOUSE) |  |  | 374 | 686 | 70 | 24-May-22 A | 27-Jun-25 | J: 52
| PHASE-1: FINISHES - SUPPORT SPACES / CORRIDORS & COMMONS |  |  | 374 | 686 | 70 | 24-May-22 A | 27-Jun-25 | J: 52
COM-1510 | Plumbing Fixtures @ (SUPPORT) |  |  | 10 | 686 | 1 | 24-May-22 A | 06-May-25 | J: 58; O: Plumbing Fixtures @ (SUPPORT)
COM-1670 | Plumbing Fixtures @ (CORR/COM) |  |  | 7 | 438 | 1 | 15-May-23 A | 06-May-25 | J: 62; O: Plumbing Fixtures @ (CORR/COM)
COM-1514 | Electrical Devices @ (SUPPORT) |  |  | 10 | 350 | 7 | 19-Sep-23 A | 31-Mar-25 | J: 84; S: Electrical Devices @ (SUPPORT)
COM-1674 | Electrical Devices @ (CORR/COM) |  |  | 7 | 350 | 5 | 19-Sep-23 A | 27-Mar-25 | J: 97; S: Electrical Devices @ (CORR/COM)
COM-1512 | HVAC Finishes/ Devices @ (SUPPORT) |  |  | 10 | 264 | 3 | 22-Jan-24 A | 24-Apr-25 | J: 66; N: HVAC Finishes/ Devices @ (SUPPORT)
COM-1672 | HVAC Finishes/ Devices @ (CORR/COM) |  |  | 7 | 264 | 2 | 22-Jan-24 A | 27-May-25 | J: 46; D: HVAC Finishes/ Devices @ (CORR/COM)
COM-1518 | Data/ Security/ Nurse/ TV/ PA Devices @ (SUPPORT) |  |  | 10 | 28 | 8 | 23-Dec-24 A | 06-May-25 | J: 54; J: Data/ Security/ Nurse/ TV/ PA Devices @ (SUPPORT)
COM-1678 | Data/ Security/ Nurse/ TV/ PA Devices @ (CORR/COM) |  |  | 7 | 28 | 6 | 23-Dec-24 A | 04-Jun-25 | J: 40; F: Data/ Security/ Nurse/ TV/ PA Devices @ (CORR/COM)
COM-1420 | Final Paint @ (SUPPORT) |  |  | 7 | 0 | 7 | 16-Apr-25 | 24-Apr-25 | J: 51; A: Final Paint @ (SUPPORT)
COM-1490 | Bathroom - Accessories @ (SUPPORT) |  |  | 5 | 0 | 5 | 25-Apr-25 | 01-May-25 | J: 61; N: Bathroom - Accessories @ (SUPPORT)
COM-1516 | Fire Alarm Devices @ (SUPPORT) |  |  | 10 | 0 | 10 | 25-Apr-25 | 08-May-25 | J: 51; O: Fire Alarm Devices @ (SUPPORT)
COM-2053 | Misc medical |  |  | 5 | 0 | 5 | 25-Apr-25 | 01-May-25 | J: 87; J: Misc medical
COM-1990 | Install Specialty Doors |  |  | 2 | 0 | 2 | 25-Apr-25 | 28-Apr-25 | J: 70; A: Install Specialty Doors
COM-2270 | Tile @ (SUPPORT) |  |  | 15 | 0 | 15 | 09-May-25 | 30-May-25 | J: 62; S: Tile @ (SUPPORT)
COM-1600 | Flooring @ (SUPPORT) |  |  | 15 | 0 | 15 | 09-May-25 | 30-May-25 | J: 62; S: Flooring @ (SUPPORT)
COM-2260 | Drop ACT Ceiling Tile @ (SUPPORT) |  |  | 5 | 0 | 5 | 09-May-25 | 15-May-25 | J: 56; N: Drop ACT Ceiling Tile @ (SUPPORT)
COM-1640 | Final Paint @ (CORR/COM) |  |  | 6 | 0 | 6 | 19-May-25 | 27-May-25 | J: 29; O: Final Paint @ (CORR/COM)
COM-1660 | Wall Covering s @ (CORR/COM) |  |  | 6 | 0 | 6 | 20-May-25 | 28-May-25 | J: 49; N: Wall Co verings @ (CORR/COM)
COM-1676 | Fire Alarm Devices @ (CORR/COM) |  |  | 7 | 0 | 7 | 28-May-25 | 05-Jun-25 | J: 39; D: Fire Alarm Devices @ (CORR/COM)
COM-2250 | Wall Prot ec tion @ (CORR /COM) |  |  | 15 | 0 | 15 | 29-May-25 | 18-Jun-25 | J: 49; D: Wall Prot ec tion @ (CORR /COM)
COM-2043 | Signage @ COM |  |  | 5 | 0 | 5 | 29-May-25 | 04-Jun-25 | J: 69; A: Signage @ COM
COM-1680 | Bathroom - Accessories @ (CORR/COM) |  |  | 3 | 0 | 3 | 03-Jun-25 | 05-Jun-25 | J: 58; J: Bathroom - Accessories @ (CORR/COM)
COM-2280 | Tile @ (CORR/COM) |  |  | 15 | 0 | 15 | 06-Jun-25 | 26-Jun-25 | J: 48; O: Tile @ (CORR/COM)
| Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 19 of 46 |  | J: TASK filter: Activity Status.
| Actual Level of Effort | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  | Original | Actual | Remaining | Start | Finish | Total Float | M: 2025; J: 2026; F: 2027
|  |  | Duration | Duration | Duration | bar: A
[8 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
COM-1690 | Drop ACT Ceiling Tile @ (CO RR/COM) |  | 3 | 0 | 3 | 06-Jun-25 | 10-Jun-25 | J: 39; D: Drop ACT Ceiling Tile @ (CORR/COM)
COM-1710 | Flooring @ (CORR/COM) |  | 15 | 0 | 15 | 09-Jun-25 | 27-Jun-25 | J: 47; N: Flooring @ (CORR/COM)
| PHASE-1: FINAL FINISHES (BISTRO / SERVERY) |  | 337 | 438 | 26 | 15-May-23 A | 24-Jun-25 | J: 43
COM-1554 | Plumbing Finishes/ Connections to Kitchen Equip @ (CAFÉ) |  | 3 | 438 | 1 | 15-May-23 A | 24-Jun-25 | J: 38; M: Plumbing Finishes/ Connections to Kitchen Equip @ (CAFÉ)
COM-1556 | Electrical Fixtures/ Devices/ Connections to Kitchen Equip @ (CAFÉ) |  | 3 | 378 | 1 | 09-Aug-23 A | 24-Jun-25 | J: 43; A: Electrical Fixtures/ Devices/ Connections to Kitchen Equip @ (CAFÉ)
COM-1540 | Bistro Fitout & Specialities |  | 15 | 0 | 15 | 19-May-25 | 09-Jun-25 | J: 29; O: Bistro Fitout & Specialities
COM-1630 | Epoxy Floor @ (SERVERY) |  | 8 | 0 | 8 | 10-Jun-25 | 19-Jun-25 | J: 29; N: Epoxy Floor @ (SERVERY)
COM-1550 | Set Kitchen Equipment @ (CAFÉ) |  | 2 | 0 | 2 | 20-Jun-25 | 23-Jun-25 | J: 34; N: Set Kitchen Equipment @ (CAFÉ)
COM-1650 | Set / Connect Kitchen Equipment @ (SERVERY) |  | 3 | 0 | 3 | 20-Jun-25 | 24-Jun-25 | J: 29; F: Set / Connect Kitchen Equipment @ (SERVERY)
| PHASE-1: FINAL CLEAN / PUNCH / TURNOVER |  | 92 | 0 | 92 | 18-Jun-25 | 27-Oct-25 | J: 13
COM-1700 | HVAC Systems Startups |  | 10 | 0 | 10 | 18-Jun-25 | 01-Jul-25 | J: 29; N: HVAC Systems Startups
COM-1702 | Submit Conrols Testing Plan |  | 5 | 0 | 5 | 18-Jun-25 | 24-Jun-25 | J: 29; N: Submit Conrols Testing Plan
COM-1720 | Rough Clean |  | 5 | 0 | 5 | 25-Jun-25 | 01-Jul-25 | J: 45; S: Rough Clean
COM-1712 | Fire AlarmTest |  | 2 | 0 | 2 | 08-Jul-25 | 09-Jul-25 | J: 35; O: Fire AlarmTest
COM-1790 | Contractor Pre-Final Inspections |  | 10 | 0 | 10 | 10-Jul-25 | 23-Jul-25 | J: 35; D: Contractor Pre-Final Inspections
COM-4454 | Main Feeders Ready to Test - COM |  | 0 | 0 | 0 |  | 18-Aug-25 | J: -9; F: Main Feeders Ready to Test - COM
COM-1704 | Controls Test ing |  | 10 | 0 | 10 | 19-Aug-25 | 02-Sep-25 | J: -9; N: Controls Test ing
COM-1706 | Air & Water Balancing |  | 10 | 0 | 10 | 19-Aug-25 | 02-Sep-25 | J: 0; D: Air & Water Balancing
COM-1708 | Sprinkler Systems Test |  | 5 | 0 | 5 | 19-Aug-25 | 25-Aug-25 | J: 12; D: Sprinkler Systems Test
COM-4210 | Red Zone Meeting |  | 60 | 0 | 60 | 22-Aug-25 | 21-Oct-25 | J: 24; J: Red Zone Meeting
COM-1714 | HVAC Commissioning |  | 10 | 0 | 10 | 29-Aug-25 | 12-Sep-25 | J: -9; D: HVAC Commissioning
COM-4484 | Government Furniture/IT Installation @ Bldg K |  | 5 | 0 | 5 | 13-Sep-25 | 17-Sep-25 | J: -13; A: Government Furniture/IT Installation @ Bldg K
COM-1716 | Performance Verification Testing |  | 10 | 0 | 10 | 15-Sep-25 | 26-Sep-25 | J: -1; F: Performance Verification Testing
COM-4494 | Pre-Final Data Room Inspection & Punchlist Generation |  | 2 | 0 | 2 | 15-Sep-25 | 16-Sep-25 | J: -8; M: Pre-Final Data Room Inspection & Punchlist Generation
COM-4504 | Data Room Punchlist Corrections |  | 5 | 0 | 5 | 17-Sep-25 | 23-Sep-25 | J: -8; F: Data Room Punchlist Corrections
COM-1770 | Final Clean |  | 5 | 0 | 5 | 18-Sep-25 | 24-Sep-25 | J: -9; N: Final Clean
COM-4514 | IT Room(s) Read for VA Move In |  | 0 | 0 | 0 |  | 23-Sep-25 | J: -12; F: IT Room(s) Read for VA Move In
COM-1780 | COMMUNITY CENTER - SUBSTANTIAL C OMPLETION |  | 0 | 0 | 0 |  | 24-Sep-25 | J: -9; J: COMMUNITY CENTER - SUBSTANTIAL COMPLETION
COM-1800 | Contractor Pre-Final Punchlist Corrections |  | 10 | 0 | 10 | 25-Sep-25 | 08-Oct-25 | J: -9; A: Contractor Pre-Final Punchlist Corrections
COM-1810 | Government Pre-Final Inspections |  | 8 | 0 | 8 | 09-Oct-25 | 20-Oct-25 | J: -9; M: Government Pre-Final Inspections
COM-1820 | Final Inspections |  | 3 | 0 | 3 | 21-Oct-25 | 23-Oct-25 | J: -7; J: Final Inspections
COM-1815 | Corrections of Punchlist from Government Pre-Final Inspection |  | 5 | 0 | 5 | 21-Oct-25 | 27-Oct-25 | J: -9; A: Corrections of Punchlist from Government Pre-Final Inspection
COM-1830 | COMMUNITY CENTER - READY FOR OCCUPANCY |  | 0 | 0 | 0 |  | 27-Oct-25 | J: -9; J: COMMUNITY CENTER - READY FOR OCCUPANCY
| PHASE-1: ENTRY BUILDING L & WALKWAYS |  | 507 | 511 | 169 | 01-Feb-23 A | 30-Sep-25 | J: 32
PHASE-1: BUILDING L |  |  | 358 | 244 | 131 | 19-Feb-24 A | 06-Aug-25 | J: 70
L-1130 | Wall F rame In terior & Exterior BLDG L |  | 4 | 183 | 1 | 19-Feb-24 A | 03-Feb-25 | J: -1; A: Wall F rame Interior & Exterior BLDG L
L-1200 | Roofing VB & Slate Shingle BLDG L |  | 5 | 57 | 1 | 02-Oct-24 A | 03-Feb-25 | J: 0; A: Roofing VB & Slate Shingle BLDG L
L-1240 | 3" Rigid Wall Insulat ion BL DG L |  | 4 | 36 | 2 | 11-Dec-24 A | 07-Feb-25 | J: -2; J: 3" Rigid Wall Insulation BL DG L
L-1260 | Metal Panel System BLDG L |  | 2 | 36 | 1 | 11-Dec-24 A | 10-Feb-25 | J: 164; J: Metal Panel System BLDG L
L-1190 | Mechanical Hangers BLDG L |  | 5 | 31 | 2 | 18-Dec-24 A | 04-Feb-25 | J: 1; J: Mechanical Hangers BLDG L
L-1120 | Install Door Frames BLDG L |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: -4; J: Install Door Frames BLDG L
L-1220 | Roof Inspection BLDG L |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: 178; J: Roof Inspection BLDG L
L-1140 | Framing Inspection BLDG L |  | 2 | 0 | 2 | 04-Feb-25 | 05-Feb-25 | J: -2; J: Framing Inspection BLDG L
L-1280 | Pre-Rock Bottom of Trusses BLDG L |  | 2 | 0 | 2 | 10-Feb-25 | 11-Feb-25 | J: -2; A: Pre-Rock Bottom of Trusses BLDG L
L-1300 | Terra Cotta System BLDG L |  | 10 | 0 | 10 | 11-Feb-25 | 24-Feb-25 | J: 164; J: Terra Cotta System BLDG L
L-1320 | Mech In-wall Rough in BLDG L |  | 5 | 0 | 5 | 12-Feb-25 | 18-Feb-25 | J: 60; J: Mech In-wall Rough in BLDG L
L-1310 | Mech Overhead Rough in BLDG L |  | 15 | 0 | 15 | 12-Feb-25 | 04-Mar-25 | J: 46; A: Mech Overhead Rough in BLDG L
L-1590 | Plumbing Overhead Rough in BLDG L |  | 15 | 0 | 15 | 12-Feb-25 | 04-Mar-25 | J: 46; S: Plumbing Overhead Rough in BLDG L
L-1600 | Electrical Overhead Rough in BLDG L |  | 15 | 0 | 15 | 12-Feb-25 | 04-Mar-25 | J: -2; S: Electrical Overhead Rough in BLDG L
Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 20 of 46 |  | J: TASK filter: Activity Status.
Actual Level of Effort | Remaining Work | Milestone | [5 empty] | D: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  | Original | Actual | Remaining | Start | J: Finish; F: Total Float; J: 2025; J: 2026; A: 2027
|  |  |  | Duration | Duration | Duration | [30 empty] | M
[9 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
L-1610 | Electric In-wall Rough in BLDG L |  |  | 5 | 0 | 5 | 12-Feb-25 | 18-Feb-25 | J: 60; J: Electric In-wall Rough in BLDG L
L-1620 | Plumbing In-wall Rough in BLDG L |  |  | 5 | 0 | 5 | 12-Feb-25 | 18-Feb-25 | J: 60; A: Plumbing In-wall Rough in BLDG L
L-1630 | Fire Protection Overhead Rough in BLDG L |  |  | 15 | 0 | 15 | 12-Feb-25 | 04-Mar-25 | J: 46; O: Fire Protection Overhead Rough in BLDG L
L-1330 | MEP In-wall Rough in Inspection BLDG L |  |  | 2 | 0 | 2 | 19-Feb-25 | 20-Feb-25 | J: 60; S: MEP In-wall Rough in Inspection BLDG L
L-1340 | Insulate Wall BL DG L |  |  | 2 | 0 | 2 | 21-Feb-25 | 24-Feb-25 | J: 60; J: Insulate Wall BLDG L
L-1360 | Hang Drywall BLDG L |  |  | 3 | 0 | 3 | 25-Feb-25 | 27-Feb-25 | J: 60; J: Hang Drywall BLDG L
L-1350 | Site Finishes & Landscaping BLDG L |  |  | 10 | 0 | 10 | 25-Feb-25 | 10-Mar-25 | J: 164; S: Site Finishes & Landscaping BLDG L
L-1380 | Frame Hard Ceilings BLDG L |  |  | 3 | 0 | 3 | 05-Mar-25 | 07-Mar-25 | J: 46; J: Frame Hard Ceilings BLDG L
L-820 | MEP Firestopping |  |  | 2 | 0 | 2 | 05-Mar-25 | 06-Mar-25 | J: 79; J: MEP Firestopping
L-1390 | Drop Diffusers in Hard Ceilings BLDG L |  |  | 3 | 0 | 3 | 10-Mar-25 | 12-Mar-25 | J: 46; S: Drop Diffusers in Hard Ceilings BLDG L
L-1392 | Drop Light Fixtures in Hard Ceilings BLDG L |  |  | 3 | 0 | 3 | 10-Mar-25 | 12-Mar-25 | J: 46; O: Drop Light Fixtures in Hard Ceilings BLDG L
L-1400 | Above Ceiling Inpsection #1 BLDG L |  |  | 3 | 0 | 3 | 13-Mar-25 | 17-Mar-25 | J: 46; S: Above Ceiling Inpsection #1 BLDG L
L-1410 | Insulate Attic BLDG L |  |  | 2 | 0 | 2 | 18-Mar-25 | 19-Mar-25 | J: 46; J: Insulate Attic BLDG L
L-1420 | Hang Hard Ceilings BLDG L |  |  | 1 | 0 | 1 | 20-Mar-25 | 20-Mar-25 | J: 46; A: Hang Hard Ceilings BLDG L
L-1290 | Curtain Wall & Entr y Doors | BLDG L |  | 3 | 0 | 3 | 12-May-25 | 14-May-25 | J: 6; S: Curtain Wall & Entr y Doors; M: BLDG L
L-1370 | Tape & Finish Drywall / Firetape BLDG L |  |  | 1 | 0 | 1 | 15-May-25 | 15-May-25 | J: 6; N: Tape & Finish Drywall / Firetape BLDG L
L-1430 | Final Tape and Finish BLDG L |  |  | 8 | 0 | 8 | 16-May-25 | 28-May-25 | J: 6; N: Final Tape and Finish BLDG L
L-1440 | Drywall Finish Punchlist BLDG L |  |  | 2 | 0 | 2 | 29-May-25 | 30-May-25 | J: 6; N: Drywall Finish Punchlist BLDG L
L-1450 | Prime Paint Wall BLDG L |  |  | 1 | 0 | 1 | 02-Jun-25 | 02-Jun-25 | J: 6; O: Prime Paint Wall BLDG L
L-1460 | 1st Coat Paint BLDG L |  |  | 1 | 0 | 1 | 03-Jun-25 | 03-Jun-25 | J: 6; O: 1st Coat Paint BLDG L
L-1470 | Install Ceiling Grid BLDG L |  |  | 3 | 0 | 3 | 04-Jun-25 | 06-Jun-25 | J: 6; O: Install Ceiling Grid BLDG L
L-1480 | Diffusers in Ceiling Grid BLDG L |  |  | 4 | 0 | 4 | 09-Jun-25 | 12-Jun-25 | J: 6; N: Diffusers in Ceiling Grid BLDG L
L-1482 | Light Fixtures in Ceiling Grid BLDG L |  |  | 4 | 0 | 4 | 09-Jun-25 | 12-Jun-25 | J: 6; D: Light Fixtures in Ceiling Grid BLDG L
L-1484 | Sprinkler Heads in Ceiling Grid BLDG L |  |  | 4 | 0 | 4 | 09-Jun-25 | 12-Jun-25 | J: 6; D: Sprinkler Heads in Ceiling Grid BLDG L
L-1490 | Install Doors & Hardware BLDG L |  |  | 3 | 0 | 3 | 13-Jun-25 | 17-Jun-25 | J: 6; D: Install Doors & Hardware BLDG L
L-1500 | Install Cabinets BLDG L |  |  | 2 | 0 | 2 | 13-Jun-25 | 16-Jun-25 | J: 9; O: Install Cabinets BLDG L
L-1510 | Above Ceiling Inpsection #2 BLDG L |  |  | 4 | 0 | 4 | 13-Jun-25 | 18-Jun-25 | J: 10; D: Above Ceiling Inpsection #2 BLDG L
L-1520 | Install Flooring BLDG L |  |  | 3 | 0 | 3 | 20-Jun-25 | 24-Jun-25 | J: 6; O: Install Flooring BLDG L
L-2133 | Misc medical |  |  | 5 | 0 | 5 | 25-Jun-25 | 01-Jul-25 | J: 10; S: Misc medical
L-1530 | Install Ceiling Tile BLDG L |  |  | 1 | 0 | 1 | 25-Jun-25 | 25-Jun-25 | J: 6; N: Install Ceiling Tile BLDG L
L-1540 | Final Paint BLDG L |  |  | 3 | 0 | 3 | 26-Jun-25 | 30-Jun-25 | J: 6; O: Final Paint BLDG L
L-2033 | Signage @ L |  |  | 5 | 0 | 5 | 01-Jul-25 | 08-Jul-25 | J: 6; S: Signage @ L
L-2123 | Window Shades |  |  | 5 | 0 | 5 | 01-Jul-25 | 08-Jul-25 | J: 6; O: Window Shades
L-1550 | Work Protection Panel BLDG L |  |  | 3 | 0 | 3 | 01-Jul-25 | 03-Jul-25 | J: 8; D: Work Protection Panel BLDG L
L-1560 | PHB Pre Punch BLDG L |  |  | 10 | 0 | 10 | 09-Jul-25 | 22-Jul-25 | J: 6; N: PHB Pre Punch BLDG L
L-2153 | Government Furniture/IT Installation @ Bldg L |  |  | 5 | 0 | 5 | 09-Jul-25 | 13-Jul-25 | J: 108; F: Government Furniture/IT Installation @ Bldg L
L-1570 | USACE Punch BLDG L |  |  | 10 | 0 | 10 | 23-Jul-25 | 05-Aug-25 | J: 70; D: USACE Punch BLDG L
L-1580 | AHJ C of O Walkthru BLDG L |  |  | 1 | 0 | 1 | 06-Aug-25 | 06-Aug-25 | J: 70; J: AHJ C of O Walkt hru BLDG L
PHASE-1: WALKWAYS |  |  |  | 507 | 511 | 169 | 01-Feb-23 A | 30-Sep-25 | J: 32
| PHASE-1: WALKWAY#2/#3/#1 (BLDG-K to (to CORNER of Y/L/J) to BLDG-J/I/H) |  |  | 494 | 511 | 169 | 01-Feb-23 A | 30-Sep-25 | J: 32
| PHASE-1: WALKWAY SITE WORK & STRUCTURE 1/2/3 |  |  | 298 | 424 | 5 | 05-Jun-23 A | 07-Feb-25 | J: 68
WW231-1310 | Interior & Exterior Brick |  |  | 25 | 424 | 1 | 05-Jun-23 A | 03-Feb-25 | J: 51; J: Interior & Exterior Brick
WW231-1170 | Set Wood Trusses |  |  | 8 | 270 | 1 | 22-Aug-23 A | 03-Feb-25 | J: 34; M: Set Wood Trusses
WW231-1180 | Inspect Trusses |  |  | 2 | 369 | 1 | 22-Aug-23 A | 03-Feb-25 | J: 51; A: Inspect Trusses
WW231-1190 | Sheath Roof |  |  | 8 | 262 | 1 | 06-Sep-23 A | 03-Feb-25 | J: 34; A: Sheath Roof
WW231-1200 | Shingle Roof |  |  | 10 | 231 | 1 | 27-Oct-23 A | 03-Feb-25 | J: 34; A: Shingle Roof
WW231-1260 | Install Vapor Barrier |  |  | 5 | 187 | 1 | 07-Feb-24 A | 03-Feb-25 | J: 34; M: Install Vapor Barrier
WW231-1300 | Electrical In-wall Rough in |  |  | 25 | 189 | 5 | 06-May-24 A | 07-Feb-25 | J: 68; J: Electrical In-wall Rough in
WW231-1340 | Insulate / Poly Bot of Trusses |  |  | 4 | 37 | 2 | 10-Dec-24 A | 05-Feb-25 | J: 51; J: Insulate / Poly Bot of Trusses
Remaining Level of Effort |  | Actual Work | Critical Remaining Work |  |  |  | Page 21 of 46 |  | J: TASK filter: Activity Status.
Actual Level of Effort |  | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  | Original | Actual | Remaining | Start | Finish | Total Float | M: 2025; M: 2026; F: 2027
|  |  | Duration | Duration | Duration | bar: A
[8 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
PHASE-1: WALKWAY FINISHES 1/2/3 |  |  | 439 | 511 | 114 | 01-Feb-23 A | 14-Jul-25 | J: 52
WW231-1470 | HVAC In Ceiling |  | 30 | 511 | 15 | 01-Feb-23 A | 14-Apr-25 | J: 38; J: HVAC In Ceiling
WW231-1210 | HVAC Support Hangers |  | 10 | 444 | 2 | 05-May-23 A | 04-Feb-25 | J: 51; J: HVAC Support Hangers
WW231-1360 | Drywall Bottom of Trusses |  | 5 | 419 | 2 | 12-Jun-23 A | 05-Feb-25 | J: 51; J: Drywall Bottom of Trusses
WW231-1440 | Tape & Finish Drywall |  | 8 | 324 | 4 | 25-Oct-23 A | 28-Mar-25 | J: 19; J: Tape & Finish Drywall
WW231-1430 | Poly & Drywall at LTGA Framing |  | 6 | 324 | 4 | 25-Oct-23 A | 12-Feb-25 | J: 51; J: Poly & Drywall at LTGA Framing
WW231-1216 | Sprinkler Support Hangers |  | 10 | 322 | 4 | 27-Oct-23 A | 06-Feb-25 | J: 51; J: Sprinkler Support Hangers
WW231-1390 | Batt & Blowing in Attic |  | 6 | 259 | 2 | 29-Jan-24 A | 05-Feb-25 | J: 56; M: Batt & Blowing in Attic
WW231-1420 | Install Windows |  | 15 | 229 | 2 | 11-Mar-24 A | 05-Feb-25 | J: 117; M: Install Windows
WW231-1472 | Electrical In Ceiling |  | 30 | 199 | 21 | 22-Apr-24 A | 28-Mar-25 | J: 49; J: Electrical In Ceiling
WW231-1450 | Phenolic Panels |  | 20 | 194 | 6 | 29-Apr-24 A | 21-Feb-25 | J: 109; M: Phenolic Panels
WW231-1370 | Phenolic Panel Clips |  | 6 | 121 | 2 | 12-Aug-24 A | 04-Feb-25 | J: 122; M: Phenolic Panel Clips
WW231-1410 | Mineral Wool Exterior |  | 6 | 87 | 2 | 12-Aug-24 A | 06-Feb-25 | J: 91; M: Mineral Wool Exterior
WW231-1400 | LTGA Framing & Soffits above Windows |  | 6 | 33 | 5 | 16-Dec-24 A | 12-Feb-25 | J: 51; A: LTGA Framing & Soffits above Windows
WW231-1490 | Exterior Soffits |  | 5 | 17 | 2 | 16-Dec-24 A | 28-Feb-25 | J: 87; M: Exterior Soffits
WW231-1460 | Drywall Inspections |  | 2 | 0 | 2 | 31-Mar-25 | 01-Apr-25 | J: 42; J: Drywall Inspections
WW231-1474 | Sprinkler In Ceiling |  | 30 | 0 | 30 | 31-Mar-25 | 09-May-25 | J: 19; A: Sprinkler In Ceiling
WW231-1480 | Prime / 1st Coat Paint |  | 5 | 0 | 5 | 02-Apr-25 | 08-Apr-25 | J: 42; A: Prime / 1st Coat Paint
WW231-1500 | Ceiling Grid |  | 7 | 0 | 7 | 12-May-25 | 20-May-25 | J: 19; J: Ceiling Grid
WW231-1218 | MEP Firestopping |  | 2 | 0 | 2 | 12-May-25 | 13-May-25 | J: 34; A: MEP Firestopping
WW231-1510 | Lights + Devices |  | 10 | 0 | 10 | 21-May-25 | 04-Jun-25 | J: 19; S: Lights + Devices
WW231-1512 | Diffusers |  | 10 | 0 | 10 | 21-May-25 | 04-Jun-25 | J: 19; A: Diffusers
WW231-1514 | Sprinkler Heads |  | 10 | 0 | 10 | 21-May-25 | 04-Jun-25 | J: 19; S: Sprinkler Heads
WW231-1516 | Fire Alarm Devices |  | 10 | 0 | 10 | 21-May-25 | 04-Jun-25 | J: 19; S: Fire Alarm Devices
WW231-1520 | Above Ceiling Inspections |  | 5 | 0 | 5 | 05-Jun-25 | 11-Jun-25 | J: 19; O: Above Ceiling Inspections
WW231-1530 | Drop Ceiling Tiles |  | 6 | 0 | 6 | 12-Jun-25 | 19-Jun-25 | J: 52; S: Drop Ceiling Tiles
WW231-1540 | Handrails |  | 6 | 0 | 6 | 20-Jun-25 | 27-Jun-25 | J: 52; A: Handrails
WW231-1550 | Flooring |  | 10 | 0 | 10 | 30-Jun-25 | 14-Jul-25 | J: 52; S: Flooring
| PHASE-1: WALKWAY PUNCHLIST / COMMISSIONING 1/2/3/ |  | 77 | 0 | 77 | 12-Jun-25 | 30-Sep-25 | J: 32
WW231-1590 | Submit Controls Testing Plan |  | 5 | 0 | 5 | 12-Jun-25 | 18-Jun-25 | J: 64; N: Submit Controls Testing Plan
WW231-1600 | Fire AlarmTest |  | 5 | 0 | 5 | 12-Jun-25 | 18-Jun-25 | J: 84; S: Fire AlarmTest
WW231-1560 | PHB Punchlist |  | 10 | 0 | 10 | 15-Jul-25 | 28-Jul-25 | J: 52; O: PHB Punchlist
WW231-1620 | Controls Test ing |  | 5 | 0 | 5 | 22-Jul-25 | 28-Jul-25 | J: 42; N: Controls Test ing
WW231-1630 | Air & Water Balancing |  | 10 | 0 | 10 | 29-Jul-25 | 11-Aug-25 | J: 47; D: Air & Water Balancing
WW231-1610 | Contractor Pre-Final Punchlist Corrections |  | 10 | 0 | 10 | 29-Jul-25 | 11-Aug-25 | J: 52; M: Contractor Pre-Final Punchlist Corrections
WW231-1640 | HVAC Commissioning |  | 15 | 0 | 15 | 12-Aug-25 | 02-Sep-25 | J: 32; J: HVAC Commissioning
WW231-1650 | Performance Verification Testing |  | 5 | 0 | 5 | 03-Sep-25 | 09-Sep-25 | J: 32; F: Performance Verification Testing
WW231-1660 | Government Pre-Final Inspections |  | 5 | 0 | 5 | 10-Sep-25 | 16-Sep-25 | J: 32; M: Government Pre-Final Inspections
WW231-1670 | Corrections of Punchlist from Government Pre-Final Inspection |  | 5 | 0 | 5 | 17-Sep-25 | 23-Sep-25 | J: 32; J: Corrections of Punchlist from Government Pre-Final Inspection
WW231-1680 | Final Inspections |  | 5 | 0 | 5 | 24-Sep-25 | 30-Sep-25 | J: 32; J: Final Inspections
| PHASE-1: WALKWAY#4 (BLDG-K to BLDG-C/D) |  | 507 | 511 | 169 | 01-Feb-23 A | 30-Sep-25 | J: 32
| PHASE-1: WALKWAY SITE WORK & STRUCTURE 4 |  | 291 | 307 | 2 | 17-Nov-23 A | 04-Feb-25 | J: 166
WW4-1190 | Shingle Roof |  | 4 | 218 | 1 | 17-Nov-23 A | 03-Feb-25 | J: 53; A: Shingle Roof
WW4-1340 | Air Barrier |  | 2 | 179 | 1 | 20-May-24 A | 03-Feb-25 | J: 167; A: Air Barrier
WW4-1330 | Poly Bottom of Trusses |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: 75; J: Poly Bottom of Trusses
PHASE-1: WALKWAY FINISHES 4 |  |  | 386 | 511 | 48 | 01-Feb-23 A | 09-Apr-25 | J: 121
WW4-1460 | HVAC In Ceiling |  | 20 | 511 | 10 | 01-Feb-23 A | 14-Feb-25 | J: 90; M: HVAC In Ceiling
WW4-1200 | HVAC Support Hangers |  | 4 | 436 | 1 | 17-May-23 A | 03-Feb-25 | J: 75; J: HVAC Support Hangers
WW4-1360 | Phenolic Panel Clips |  | 3 | 432 | 1 | 23-May-23 A | 03-Feb-25 | J: 167; M: Phenolic Panel Clips
Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 22 of 46 |  | J: TASK filter: Activity Status.
Actual Level of Effort | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  | Original | Actual | Remaining | Start | J: Finish; F: Total Float; J: 2025; A: 2026; A: 2027
|  |  |  | Duration | Duration | Duration | [30 empty] | M
[9 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
WW4-1350 | Drywall Bottom of Trusses |  |  | 2 | 419 | 1 | 12-Jun-23 A | 04-Feb-25 | J: 75; J: Drywall Bottom of Trusses
WW4-1420 | Poly & Drywall at LTGA Framing |  |  | 3 | 322 | 2 | 27-Oct-23 A | 07-Feb-25 | J: 75; J: Poly & Drywall at LTGA Framing
WW4-1430 | Tape & Finish Drywall |  |  | 8 | 322 | 1 | 27-Oct-23 A | 07-Feb-25 | J: 75; M: Tape & Finish Drywall
WW4-1202 | Electrical Support Hangers |  |  | 4 | 316 | 1 | 06-Nov-23 A | 03-Feb-25 | J: 75; J: Electrical Support Hangers
WW4-1462 | Electrical In Ceiling |  |  | 20 | 199 | 14 | 22-Apr-24 A | 20-Feb-25 | J: 86; M: Electrical In Ceiling
WW4-1480 | Exterior Soffits |  |  | 3 | 33 | 1 | 11-Nov-24 A | 04-Feb-25 | J: 128; A: Exterior Soffits
WW4-1380 | Batt & Blowing in Attic |  |  | 3 | 0 | 3 | 05-Feb-25 | 07-Feb-25 | J: 75; M: Batt & Blowing in Attic
WW4-1390 | LTGA Framing & Soffits above Windows |  |  | 3 | 0 | 3 | 05-Feb-25 | 07-Feb-25 | J: 75; A: LTGA Framing & Soffits above Windows
WW4-1450 | Drywall Inspections |  |  | 2 | 0 | 2 | 10-Feb-25 | 11-Feb-25 | J: 89; M: Drywall Inspections
WW4-1464 | Sprinkler In Ceiling |  |  | 20 | 0 | 20 | 10-Feb-25 | 07-Mar-25 | J: 75; J: Sprinkler In Ceiling
WW4-1470 | Prime / 1st Coat Paint |  |  | 4 | 0 | 4 | 12-Feb-25 | 17-Feb-25 | J: 89; J: Prime / 1st Coat Paint
WW4-1490 | Ceiling Grid |  |  | 3 | 0 | 3 | 10-Mar-25 | 12-Mar-25 | J: 75; M: Ceiling Grid
WW4-810 | MEP Firestopping |  |  | 2 | 0 | 2 | 10-Mar-25 | 11-Mar-25 | J: 81; J: MEP Firestopping
WW4-1502 | Diffusers |  |  | 5 | 0 | 5 | 13-Mar-25 | 19-Mar-25 | J: 75; M: Diffusers
WW4-1504 | Sprinkler Heads |  |  | 5 | 0 | 5 | 13-Mar-25 | 19-Mar-25 | J: 75; J: Sprinkler Heads
WW4-1506 | Fire Alarm Devices |  |  | 5 | 0 | 5 | 13-Mar-25 | 19-Mar-25 | J: 75; J: Fire Alarm Devices
WW4-1500 | Lights + Devices |  |  | 5 | 0 | 5 | 13-Mar-25 | 19-Mar-25 | J: 75; J: Lights + Devices
WW4-1510 | Above Ceiling Inspections |  |  | 3 | 0 | 3 | 20-Mar-25 | 24-Mar-25 | J: 75; J: Above Ceiling Inspections
WW4-1520 | Drop Ceiling Tiles |  |  | 3 | 0 | 3 | 25-Mar-25 | 27-Mar-25 | J: 121; J: Drop Ceiling Tiles
WW4-1530 | Handrails |  |  | 4 | 0 | 4 | 28-Mar-25 | 02-Apr-25 | J: 121; M: Handrails
WW4-1540 | Flooring |  |  | 5 | 0 | 5 | 03-Apr-25 | 09-Apr-25 | J: 121; J: Flooring
| PHASE-1: WALKWAY PUNCHLIST / COMMISSIONING 4 |  |  | 133 | 0 | 133 | 25-Mar-25 | 30-Sep-25 | J: 32
WW4-1580 | Submit Controls Testing Plan |  |  | 5 | 0 | 5 | 25-Mar-25 | 31-Mar-25 | J: 110; A: Submit Controls Testing Plan
WW4-1590 | Fire AlarmTest |  |  | 5 | 0 | 5 | 25-Mar-25 | 31-Mar-25 | J: 140; J: Fire AlarmTest
WW4-1550 | PHB Punchlist |  |  | 7 | 0 | 7 | 10-Apr-25 | 18-Apr-25 | J: 121; J: PHB Punchlist
WW4-1630 | Contractor Pre-Final Punchlist Corrections |  |  | 10 | 0 | 10 | 21-Apr-25 | 02-May-25 | J: 121; N: Contractor Pre-Final Punchlist Corrections
WW4-1600 | Controls Test ing |  |  | 5 | 0 | 5 | 22-Jul-25 | 28-Jul-25 | J: 32; O: Controls Test ing
WW4-1610 | Air & Water Balancing |  |  | 10 | 0 | 10 | 29-Jul-25 | 11-Aug-25 | J: 32; D: Air & Water Balancing
WW4-1620 | HVAC Commissioning |  |  | 15 | 0 | 15 | 12-Aug-25 | 02-Sep-25 | J: 32; D: HVAC Commissioning
WW4-1640 | Performance Verification Testing |  |  | 5 | 0 | 5 | 03-Sep-25 | 09-Sep-25 | J: 32; F: Performance Verification Testing
WW4-1650 | Government Pre-Final Inspections |  |  | 5 | 0 | 5 | 10-Sep-25 | 16-Sep-25 | J: 32; F: Government Pre-Final Inspections
WW4-1660 |  | Corrections of Punchlist from Government Pre-Final Inspection |  | 5 | 0 | 5 | 17-Sep-25 | 23-Sep-25 | J: 32; J: Corrections of Punchlist from Government Pre-Final Inspection
WW4-1670 | Final Inspections |  |  | 5 | 0 | 5 | 24-Sep-25 | 30-Sep-25 | J: 32; J: Final Inspections
| PHASE-1: SOUTH WEST_COURTYARD /LANDSCP/ HARDSCP |  |  | 633 | 797 | 54 | 16-Dec-21 A | 06-Oct-25 | J: 6
COM-4000 | Rough Grade |  |  | 4 | 581 | 1 | 16-Dec-21 A | 22-Jul-25 | J: 5; S: Rough Grade
COM-430 | Seat Walls |  |  | 4 | 18 | 3 | 11-Dec-24 A | 24-Jul-25 | J: 5; S: Seat Walls
COM-4030 | Lighting Install |  |  | 5 | 0 | 5 | 22-Jul-25 | 28-Jul-25 | J: 6; O: Lighting Install
COM-4040 | Concrete Walk s & Concret e Paving |  |  | 15 | 0 | 15 | 29-Jul-25 | 18-Aug-25 | J: 6; F: Concrete Walk s & Con crete Paving
COM-4050 | Ramps & Railings |  |  | 4 | 0 | 4 | 29-Jul-25 | 01-Aug-25 | J: 32; N: Ramps & Railings
COM-4060 | Stairs |  |  | 5 | 0 | 5 | 19-Aug-25 | 25-Aug-25 | J: 6; S: Stairs
COM-4070 | Pedestrian Pavers |  |  | 10 | 0 | 10 | 26-Aug-25 | 09-Sep-25 | J: 6; D: Pedestrian Pavers
COM-4080 | Seeding |  |  | 2 | 0 | 2 | 26-Aug-25 | 27-Aug-25 | J: 14; O: Seeding
COM-4090 | Final Grade |  |  | 5 | 0 | 5 | 10-Sep-25 | 16-Sep-25 | J: 6; N: Final Grade
COM-4100 | Plantings |  |  | 10 | 0 | 10 | 17-Sep-25 | 30-Sep-25 | J: 6; N: Plantings
COM-4110 | Horseshoe Pits |  |  | 1 | 0 | 1 | 17-Sep-25 | 17-Sep-25 | J: 19; D: Horseshoe Pits
COM-4130 | Weed Barrier |  |  | 3 | 0 | 3 | 01-Oct-25 | 03-Oct-25 | J: 7; D: Weed Barrier
COM-4120 | Mulch |  |  | 3 | 0 | 3 | 01-Oct-25 | 03-Oct-25 | J: 6; N: Mulch
COM-4140 | Grills |  |  | 1 | 0 | 1 | 06-Oct-25 | 06-Oct-25 | J: 6; N: Grills
| Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 23 of 46 |  | J: TASK filter: Activity Status.
| Actual Level of Effort | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  | Original | Actual | Remaining | Start | Finish | J: Total Float; J: 2025; J: 2026; M: 2027
|  |  |  | Duration | Duration | Duration | [30 empty] | M
[9 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
COM-4160 | COURTYARD-B COMPLETE |  |  | 0 | 0 | 0 |  | 06-Oct-25 | J: 6; F: COURTYARD-B COMPLETE
| PHASE-1:COMMUNITY CENTER OWNER MOVE-IN |  |  | 30 | 0 | 30 | 28-Oct-25 | 26-Nov-25 | J: -13
COM-MOVE | OWNER (Phase-1) Move-in Community Center |  |  | 30 | 0 | 30 | 28-Oct-25 | 26-Nov-25 | J: -13; J: OWNER (Phase-1) Move-in Community Center
| PHASE-1: COTTAGE-C&D |  |  | 670 | 587 | 173 | 13-Oct-22 A | 06-Oct-25 | J: 28
| PHASE-1: COTTAGE-C&D_BUILDING ENCLOSURE / WATER TIGHT |  |  | 425 | 434 | 22 | 19-May-23 A | 04-Mar-25 | J: 124
CD-262 | Install Accordian Doors |  |  | 10 | 434 | 3 | 19-May-23 A | 05-Feb-25 | J: 143; J: Install Accordian Doors
CD-295 | Inspect Door & Window Installation |  |  | 2 | 423 | 1 | 06-Jun-23 A | 04-Mar-25 | J: 122; A: Inspect Door & Window Installation
CD-260 | Install Doors |  |  | 10 | 0 | 10 | 19-Feb-25 | 04-Mar-25 | J: 122; M: Install Doors
| PHASE-1: COTTAGE-C&D_EXTERIOR BUILDING FINISHES |  |  | 5 | 0 | 5 | 04-Feb-25 | 10-Feb-25 | J: 148
CD-690 | Expansion Joint Installation |  |  | 5 | 0 | 5 | 04-Feb-25 | 10-Feb-25 | J: 148; J: Expansion Joint Installation
| PHASE-1: COTTAGE-C&D_HOUSEHOLD E: MEP/FP ROUGH-IN |  |  | 517 | 587 | 20 | 13-Oct-22 A | 28-Feb-25 | J: 119
CD-322 | HVAC Insulation |  |  | 20 | 587 | 1 | 13-Oct-22 A | 03-Feb-25 | J: 78; A: HVAC Insulation
CD-350 | Electrical Rough |  |  | 20 | 517 | 1 | 24-Jan-23 A | 03-Feb-25 | J: 69; A: Electrical Rough
CD-352 | OH Rough Electrical/ Security/ AV Systems |  |  | 20 | 397 | 1 | 13-Jul-23 A | 03-Feb-25 | J: 78; A: OH Rough Electrical/ Security/ AV Systems
CD-257 | Install Electrical Hangers on Steel @ Walk way |  |  | 5 | 392 | 4 | 20-Jul-23 A | 06-Feb-25 | J: 81; A: Install Electrical Hangers on Steel @ Wa lk way
CD-356 | Install Branch Circuit Wire |  |  | 10 | 373 | 1 | 16-Aug-23 A | 03-Feb-25 | J: 129; J: Install Branch Circuit Wire
CD-342 | MEP Firestopping |  |  | 2 | 357 | 1 | 08-Sep-23 A | 03-Feb-25 | J: 80; A: MEP Firestopping
CD-259 | Install Sprinkler Hangers on Steel @ Walkway |  |  | 5 | 306 | 1 | 20-Nov-23 A | 03-Feb-25 | J: 81; A: Install Sprinkler Hangers on Steel @ Walkway
CD-244 | Fire Suppression Attic Rough |  |  | 15 | 0 | 15 | 03-Feb-25 | 21-Feb-25 | J: 61; J: Fire Suppression Attic Rough
CD-325 | Inspect Attic Insulation |  |  | 3 | 0 | 3 | 03-Feb-25 | 05-Feb-25 | J: 136; M: Inspect Attic Insulation
CD-245 | Attic MEP Inspection |  |  | 5 | 0 | 5 | 24-Feb-25 | 28-Feb-25 | J: 61; J: Attic MEP Inspection
CD-370 | INSPECTION - MEPs |  |  | 0 | 0 | 0 |  | 28-Feb-25 | J: 61; J: INSPECTION - MEPs
| PHASE-1: COTTAGE-C&D_INTERIOR WALL & CEILING FRAMING |  |  | 20 | 271 | 1 | 11-Jan-24 A | 03-Feb-25 | J: 69
CD-360 | Prerock & Framing - Ceilings / Soffits |  |  | 20 | 271 | 1 | 11-Jan-24 A | 03-Feb-25 | J: 69; A: Prerock & Framing - Ceilings / Soffits
| PHASE-1: COTTAGE-C&D_DRYWALL / PRIME-PAINT / OVERHEAD FINISHES |  |  | 148 | 138 | 52 | 18-Jul-24 A | 15-Apr-25 | J: 143
CD-460 | ACT Ceiling Grid @ (CORR/COM) |  |  | 10 | 138 | 3 | 18-Jul-24 A | 28-Feb-25 | J: 61; A: ACT Ceiling Grid @ (CORR/COM)
CD-450 | Bathroom - Tile @ (UNITS) |  |  | 15 | 73 | 12 | 18-Oct-24 A | 18-Feb-25 | J: 69; J: Bathroom - Tile @ (UNITS)
CD-490 | Doors / Running Trim @ (CORR/COM) |  |  | 10 | 28 | 9 | 23-Dec-24 A | 07-Apr-25 | J: 44; O: Doors / Running Trim @ (CORR/COM)
CD-440 | Doors / Running Trim @ (UNITS) |  |  | 10 | 28 | 9 | 23-Dec-24 A | 25-Mar-25 | J: 41; A: Doors / Running Trim @ (UNITS)
CD-415 | Shower Wall Panels |  |  | 8 | 0 | 8 | 03-Feb-25 | 12-Feb-25 | J: 121; M: Shower Wall Panels
CD-4444 | Seal Concrete Floor @ CD |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: 185; J: Seal Concrete Floor @ CD
CD-510 | Ceramic Tile @ (CORR/COM) |  |  | 15 | 0 | 15 | 26-Mar-25 | 15-Apr-25 | J: 44; A: Ceramic Tile @ (CORR/COM)
CD-480 | Kitchenette - Vinyl Sheeting @ (UNITS) |  |  | 10 | 0 | 10 | 26-Mar-25 | 08-Apr-25 | J: 41; O: Kitchenette - Vinyl Sheeting @ (UNITS)
| PHASE-1: COTTAGE-C&D_MILLWORK |  |  | 25 | 51 | 20 | 19-Nov-24 A | 06-May-25 | J: 41
CD-560 | Millwork / Casework @ (CORR/COM) |  |  | 15 | 51 | 12 | 19-Nov-24 A | 06-May-25 | J: 41; N: Millwork / Casework @ (CORR/COM)
CD-520 | Millwork / Vanities / Cabinets @ (UNITS) |  |  | 10 | 51 | 8 | 19-Nov-24 A | 18-Apr-25 | J: 41; O: Millwork / Vanities / Cabinets @ (UNITS)
| PHASE-1: COTTAGE-C&D_FINAL FINISHES |  |  | 391 | 421 | 95 | 08-Jun-23 A | 16-Jun-25 | J: 106
| PHASE-1: COTTAGE-C&D_HOUSEHOLD E: FINISHES - UNITS |  |  | 385 | 421 | 77 | 08-Jun-23 A | 20-May-25 | J: 124
CD-630 | Plumbing Fixtures @ (UNITS) |  |  | 15 | 421 | 1 | 08-Jun-23 A | 19-Feb-25 | J: 103; J: Plumbing Fixtures @ (UNITS)
CD-644 | Light Fixtures @ (UNITS) |  |  | 15 | 366 | 1 | 25-Aug-23 A | 23-Apr-25 | J: 54; A: Light Fixtures @ (UNITS)
CD-654 | Sprinkler Devices @ (UNITS) |  |  | 15 | 264 | 1 | 22-Jan-24 A | 23-Apr-25 | J: 54; S: Sprinkler Devices @ (UNITS)
CD-642 | HVAC Diffusers/ Devices @ (UNITS) |  |  | 15 | 243 | 3 | 20-Feb-24 A | 25-Apr-25 | J: 54; O: HVAC Diffusers/ Devices @ (UNITS)
CD-652 | Data/ Security/ Nurse/ TV/ PA Devices @ (UNITS) |  |  | 15 | 209 | 1 | 08-Apr-24 A | 23-Apr-25 | J: 54; D: Data/ Security/ Nurse/ TV/ PA Devices @ (UNITS)
CD-646 | Electrical Devices @ (UNITS) |  |  | 15 | 191 | 1 | 02-May-24 A | 23-Apr-25 | J: 72; S: Electrical Devices @ (UNITS)
CD-540 | Final Paint @ (UNITS) |  |  | 10 | 76 | 3 | 15-Oct-24 A | 25-Apr-25 | J: 54; A: Final Paint @ (UNITS)
CD-580 | Set Countertops @ (UNITS) |  |  | 8 | 0 | 8 | 03-Feb-25 | 12-Feb-25 | J: 103; J: Set Countertops @ (UNITS)
CD-2103 | Set Kitchen Equipment |  |  | 6 | 0 | 6 | 17-Feb-25 | 24-Feb-25 | J: 185; J: Set Kitchen Equipment
CD-656 | Install Owner provided lifts |  |  | 5 | 0 | 5 | 28-Apr-25 | 02-May-25 | J: 136; A: Install Owner provided lifts
CD-600 | Bathroom - Accessories @ (UNITS) |  |  | 10 | 0 | 10 | 28-Apr-25 | 09-May-25 | J: 69; O: Bathroom - Accessories @ (UNITS)
| Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 24 of 46 |  | J: TASK filter: Activity Status.
| Actual Level of Effort | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  | Original | Actual | Remaining | Start | Finish | J: Total Float; M: 2025; J: 2026; A: 2027
|  |  |  | Duration | Duration | Duration | [30 empty] | M
[9 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
CD-2123 | Window Shades |  |  | 5 | 0 | 5 | 14-May-25 | 20-May-25 | J: 62; A: Window Shades
|  | PHASE-1: COTTAGE-C&D_HOUSEHOLD E: FINISHES - CORRIDORS / COMMONS (CORR/COM) |  | 329 | 421 | 38 | 08-Jun-23 A | 16-Jun-25 | J: 59
CD-660 | Plumbing Fixtures @ (CORR/COM) |  |  | 10 | 421 | 1 | 08-Jun-23 A | 12-May-25 | J: 45; O: Plumbing Fixtures @ (CORR/COM)
CD-664 | Light Fixtures @ (CORR/COM) |  |  | 10 | 366 | 1 | 25-Aug-23 A | 23-Apr-25 | J: 54; S: Light Fixtures @ (CORR/COM)
CD-668 | Fire Alarm Devices @ (CORR/COM) |  |  | 10 | 315 | 1 | 07-Nov-23 A | 12-May-25 | J: 41; O: Fire Alarm Devices @ (CORR/COM)
CD-662 | HVAC Diffusers/ Devices @ (CORR/COM) |  |  | 10 | 291 | 2 | 12-Dec-23 A | 13-May-25 | J: 41; N: HVAC Diffusers/ Devices @ (CORR/COM)
CD-674 | Sprinkler Devices @ (CORR/COM) |  |  | 10 | 244 | 1 | 19-Feb-24 A | 12-May-25 | J: 41; O: Sprinkler Devices @ (CORR/COM)
CD-672 |  | Data/ Security/ Nurse/ TV/ PA Devices @ (CORR/COM) |  | 10 | 204 | 1 | 15-Apr-24 A | 12-May-25 | J: 41; J: Data/ Security/ Nurse/ TV/ PA Devices @ (CORR/COM)
CD-666 | Electrical Devices @ (CORR/COM) |  |  | 10 | 191 | 1 | 02-May-24 A | 12-May-25 | J: 59; O: Electrical Devices @ (CORR/COM)
CD-610 | Final Paint @ (CORR/COM) |  |  | 8 | 76 | 2 | 15-Oct-24 A | 13-May-25 | J: 41; O: Final Paint @ (CORR/COM)
CD-670 | Drop ACT Ceiling Tile @ (CO RR/COM) |  |  | 5 | 67 | 4 | 28-Oct-24 A | 15-May-25 | J: 41; N: Drop ACT Ceiling Tile @ (CORR/COM)
CD-2250 | Wall Prot ec tion @ (CORR /COM) |  |  | 25 | 60 | 15 | 06-Nov-24 A | 16-Jun-25 | J: 59; N: Wall Prot ec tion @ (CORR /COM)
CD-620 | Wall Covering s @ (CORR/COM) |  |  | 10 | 0 | 10 | 12-May-25 | 23-May-25 | J: 59; O: Wall Coverings @ (CORR/COM)
CD-680 | Bathroom - Accessories @ (CORR/COM) |  |  | 10 | 0 | 10 | 13-May-25 | 27-May-25 | J: 58; D: Bathroom - Accessories @ (CORR/COM)
CD-740 | Inst Signage @ CD |  |  | 5 | 0 | 5 | 14-May-25 | 20-May-25 | J: 77; A: Inst Signage @ CD
CD-712 | Install Specialty Doors |  |  | 2 | 0 | 2 | 14-May-25 | 15-May-25 | J: 56; S: Install Specialty Doors
CD-700 | Carpet @ (CORR/COM) |  |  | 9 | 0 | 9 | 16-May-25 | 29-May-25 | J: 56; O: Carpet @ (CORR/COM)
| PHASE-1: NORTHEAST_COURTYARD /LANDSCP/ HARDSCP |  |  | 154 | 135 | 31 | 23-Jul-24 A | 17-Mar-25 | J: 123
CD-500 | Concrete Walk s & Concret e Paving |  |  | 15 | 135 | 1 | 23-Jul-24 A | 03-Feb-25 | J: 128; J: Concrete Walk s & Concrete Paving
CD-820 | Phenolic Panels |  |  | 2 | 134 | 1 | 24-Jul-24 A | 03-Feb-25 | J: 127; A: Phenolic Panels
CD-570 | Final Grade |  |  | 5 | 0 | 5 | 04-Feb-25 | 10-Feb-25 | J: 127; A: Final Grade
CD-830 | Expansion Joints |  |  | 5 | 0 | 5 | 04-Feb-25 | 10-Feb-25 | J: 148; M: Expansion Joints
CD-790 | Seeding |  |  | 1 | 0 | 1 | 11-Feb-25 | 11-Feb-25 | J: 147; M: Seeding
CD-590 | Plantings |  |  | 10 | 0 | 10 | 17-Feb-25 | 28-Feb-25 | J: 123; A: Plantings
CD-4100 | Weed barrier |  |  | 8 | 0 | 8 | 03-Mar-25 | 12-Mar-25 | J: 123; M: Weed barrier
CD-800 | Grills |  |  | 1 | 0 | 1 | 03-Mar-25 | 03-Mar-25 | J: 133; A: Grills
CD-780 | Mulch |  |  | 3 | 0 | 3 | 13-Mar-25 | 17-Mar-25 | J: 123; A: Mulch
CD-640 | COURTYARD-B COMPLETE |  |  | 0 | 0 | 0 |  | 17-Mar-25 | J: 123; A: COURTYARD-B COMPLETE
| PHASE-1: COTTAGE-C&D_FINAL CLEAN / PUNCH / TURNOVER |  |  | 103 | 0 | 103 | 12-May-25 | 06-Oct-25 | J: 28
CD-715 | Submit Conrols Testing Plan |  |  | 5 | 0 | 5 | 12-May-25 | 16-May-25 | J: 41; O: Submit Conrols Testing Plan
CD-735 | Sprinkler Systems Test |  |  | 5 | 0 | 5 | 23-May-25 | 30-May-25 | J: 77; S: Sprinkler Systems Test
CD-745 | Fire AlarmTest |  |  | 5 | 0 | 5 | 13-Jun-25 | 19-Jun-25 | J: 63; S: Fire AlarmTest
CD-722 | Main Feeders Ready to Test - CD |  |  | 0 | 0 | 0 |  | 07-Jul-25 | J: 7; D: Main Feeders Ready to Test - CD
CD-695 | Air & Water Balancing |  |  | 5 | 0 | 5 | 08-Jul-25 | 14-Jul-25 | J: 33; O: Air & Water Balancing
CD-725 | Controls Test ing |  |  | 5 | 0 | 5 | 08-Jul-25 | 14-Jul-25 | J: 7; O: Controls Test ing
CD-705 | HVAC Commissioning |  |  | 15 | 0 | 15 | 15-Jul-25 | 04-Aug-25 | J: 7; N: HVAC Commissioning
CD-4494 | Rough Clean @ CD |  |  | 5 | 0 | 5 | 15-Jul-25 | 21-Jul-25 | J: 17; O: Rough Clean @ CD
CD-772 | Red Zone Meeting |  |  | 60 | 0 | 60 | 01-Aug-25 | 30-Sep-25 | J: 45; J: Red Zone Meeting
CD-775 | Performance Verification Testing |  |  | 3 | 0 | 3 | 05-Aug-25 | 07-Aug-25 | J: 32; J: Performance Verification Testing
CD-4454 | Government Furniture Installation @ CD |  |  | 5 | 0 | 5 | 05-Aug-25 | 09-Aug-25 | J: 9; F: Government Furniture Installation @ CD
CD-4464 |  | Pre-Final Data Room Inspection & Punchlist Generation |  | 2 | 0 | 2 | 05-Aug-25 | 06-Aug-25 | J: 18; M: Pre-Final Data Room Inspection & Punchlist Generation
CD-4474 | Data Room Punchlist Corrections |  |  | 5 | 0 | 5 | 07-Aug-25 | 13-Aug-25 | J: 18; J: Data Room Punchlist Corrections
CD-710 | Final Clean |  |  | 5 | 0 | 5 | 11-Aug-25 | 15-Aug-25 | J: 6; O: Final Clean
CD-4484 | IT Room(s) Ready for VA Move In |  |  | 0 | 0 | 0 |  | 13-Aug-25 | J: 27; J: IT Room(s) Ready for VA Move In
CD-720 | Contractor Pre-Final Inspections |  |  | 10 | 0 | 10 | 18-Aug-25 | 29-Aug-25 | J: 6; J: Contractor Pre-Final Inspections
CD-730 | SUBSTANTIAL COMPLETION |  |  | 0 | 0 | 0 |  | 29-Aug-25 | J: 6; J: SUBSTANTIAL COMPLETION
CD-755 | Contractor Pre-Final Punchlist Corrections |  |  | 10 | 0 | 10 | 02-Sep-25 | 15-Sep-25 | J: 6; A: Contractor Pre-Final Punchlist Corrections
CD-760 | Government Pre-Final Inspections |  |  | 5 | 0 | 5 | 16-Sep-25 | 22-Sep-25 | J: 6; M: Government Pre-Final Inspections
CD-765 |  | Corrections of Punchlist from Government Pre-Final Inspection |  | 5 | 0 | 5 | 23-Sep-25 | 29-Sep-25 | J: 6; J: Corrections of Punchlist from Government Pre-Final Inspection
| Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 25 of 46 |  | J: TASK filter: Activity Status.
| Actual Level of Effort | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  |  | Original | Actual | Remaining | Start | J: Finish; F: Total Float; J: 2025; A: 2026; A: 2027
[5 empty] | Duration | Duration | Duration | [30 empty] | M
[10 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
CD-770 | Final Inspections |  |  |  | 5 | 0 | 5 | 30-Sep-25 | 06-Oct-25 | J: 6; D: Final Inspections
CD-750 | READY FOR OCCUPANCY |  |  |  | 0 | 0 | 0 |  | 06-Oct-25 | J: 6; F: READY FOR OCCUPANCY
PHASE-1: COTTAGE MOVE IN |  |  |  |  | 30 | 0 | 30 | 14-Oct-25 | 12-Nov-25 | bar: J
COTT-MOVE | OWNER MOVE TO COTTAGES |  |  |  | 30 | 0 | 30 | 14-Oct-25 | 12-Nov-25 | J: 1; A: OWNER MOVE TO COTTAGES
PHASE-2: BUILDING-9 |  |  |  |  | 626 | 454 | 309 | 21-Apr-23 A | 18-Apr-26 | J: -108
BUILDING 9 |  |  |  |  | 626 | 454 | 309 | 21-Apr-23 A | 18-Apr-26 | J: -108
BLDG 9 GROUND FLOOR |  |  |  |  | 409 | 229 | 205 | 11-Mar-24 A | 19-Nov-25 | bar: J
| GENERAL FLOOR ABAT EMENT / DEMO |  |  |  | 18 | 177 | 1 | 22-May-24 A | 13-Feb-25 | J: -88
B9LG-320 | Replace Windows GND Fl |  |  |  | 18 | 177 | 1 | 22-May-24 A | 13-Feb-25 | J: -88; J: Replace Windows GND Fl
| FOOTINGS/STRUCTURE GND TO 1ST |  |  |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: 199
SERVICE ELEVATOR |  |  |  |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: 199
B9LG-710 | Waterproof Membr ane & Bac kfill |  |  |  | 2 | 0 | 2 | 03-Feb-25 | 04-Feb-25 | J: 199; J: Waterproof Membr ane & Bac kfill
B9LG-730 | Inst Pit Ladder and Sump Cover |  |  |  | 1 | 0 | 1 | 03-Feb-25 | 03-Feb-25 | J: 77; J: Inst Pit Ladder and Sump Cover
ROUGH IN LVL G |  |  |  |  | 294 | 229 | 90 | 11-Mar-24 A | 09-Jun-25 | J: -21
B9LG-240 | Layout/Top Track | Lvl G |  |  | 8 | 229 | 5 | 11-Mar-24 A | 07-Feb-25 | J: -133; M: Layout/Top Track; A: Lvl G
B9LG-330 |  | Metal Framing @ Corridors + Top 4'0 DW | Lv l G |  | 10 | 187 | 7 | 08-May-24 A | 25-Feb-25 | J: -145; S: Metal Framing @ Corridors + Top 4'0 DW; A: Lv l G
B9LG-410 | Metal Framing @ Rooms |  | Lvl G |  | 10 | 178 | 7 | 21-May-24 A | 11-Apr-25 | J: -143; A: Metal Framing @ Rooms; J: Lvl G
B9LG-270 | Fireproofing | Lvl G |  |  | 5 | 155 | 5 | 24-Jun-24 A | 14-Feb-25 | J: -164; A: Fireproofing; A: Lvl G
B9LG-370 | Plumbing OH Rough In |  | Lvl G |  | 20 | 155 | 18 | 24-Jun-24 A | 21-Mar-25 | J: -117; J: Plumbing OH Rough In; D: Lvl G
B9LG-340 | Ductwork OH Rough In |  | Lvl G |  | 25 | 0 | 25 | 26-Feb-25 | 01-Apr-25 | J: -145; A: Ductwork OH Rough In; D: Lvl G
B9LG-380 | Controls OH Rough In |  | Lvl G |  | 20 | 0 | 20 | 26-Feb-25 | 25-Mar-25 | J: -113; J: Controls OH Rough In; D: Lvl G
B9LG-350 | Mechanical Equipment |  | Lvl G |  | 25 | 0 | 25 | 12-Mar-25 | 15-Apr-25 | J: -131; A: Mechanical Equipment; D: Lvl G
B9LG-360 | HVAC Pipe OH Rough In |  | Lvl G |  | 25 | 0 | 25 | 12-Mar-25 | 15-Apr-25 | J: -145; A: HVAC Pipe OH Rough In; J: Lvl G
B9LG-390 | Electrical OH Rough In |  | Lvl G |  | 15 | 0 | 15 | 19-Mar-25 | 08-Apr-25 | J: -145; A: Electrical OH Rough In; D: Lvl G
B9LG-400 | Fire Protection OH Rough In |  | Lvl G |  | 10 | 0 | 10 | 19-Mar-25 | 01-Apr-25 | J: -118; A: Fire Protection OH Rough In; F: Lvl G
B9LG-420 | OH FP Test/Inspections - |  | Lvl G |  | 5 | 0 | 5 | 02-Apr-25 | 08-Apr-25 | J: -113; A: OH FP Test/Inspections -; J: Lvl G
B9LG-440 |  | In Wall Mechanical / Contr ols Rou gh In | Lv l G |  | 10 | 0 | 10 | 03-Apr-25 | 16-Apr-25 | J: -4; O: In Wall Mechanical / Contr ols Rough In; M: Lv l G
B9LG-450 | In Wall Plumbing Rough In |  | Lv l G |  | 10 | 0 | 10 | 03-Apr-25 | 16-Apr-25 | J: -130; A: In Wall Plumbing Rough In; J: Lv l G
B9LG-460 | In Wall Electrical Rough In |  | Lv l G |  | 10 | 0 | 10 | 03-Apr-25 | 16-Apr-25 | J: -133; A: In Wall Electrical Rough In; J: Lv l G
B9LG-344 | Power In Wall Branc h |  | Lv l G |  | 10 | 0 | 10 | 03-Apr-25 | 16-Apr-25 | J: -143; A: Power In Wall Branc h; D: Lv l G
B9LG-282 | Electrical Power Conduits Lvl G |  |  |  | 10 | 0 | 10 | 09-Apr-25 | 22-Apr-25 | J: -145; S: Electrical Power Conduits Lvl G
B9LG-292 | Cable Tray Lvl G |  |  |  | 10 | 0 | 10 | 09-Apr-25 | 22-Apr-25 | J: -116; A: Cable Tray Lvl G
B9LG-342 | Distribution Panels Install |  | Lvl G |  | 10 | 0 | 10 | 09-Apr-25 | 22-Apr-25 | J: -137; A: Distribution Panels Install; J: Lvl G
B9LG-346 | Lighting In Wall Branch |  | L vl G |  | 10 | 0 | 10 | 10-Apr-25 | 23-Apr-25 | J: -143; A: Lighting In Wall Bran ch; D: L vl G
B9LG-520 | Frame Soffits & Ceilings |  | Lvl G |  | 10 | 0 | 10 | 16-Apr-25 | 29-Apr-25 | J: -128; A: Frame Soffits & Ceilings; J: Lvl G
B9LG-510 | OH Mechanical Test/Inspections |  | Lvl G |  | 3 | 0 | 3 | 16-Apr-25 | 18-Apr-25 | J: -131; S: OH Mechanical Test/Inspections; A: Lvl G
B9LG-570 | Pull Control Wire to Devices- |  | Lvl G |  | 10 | 0 | 10 | 17-Apr-25 | 30-Apr-25 | J: -4; S: Pull Control Wire to Devices-; M: Lvl G
B9LG-348 | Fire Alarm In Wall Conduits |  | Lvl G |  | 10 | 0 | 10 | 17-Apr-25 | 30-Apr-25 | J: -143; S: Fire Alarm In Wall Conduits; F: Lvl G
B9LG-352 | Security In Wall Conduits |  | Lvl G |  | 10 | 0 | 10 | 17-Apr-25 | 30-Apr-25 | J: -143; A: Security In Wall Conduits; J: L vl G
B9LG-354 | Data In Wall C ondu its |  | Lv l G |  | 10 | 0 | 10 | 17-Apr-25 | 30-Apr-25 | J: -143; A: Data In Wall C onduits; D: Lv l G
B9LG-610 |  | Insulate OH Mechanical Piping w/Duct | Lvl G |  | 10 | 0 | 10 | 21-Apr-25 | 02-May-25 | J: -131; N: Insulate OH Mechanical Piping w/Duct; J: Lvl G
B9LG-284 | Lighting Conduits | Lvl G |  |  | 10 | 0 | 10 | 23-Apr-25 | 06-May-25 | J: -145; A: Lighting Conduits; D: Lvl G
B9LG-680 | Terminate Controls - |  | Lvl G |  | 10 | 0 | 10 | 01-May-25 | 14-May-25 | J: -4; A: Terminate Controls -; J: Lvl G
B9LG-600 | Inspect In-Wall Electric al |  | Lvl G |  | 1 | 0 | 1 | 01-May-25 | 01-May-25 | J: -143; A: Inspect In-Wa ll Elect ric al; J: Lvl G
B9LG-452 | Pull & Terminate Br anch W ire |  | Lvl G |  | 10 | 0 | 10 | 02-May-25 | 15-May-25 | J: -142; O: Pull & Terminate Br anch W ire; M: Lvl G
B9LG-286 | Fire Alarm Conduits Lvl G |  |  |  | 10 | 0 | 10 | 07-May-25 | 20-May-25 | J: -126; S: Fire Alarm Conduits Lvl G
B9LG-288 |  | Security Conduits/ J-Hooks/ Sleeves | Lvl G |  | 10 | 0 | 10 | 07-May-25 | 20-May-25 | J: -126; N: Security Conduits/ J-Hooks/ Sleeves; J: Lvl G
B9LG-454 | Pull & Terminate Br anch Lighting |  | Lvl G |  | 10 | 0 | 10 | 07-May-25 | 20-May-25 | J: -145; O: Pull & Terminate Br anch L ighting; A: Lvl G
B9LG-530 |  | Seal Penetrations Thru Fire Wall /Floors | Lvl G |  | 4 | 0 | 4 | 19-May-25 | 22-May-25 | J: -145; D: Seal Penetrations Thru Fire Wall /Floors; J: Lvl G
Remaining Level of Effort |  |  | Actual Work | Critical Remaining Work |  |  |  | Page 26 of 46 |  | J: TASK filter: Activity Status.
Actual Level of Effort |  |  | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  |  | Original | Actual | Remaining | Start | Finish | J: Total Float; J: 2025; J: 2026; M: 2027
[5 empty] | Duration | Duration | Duration | [30 empty] | M
[10 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
B9LG-590 |  | OH Electrical Inspections - | Lvl G |  | 2 | 0 | 2 | 21-May-25 | 22-May-25 | J: -145; S: OH Electrical Inspections -; M: Lvl G
B9LG-456 | Pull Fire Alarm | Lvl G |  |  | 10 | 0 | 10 | 21-May-25 | 04-Jun-25 | J: -126; A: Pull Fire Alarm; D: Lvl G
B9LG-458 | Pull Data & Security | Lvl G |  |  | 10 | 0 | 10 | 21-May-25 | 04-Jun-25 | J: -126; S: Pull Data & Security; J: Lvl G
B9LG-620 |  | Pull & Terminate Electrical Wires- | Lvl G |  | 10 | 0 | 10 | 23-May-25 | 06-Jun-25 | J: -59; N: Pull & Terminate Electrical Wires-; J: Lvl G
B9LG-580 |  | Plumbing Testing & Insp ection | Lvl G |  | 3 | 0 | 3 | 23-May-25 | 28-May-25 | J: -156; O: Plumbing Testing & Inspection; A: Lvl G
B9LG-630 |  | Insulate Plumbing Piping | Lvl G |  | 8 | 0 | 8 | 29-May-25 | 09-Jun-25 | J: -156; O: Insulate Plumbing Piping; M: Lvl G
B9LG-690 |  | OH Inspection - Lvl G |  |  | 0 | 0 | 0 |  | 09-Jun-25 | J: -156; O: OH Inspection - Lvl G
FINISH LVL G |  |  |  |  | 141 | 0 | 141 | 02-May-25 | 19-Nov-25 | J: -125
B9LG-540 | Gypsum Board Walls | Lvl G |  |  | 20 | 0 | 20 | 02-May-25 | 30-May-25 | J: -143; S: Gypsum Board Walls; F: Lvl G
B9LG-670 | Tape and Finish Walls | Lvl G |  |  | 25 | 0 | 25 | 09-May-25 | 13-Jun-25 | J: -143; S: Tape and Finish Walls; M: Lvl G
B9LG-564 | Terminate Security | Lvl G |  |  | 10 | 0 | 10 | 05-Jun-25 | 18-Jun-25 | J: -56; S: Terminate Security; F: Lvl G
B9LG-566 | Terminate Fire Alarm | Lvl G |  |  | 10 | 0 | 10 | 05-Jun-25 | 18-Jun-25 | J: -56; S: Terminate Fire Alarm; F: Lvl G
B9LG-562 |  | Install & Ter minate WAP | Lvl G |  | 10 | 0 | 10 | 09-Jun-25 | 20-Jun-25 | J: -48; O: Install & Ter minate WAP; M: Lvl G
B9LG-700 |  | Gypsum Board Soffits & Ceilings | Lvl G |  | 15 | 0 | 15 | 10-Jun-25 | 30-Jun-25 | J: -156; D: Gypsum Board Soffits & Ceilings; J: Lvl G
B9LG-740 |  | Tape and Finish Soffit s & C eilings | Lvl G |  | 12 | 0 | 12 | 17-Jun-25 | 02-Jul-25 | J: -156; D: Tape and Finish Soffit s & C eilings; J: Lvl G
B9LG-780 | Prime Paint & 1st Coat | Lvl G |  |  | 10 | 0 | 10 | 03-Jul-25 | 17-Jul-25 | J: -156; N: Prime Paint & 1st Coat; A: Lvl G
B9LG-800 | ACT Ceiling Grid | Lvl G |  |  | 8 | 0 | 8 | 18-Jul-25 | 29-Jul-25 | J: -156; O: ACT Ceiling Grid; M: Lvl G
B9LG-782 | Install Specialty Doors | Lvl G |  |  | 10 | 0 | 10 | 18-Jul-25 | 31-Jul-25 | J: -62; N: Install Specialty Doors; A: Lvl G
B9LG-784 | Install Security Doors | Lvl G |  |  | 10 | 0 | 10 | 18-Jul-25 | 31-Jul-25 | J: -62; N: Install Security Doors; A: Lvl G
B9LG-830 |  | Mech OH Ceiling Finishes | Lvl G |  | 12 | 0 | 12 | 23-Jul-25 | 07-Aug-25 | J: -156; D: Mech OH Ceiling Finishes; J: Lvl G
B9LG-840 |  | Electrical Ceiling Finishes | Lvl G |  | 12 | 0 | 12 | 23-Jul-25 | 07-Aug-25 | J: -156; D: Electrical Ceiling Finishes; M: Lvl G
B9LG-850 |  | Fire Protection Ceiling Finishes | Lvl G |  | 5 | 0 | 5 | 23-Jul-25 | 29-Jul-25 | J: -149; J: Fire Protection Ceiling Finishes; J: Lvl G
B9LG-880 | Ceramic Tile | Lvl G |  |  | 10 | 0 | 10 | 08-Aug-25 | 21-Aug-25 | J: -134; O: Ceramic Tile; F: Lvl G
B9LG-890 |  | Mill Work & Countertops Lvl G |  |  | 20 | 0 | 20 | 08-Sep-25 | 03-Oct-25 | J: -144; M: Mill Work & Countertops Lvl G
B9LG-900 | Doors and Hardware | Lvl G |  |  | 10 | 0 | 10 | 08-Sep-25 | 19-Sep-25 | J: -97; J: Doors and Hardware; J: Lvl G
B9LG-910 | Final Paint | Lvl G |  |  | 10 | 0 | 10 | 22-Sep-25 | 03-Oct-25 | J: -144; D: Final Paint; M: Lvl G
B9LG-940 |  | Wall and Co rner Protection | Lvl G |  | 5 | 0 | 5 | 06-Oct-25 | 10-Oct-25 | J: -112; M: Wall a nd Corner Protection; A: Lvl G
B9LG-920 |  | Plumbing Finishes Lvl G |  |  | 5 | 0 | 5 | 06-Oct-25 | 10-Oct-25 | J: -126; M: Plumbing Finishes Lvl G
B9LG-950 | Signage | Lvl G |  |  | 5 | 0 | 5 | 06-Oct-25 | 10-Oct-25 | J: -112; D: Signage; M: Lvl G
B9LG-930 |  | Electrical Wall F inis hes | Lv l G |  | 10 | 0 | 10 | 06-Oct-25 | 17-Oct-25 | J: -131; F: Electrical Wall F inis hes; J: Lv l G
B9LG-652 | Fire Alarm Devices | Lvl G |  |  | 10 | 0 | 10 | 06-Oct-25 | 17-Oct-25 | J: -131; F: Fire Alarm Devices; J: Lvl G
B9LG-654 | Security Devices | Lvl G |  |  | 10 | 0 | 10 | 06-Oct-25 | 17-Oct-25 | J: -131; J: Security Devices; M: Lvl G
B9LG-656 | Data Devices | Lvl G |  |  | 10 | 0 | 10 | 06-Oct-25 | 17-Oct-25 | J: -102; J: Data Devices; A: Lvl G
B9LG-1000 | Ceiling Tiles | Lvl G |  |  | 8 | 0 | 8 | 20-Oct-25 | 29-Oct-25 | J: -131; J: Ceiling Tiles; A: Lvl G
B9LG-1050 | Carpet/VCT | Lvl G |  |  | 15 | 0 | 15 | 30-Oct-25 | 19-Nov-25 | J: -125; F: Carpet/VCT; M: Lvl G
KITCHEN FINISHES |  |  |  |  | 60 | 0 | 60 | 08-Aug-25 | 31-Oct-25 | J: -133
B9LG-870 |  | Terrazzo / Resinous Flooring | Lvl G |  | 20 | 0 | 20 | 08-Aug-25 | 05-Sep-25 | J: -156; F: Terrazzo / Resinous Flooring; J: Lvl G
B9LG-2073 |  | Set Kitchen Equipment 9 Lvl G |  |  | 20 | 0 | 20 | 08-Sep-25 | 03-Oct-25 | J: -156; M: Set Kitchen Equipment 9 Lvl G
B9LG-2093 |  | Plumbing Connections Lvl G |  |  | 20 | 0 | 20 | 22-Sep-25 | 17-Oct-25 | J: -123; M: Plumbing Connections Lvl G
B9LG-2103 |  | Electrical Connections Lvl G |  |  | 20 | 0 | 20 | 22-Sep-25 | 17-Oct-25 | J: -146; M: Electrical Connections Lvl G
B9LG-2113 |  | HVAC Hook-Ups /Connections Lvl G |  |  | 20 | 0 | 20 | 06-Oct-25 | 31-Oct-25 | J: -156; M: HVAC Hook-Ups /Connections Lvl G
TOILET / LOCKER RM FINISHES |  |  |  |  | 26 | 0 | 26 | 06-Oct-25 | 10-Nov-25 | J: -139
B9LG-1430 | Toiltet Accessories |  |  |  | 4 | 0 | 4 | 06-Oct-25 | 09-Oct-25 | J: -117; J: Toiltet Accessories
B9LG-2063 | LOCKERS 9 Lvl G |  |  |  | 5 | 0 | 5 | 04-Nov-25 | 10-Nov-25 | J: -139; F: LOCKERS 9 Lvl G
FINISHES COMMON SPACES LVL G |  |  |  |  | 21 | 0 | 21 | 06-Oct-25 | 03-Nov-25 | J: -113
B9LG-960 |  |  | Finish Coat Paint Corridor/Lobby/ Waiting - LVG Common |  | 3 | 0 | 3 | 06-Oct-25 | 08-Oct-25 | J: -144; J: Finish Coat Paint Corridor/Lobby/ Waiting - LVG Common
B9LG-2083 | Misc Medical Install |  |  |  | 5 | 0 | 5 | 09-Oct-25 | 15-Oct-25 | J: -121; F: Misc Medical Install
B9LG-970 |  |  | Ceiling Tile Install Corridor/Lobby/ Waiting - LVG Common |  | 4 | 0 | 4 | 09-Oct-25 | 14-Oct-25 | J: -135; J: Ceiling Tile Install Corridor/Lobby/ Waiting - LVG Common
B9LG-752 |  |  | Fire Alarm Devices -Corridor/Lobby/ Waiting -LVG Common |  | 5 | 0 | 5 | 09-Oct-25 | 15-Oct-25 | J: -144; J: Fire Alarm Devices -Corridor/Lobby/ Waiting -LVG Common
Remaining Level of Effort |  |  | Actual Work | Critical Remaining Work |  |  |  | Page 27 of 46 |  | J: TASK filter: Activity Status.
Actual Level of Effort |  |  | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  |  | Original | Actual | Remaining | Start | Finish | J: Total Float; J: 2025; J: 2026; M: 2027
[5 empty] | Duration | Duration | Duration
[10 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | AM
B9LG-754 |  |  | Security Devices -Corridor/Lobby/ Waiting - LVG Common |  | 5 | 0 | 5 | 09-Oct-25 | 15-Oct-25 | J: -144; J: Security Devices -Corridor/Lobby/ Waiting - LVG Common
B9LG-756 |  |  | Data Devices -Corridor/Lobby/ Waiting -LVG Common |  | 5 | 0 | 5 | 09-Oct-25 | 15-Oct-25 | J: -144; J: Data Devices -Corridor/Lobby/ Waiting -LVG Common
B9LG-980 |  |  | Electrical Wall D ev ic es Corridor/Lobby/ Waiting - LVG Common |  | 3 | 0 | 3 | 10-Oct-25 | 14-Oct-25 | J: -143; J: Electrical Wall Dev ic es Corridor/Lo bby/ Waiting - LVG Common
B9LG-990 |  | Control Finishes Installation Lvl 2 Common |  |  | 3 | 0 | 3 | 13-Oct-25 | 15-Oct-25 | J: -139; A: Control Finishes Installation Lvl 2 Common
B9LG-1020 |  |  | Wall Mount Accessories Corridor/Lobby/ Waiting - Lvl 2 Common |  | 5 | 0 | 5 | 17-Oct-25 | 23-Oct-25 | J: -106; A: Wall Mount Accessories Corridor/Lobby/ Waiting - Lvl 2 Common
B9LG-1030 |  | Signage Corridor/Lobby/ Waiting - Lv l 2 Common |  |  | 3 | 0 | 3 | 17-Oct-25 | 21-Oct-25 | J: -104; M: Signage Corridor/Lobby/ Waiting - Lv l 2 Common
B9LG-1040 |  |  | Flooring Finishes Corridor/Lobby/ Waiting -Lvl 2 Common |  | 10 | 0 | 10 | 21-Oct-25 | 03-Nov-25 | J: -139; J: Flooring Finishes Corridor/Lobby/ Waiting -Lvl 2 Common
BLDG 9 1ST FLOOR |  |  |  |  | 417 | 225 | 213 | 15-Mar-24 A | 02-Dec-25 | J: -133
GENERAL FLOOR ABAT EMENT / DEMO |  |  |  |  | 78 | 225 | 5 | 15-Mar-24 A | 07-Feb-25 | J: -81
B9L1-120 |  | Sawcut Floor & Rmv Fl @ 1st Floor |  |  | 6 | 225 | 4 | 15-Mar-24 A | 06-Feb-25 | J: -170; J: Sawcut Floor & Rmv Fl @ 1st Floor
B9L1-880 | Replace Windows 1st Fl |  |  |  | 18 | 163 | 5 | 12-Jun-24 A | 07-Feb-25 | J: -81; J: Replace Windows 1st Fl
STRUCTURE 1ST TO 2ND |  |  |  |  | 10 | 0 | 10 | 07-Feb-25 | 20-Feb-25 | J: -170
B9L1-910 |  |  | Inst Steel Stair Structure & Deck Gnd to 1st @ Str A & B |  | 10 | 0 | 10 | 07-Feb-25 | 20-Feb-25 | J: -170; N: Inst Steel Stair Structure & Deck Gnd to 1st @ Str A & B
ROUGH IN LVL 1 |  |  |  |  | 178 | 155 | 90 | 24-Jun-24 A | 09-Jun-25 | J: -33
B9L1-230 | Ductwork OH Rough In |  | 1-1 |  | 20 | 155 | 19 | 24-Jun-24 A | 08-Apr-25 | J: -158; A: Ductwork OH Rough In; D: 1-1
B9L1-2103 |  | Metal Framing @ Exterior Walls 1-1 |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: -86; J: Metal Framing @ Exterior Walls 1-1
B9L1-180 | Inst Hanger Duct | Lvl 1 |  |  | 4 | 0 | 4 | 17-Feb-25 | 20-Feb-25 | J: -169; M: Inst Hanger Duct; S: Lvl 1
B9L1-200 | Inst Hanger Plumbing |  | Lvl 1 |  | 4 | 0 | 4 | 17-Feb-25 | 20-Feb-25 | J: -169; J: Inst Hanger Plumbing; O: Lvl 1
B9L1-190 |  | Inst Hanger HVAC Piping Lvl 1 |  |  | 4 | 0 | 4 | 17-Feb-25 | 20-Feb-25 | J: -169; J: Inst Hanger HVAC Piping Lvl 1
B9L1-210 | Inst Hanger Electrical |  | 1-1 |  | 4 | 0 | 4 | 17-Feb-25 | 20-Feb-25 | J: -169; J: Inst Hanger Electrical; O: 1-1
B9L1-160 | Layout/Top Track | Lvl 1 |  |  | 8 | 0 | 8 | 03-Mar-25 | 12-Mar-25 | J: -158; J: Layout/Top Track; O: Lvl 1
B9L1-170 | Fireproofing | Lvl 1 |  |  | 5 | 0 | 5 | 04-Mar-25 | 10-Mar-25 | J: -168; M: Fireproofing; A: Lvl 1
B9L1-220 |  | Metal Framing @ Corridors + Top 4'0 DW | 1-1 |  | 7 | 0 | 7 | 04-Mar-25 | 12-Mar-25 | J: -158; S: Metal Framing @ Corridors + Top 4'0 DW; A: 1-1
B9L1-240 | Mechanical Equipment |  | 1-1 |  | 20 | 0 | 20 | 13-Mar-25 | 09-Apr-25 | J: -139; A: Mechanical Equipment; D: 1-1
B9L1-250 | HVAC Pipe OH Rough In |  | 1-1 |  | 20 | 0 | 20 | 13-Mar-25 | 09-Apr-25 | J: -158; A: HVAC Pipe OH Rough In; J: 1-1
B9L1-300 |  | Metal Framing @ Rooms | 1-1 |  | 13 | 0 | 13 | 13-Mar-25 | 31-Mar-25 | J: -141; A: Metal Framing @ Rooms; D: 1-1
B9L1-310 |  | In Wall Mechanical / Contr ols Rou gh In | 1-1 |  | 15 | 0 | 15 | 14-Mar-25 | 03-Apr-25 | J: -122; O: In Wall Mechanical / Contr ols Rough In; A: 1-1
B9L1-330 |  | In Wall Electrical Rough In | 1 -1 |  | 15 | 0 | 15 | 17-Mar-25 | 04-Apr-25 | J: -136; A: In Wall Electrical Rough In; J: 1 -1
B9L1-344 | Power In Wall Branc h |  | 1- 1 |  | 10 | 0 | 10 | 17-Mar-25 | 28-Mar-25 | J: -141; J: Power In Wall Branc h; N: 1- 1
B9L1-320 |  | In Wall Plumbing Rough In | 1 -1 |  | 15 | 0 | 15 | 17-Mar-25 | 04-Apr-25 | J: -134; A: In Wall Plumbing Rough In; J: 1 -1
B9L1-342 |  | Distribution Panels Install | 1-1 |  | 10 | 0 | 10 | 20-Mar-25 | 02-Apr-25 | J: -134; A: Distribution Panels Install; J: 1-1
B9L1-280 | Electrical OH Rough In |  | 1-1 |  | 15 | 0 | 15 | 20-Mar-25 | 09-Apr-25 | J: -158; A: Electrical OH Rough In; D: 1-1
B9L1-290 |  | Fire Protection OH Rough In | 1-1 |  | 10 | 0 | 10 | 20-Mar-25 | 02-Apr-25 | J: -131; A: Fire Protection OH Rough In; J: 1-1
B9L1-346 | Lighting In Wall Branch |  | 1 -1 |  | 10 | 0 | 10 | 24-Mar-25 | 04-Apr-25 | J: -141; J: Lighting In Wall Branch; D: 1 -1
B9L1-260 | Plumbing OH Rough In |  | 1-1 |  | 20 | 0 | 20 | 27-Mar-25 | 23-Apr-25 | J: -147; A: Plumbing OH Rough In; J: 1-1
B9L1-348 |  | Fire Alarm In Wall Conduits | 1-1 |  | 10 | 0 | 10 | 31-Mar-25 | 11-Apr-25 | J: -141; A: Fire Alarm In Wall Conduits; F: 1-1
B9L1-352 | Security In Wall Conduits |  | 1-1 |  | 10 | 0 | 10 | 31-Mar-25 | 11-Apr-25 | J: -141; A: Security In Wall Conduits; J: 1-1
B9L1-354 | Data In Wall C ondu its |  | 1- 1 |  | 10 | 0 | 10 | 31-Mar-25 | 11-Apr-25 | J: -141; J: Data In Wall Condu its; D: 1- 1
B9L1-380 | Spray Foam Insulation |  | 1-1 |  | 5 | 0 | 5 | 01-Apr-25 | 07-Apr-25 | J: -122; J: Spray Foam Insulation; D: 1-1
B9L1-270 | Controls OH Rough In |  | 1-1 |  | 20 | 0 | 20 | 03-Apr-25 | 30-Apr-25 | J: -151; A: Controls OH Rough In; J: 1-1
B9L1-340 |  | OH FP Test/Inspections - | 1-1 |  | 5 | 0 | 5 | 03-Apr-25 | 09-Apr-25 | J: -126; A: OH FP Test/Inspections -; J: 1-1
B9L1-282 |  | Electrical Power Conduits | 1-1 |  | 10 | 0 | 10 | 10-Apr-25 | 23-Apr-25 | J: -158; S: Electrical Power Conduits; J: 1-1
B9L1-292 | Cable Tray | 1-1 |  |  | 10 | 0 | 10 | 10-Apr-25 | 23-Apr-25 | J: -114; J: Cable Tray; S: 1-1
B9L1-350 |  | OH Mechanical Test/Inspections | 1-1 |  | 3 | 0 | 3 | 10-Apr-25 | 14-Apr-25 | J: -139; S: OH Mechanical Test/Inspections; M: 1-1
B9L1-430 | Inspect In-Wall Electric al |  | 1-1 |  | 1 | 0 | 1 | 14-Apr-25 | 14-Apr-25 | J: -141; A: Inspect In-Wa ll Elect ric al; J: 1-1
B9L1-450 |  | Pull & Terminate Electrical Wires- | 1-1 |  | 10 | 0 | 10 | 15-Apr-25 | 28-Apr-25 | J: -141; O: Pull & Terminate Electrical Wire s-; A: 1-1
B9L1-360 |  | Insulate OH Mechanical Piping w/Duct | 1-1 |  | 10 | 0 | 10 | 15-Apr-25 | 28-Apr-25 | J: -139; O: Insulate OH Mechanical Piping w/Duct; M: 1-1
B9L1-284 | Lighting Conduits | 1-1 |  |  | 10 | 0 | 10 | 24-Apr-25 | 07-May-25 | J: -158; A: Lighting Conduits; N: 1-1
B9L1-452 |  | Pull & Terminate Br anch W ire | 1-1 |  | 10 | 0 | 10 | 24-Apr-25 | 07-May-25 | J: -148; O: Pull & Terminate Br anch W ire; M: 1-1
Remaining Level of Effort |  |  | Actual Work | Critical Remaining Work |  |  |  | Page 28 of 46 |  | J: TASK filter: Activity Status.
Actual Level of Effort |  |  | Remaining Work | Milestone | [5 empty] | D: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  |  |  | Original | Actual | Remaining | Start | J: Finish; F: Total Float; J: 2025; A: 2026; AM: 2027
[6 empty] | Duration | Duration | Duration | [30 empty] | M
[11 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
B9L1-370 |  | Frame Soffits & Ceilings | 1-1 |  |  | 10 | 0 | 10 | 01-May-25 | 14-May-25 | J: -151; A: Frame Soffits & Ceilings; F: 1-1
B9L1-410 |  | Pull Control Wire to Devices- | 1-1 |  |  | 10 | 0 | 10 | 01-May-25 | 14-May-25 | J: -21; S: Pull Control Wire to Devices-; M: 1-1
B9L1-286 | Fire Alarm Conduits | 1-1 |  |  |  | 10 | 0 | 10 | 08-May-25 | 21-May-25 | J: -124; A: Fire Alarm Conduits; D: 1-1
B9L1-288 |  | Security Conduits/ J-Hooks/ Sleeves | 1-1 |  |  | 10 | 0 | 10 | 08-May-25 | 21-May-25 | J: -124; N: Security Conduits/ J-Hooks/ Sleeves; J: 1-1
B9L1-454 |  | Pull & Terminate Br anch Lighting | 1-1 |  |  | 10 | 0 | 10 | 08-May-25 | 21-May-25 | J: -158; O: Pull & Terminate Br anch L ighting; A: 1-1
B9L1-480 |  | Terminate Controls - | 1-1 |  |  | 5 | 0 | 5 | 15-May-25 | 21-May-25 | J: -21; A: Terminate Controls -; J: 1-1
B9L1-400 |  | Seal Penetrations Thru Fire Wall /Floors |  | 1-1 |  | 4 | 0 | 4 | 20-May-25 | 23-May-25 | J: -158; N: Seal Penetrations Thru Fire Wall /Floors; J: 1-1
B9L1-440 |  | OH Electrical Inspections - | 1-1 |  |  | 2 | 0 | 2 | 22-May-25 | 23-May-25 | J: -158; S: OH Electrical Inspections -; F: 1-1
B9L1-456 | Pull Fire Alarm | 1-1 |  |  |  | 10 | 0 | 10 | 22-May-25 | 05-Jun-25 | J: -124; A: Pull Fire Alarm; N: 1-1
B9L1-458 | Pull Data & Security | 1-1 |  |  |  | 10 | 0 | 10 | 22-May-25 | 05-Jun-25 | J: -124; S: Pull Data & Security; J: 1-1
B9L1-420 |  | Plumbing Testing & Insp ection | 1-1 |  |  | 3 | 0 | 3 | 23-May-25 | 28-May-25 | J: -168; O: Plumbing Testing & Inspection; A: 1-1
B9L1-460 |  | Insulate Plumbing Piping | 1-1 |  |  | 8 | 0 | 8 | 29-May-25 | 09-Jun-25 | J: -168; S: Insulate Plumbing Piping; M: 1-1
B9L1-490 | OH Inspection - | 1-1 |  |  |  | 0 | 0 | 0 |  | 09-Jun-25 | J: -168; A: OH Inspection -; D: 1-1
FINISH LVL 1 | [5 empty] | 167 | 0 | 167 | 01-Apr-25 | 24-Nov-25 | J: -128
B9L1-390 | Interior Windows | 1-1 |  |  |  | 5 | 0 | 5 | 01-Apr-25 | 07-Apr-25 | J: -122; J: Interior Windows; O: 1-1
B9L1-562 |  | Install & Ter minate WAP | 1-1 |  |  | 10 | 0 | 10 | 29-Apr-25 | 12-May-25 | J: -35; A: Install & Ter minate WAP; F: 1-1
B9L1-470 |  | Gypsum Board Walls | 1-1 |  |  | 10 | 0 | 10 | 29-May-25 | 11-Jun-25 | J: -158; S: Gypsum Board Walls; F: 1-1
B9L1-510 |  | Tape and Finish Walls | 1-1 |  |  | 15 | 0 | 15 | 05-Jun-25 | 25-Jun-25 | J: -158; O: Tape and Finish Walls; F: 1-1
B9L1-564 | Terminate Security | 1-1 |  |  |  | 10 | 0 | 10 | 06-Jun-25 | 19-Jun-25 | J: -41; S: Terminate Security; F: 1-1
B9L1-566 |  | Terminate Fire Alarm | 1-1 |  |  | 10 | 0 | 10 | 06-Jun-25 | 19-Jun-25 | J: -51; S: Terminate Fire Alarm; F: 1-1
B9L1-500 |  | Gypsum Board Soffits & Ceilings | 1-1 |  |  | 10 | 0 | 10 | 10-Jun-25 | 23-Jun-25 | J: -168; N: Gypsum Board Soffits & Ceilings; M: 1-1
B9L1-520 |  | Tape and Finish Soffit s & C eilings | 1-1 |  |  | 12 | 0 | 12 | 24-Jun-25 | 10-Jul-25 | J: -168; D: Tape and Finish Soffit s & Ceilings; J: 1-1
B9L1-530 |  | Prime Paint & 1st Coat | 1-1 |  |  | 10 | 0 | 10 | 11-Jul-25 | 24-Jul-25 | J: -168; N: Prime Paint & 1st Coat; M: 1-1
B9L1-532 |  | Install Specialty Doors | 1-1 |  |  | 10 | 0 | 10 | 25-Jul-25 | 07-Aug-25 | J: -168; N: Install Specialty Doors; A: 1-1
B9L1-534 |  | Install Security Doors | 1-1 |  |  | 10 | 0 | 10 | 25-Jul-25 | 07-Aug-25 | J: -168; N: Install Security Doors; A: 1-1
B9L1-540 | ACT Ceiling Grid | 1-1 |  |  |  | 8 | 0 | 8 | 08-Aug-25 | 19-Aug-25 | J: -168; N: ACT Ceiling Grid; M: 1-1
B9L1-550 |  | Mech OH Ceiling Finishes | 1-1 |  |  | 10 | 0 | 10 | 13-Aug-25 | 26-Aug-25 | J: -168; J: Mech OH Ceiling Finishes; J: 1-1
B9L1-560 |  | Electrical Ceiling Finishes | 1-1 |  |  | 10 | 0 | 10 | 13-Aug-25 | 26-Aug-25 | J: -168; J: Electrical Ceiling Finishes; J: 1-1
B9L1-570 |  | Fire Protection Ceiling Finishes | 1-1 |  |  | 10 | 0 | 10 | 13-Aug-25 | 26-Aug-25 | J: -168; F: Fire Protection Ceiling Finishes; J: 1-1
B9L1-580 | Ceramic Tile | 1-1 |  |  |  | 10 | 0 | 10 | 27-Aug-25 | 10-Sep-25 | J: -168; N: Ceramic Tile; F: 1-1
B9L1-590 |  | Terrazzo / Resinous Flooring | 1-1 |  |  | 10 | 0 | 10 | 27-Aug-25 | 10-Sep-25 | J: -168; F: Terrazzo / Resinous Flooring; J: 1-1
B9L1-610 |  | Doors and Hardware | 1-1 |  |  | 10 | 0 | 10 | 11-Sep-25 | 24-Sep-25 | J: -100; J: Doors and Hardware; M: 1-1
B9L1-600 | Mill Work | 1-1 |  |  |  | 20 | 0 | 20 | 11-Sep-25 | 08-Oct-25 | J: -168; N: Mill Work; F: 1-1
B9L1-2083 |  | Set Kitchen Equipment 9 Lvl 1 |  |  |  | 15 | 0 | 15 | 11-Sep-25 | 01-Oct-25 | J: -163; F: Set Kitchen Equipment 9 Lvl 1
B9L1-620 | Final Paint | 1-1 |  |  |  | 10 | 0 | 10 | 25-Sep-25 | 08-Oct-25 | J: -168; D: Final Paint; M: 1-1
B9L1-652 | Fire Alarm Devices | 1-1 |  |  |  | 10 | 0 | 10 | 02-Oct-25 | 15-Oct-25 | J: -123; J: Fire Alarm Devices; J: 1-1
B9L1-654 | Security Devices | 1-1 |  |  |  | 10 | 0 | 10 | 02-Oct-25 | 15-Oct-25 | J: -100; J: Security Devices; M: 1-1
B9L1-656 | Data Devices | 1-1 |  |  |  | 10 | 0 | 10 | 02-Oct-25 | 15-Oct-25 | J: -100; J: Data Devices; A: 1-1
B9L1-670 | Window Shades | 1-1 |  |  |  | 5 | 0 | 5 | 09-Oct-25 | 15-Oct-25 | J: -115; J: Window Shades; M: 1-1
B9L1-680 | Signage | 1-1 |  |  |  | 5 | 0 | 5 | 09-Oct-25 | 15-Oct-25 | J: -115; N: Signage; F: 1-1
B9L1-640 |  | Electrical Wall F inis hes | 1-1 |  |  | 10 | 0 | 10 | 09-Oct-25 | 22-Oct-25 | J: -149; F: Electrical Wall F in is hes; J: 1-1
B9L1-650 | Visual Displays | 1-1 |  |  |  | 5 | 0 | 5 | 09-Oct-25 | 15-Oct-25 | J: -115; J: Visual Displays; A: 1-1
B9L1-660 |  | Wall and Co rner Protection | 1-1 |  |  | 5 | 0 | 5 | 09-Oct-25 | 15-Oct-25 | J: -115; F: Wall and Corner Protectio n; A: 1-1
B9L1-630 | Plumbing Finishes | 1-1 |  |  |  | 5 | 0 | 5 | 09-Oct-25 | 15-Oct-25 | J: -168; J: Plumbing Finishes; M: 1-1
B9L1-2093 | Misc medical |  |  |  |  | 5 | 0 | 5 | 09-Oct-25 | 15-Oct-25 | J: -100; D: Misc medical
B9L1-700 | Ceiling Tiles | 1-1 |  |  |  | 8 | 0 | 8 | 23-Oct-25 | 03-Nov-25 | J: -128; J: Ceiling Tiles; A: 1-1
B9L1-720 | Carpet/VCT | 1-1 |  |  |  | 15 | 0 | 15 | 04-Nov-25 | 24-Nov-25 | J: -128; F: Carpet/VCT; M: 1-1
| FINISHES COMMON SPACES LVL 1 |  |  |  |  | 38 | 0 | 38 | 09-Oct-25 | 02-Dec-25 | J: -133
| Remaining Level of Effort |  | Actual Work |  | Critical Remaining Work |  |  |  | Page 29 of 46 |  | J: TASK filter: Activity Status.
| Actual Level of Effort |  | Remaining Work |  | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  |  | Original | Actual | Remaining | Start | Finish | Total Float | A: 2025; J: 2026; F: 2027
[5 empty] | Duration | Duration | Duration
[10 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | AM
B9L1-890 | Inst Toilet Accessories |  |  |  | 23 | 0 | 23 | 09-Oct-25 | 10-Nov-25 | J: -139; M: Inst Toilet Accessories
B9L1-690 |  | Wood Trim Corridor/Lobby/ Waiting -Lvl 1 Common |  |  | 10 | 0 | 10 | 16-Oct-25 | 29-Oct-25 | J: -168; J: Wood Trim Corridor/Lobby/ Waiting -Lvl 1 Common
B9L1-710 |  | Inst Interior Glass/Glazing Corridor/Lobby/ Waiting Lvl 1 C ommon |  |  | 5 | 0 | 5 | 30-Oct-25 | 05-Nov-25 | J: -168; A: Inst Interior Glass/Glazing Corridor/Lobby/ Waiting L vl 1 C omm
B9L1-730 |  | Finish Coat Paint Corridor/Lobby/ Waiting - -Lv l 1 Common |  |  | 5 | 0 | 5 | 06-Nov-25 | 12-Nov-25 | J: -168; A: Finish Coat Paint Corridor/Lobby/ Waiting - -Lv l 1 Common
B9L1-740 |  | Electrical Wall D ev ic es Corridor/Lobby/ Waiting -Lvl 1 Common |  |  | 5 | 0 | 5 | 12-Nov-25 | 18-Nov-25 | J: -168; S: Electrical Wall Dev ic es Corridor/Lobby/ Waiting -Lvl 1 Commo
B9L1-752 |  | Fire Alarm Devices -Corridor/Lobby/ Waiting -Lvl 1 Common |  |  | 5 | 0 | 5 | 12-Nov-25 | 18-Nov-25 | J: -168; S: Fire Alarm Devices -Corridor/Lobby/ Waiting -Lvl 1 Common
B9L1-754 |  | Security Devices -Corridor/Lobby/ Waiting - Lv l 1 Common |  |  | 5 | 0 | 5 | 12-Nov-25 | 18-Nov-25 | J: -168; A: Security Devices -Corridor/Lobby/ Waiting - Lv l 1 Common
B9L1-756 |  | Data Devices -Corridor/Lobby/ Waiting -Lvl 1 Co mmon |  |  | 5 | 0 | 5 | 12-Nov-25 | 18-Nov-25 | J: -168; A: Data Devices -Corridor/Lobby/ Waiting -Lvl 1 Common
B9L1-750 |  | Ceiling Tile Install Corridor/Lobby/ Waiting -Lvl 1 Common |  |  | 8 | 0 | 8 | 13-Nov-25 | 24-Nov-25 | J: -149; A: Ceiling Tile Install Corridor/Lobby/ Waiting -Lvl 1 Common
B9L1-760 |  | Control Finishes Installation -Lvl 1 Common |  |  | 6 | 0 | 6 | 13-Nov-25 | 20-Nov-25 | J: -131; J: Control Finishes Installation -Lvl 1 Common
B9L1-770 |  | Wall Mount Accessories Corridor/Lobby/ Waiting - -Lvl 1 Common |  |  | 5 | 0 | 5 | 19-Nov-25 | 25-Nov-25 | J: -129; S: Wall Mount Accessories Corridor/Lobby/ Waiting - -Lvl 1 Com
B9L1-780 |  | Signage Corridor/Lobby/ Waiting --Lvl 1 C ommon |  |  | 3 | 0 | 3 | 19-Nov-25 | 21-Nov-25 | J: -127; J: Signage Corridor/Lobby/ Waiting --Lvl 1 C ommon
B9L1-790 |  | Flooring Finishes Corridor/Lobby/ Waiting --Lvl 1 Common |  |  | 5 | 0 | 5 | 25-Nov-25 | 02-Dec-25 | J: -133; S: Flooring Finishes Corridor/Lobby/ Waiting --Lvl 1 Common
BLDG 9 2ND FLOOR |  |  |  |  | 391 | 182 | 228 | 15-May-24 A | 23-Dec-25 | J: -148
GENERAL FLOOR ABAT EMENT / DEMO |  |  |  |  | 67 | 182 | 10 | 15-May-24 A | 14-Feb-25 | J: -76
B9L2-130 | Sawcut Floor @ Openings 2nd |  |  |  | 5 | 182 | 2 | 15-May-24 A | 13-Feb-25 | J: -170; J: Sawcut Floor @ Openings 2nd
B9L2-150 | Structural Steel (17) loc 2nd |  |  |  | 9 | 181 | 1 | 16-May-24 A | 14-Feb-25 | J: -162; J: Structural Steel (17) loc 2nd
B9L1-940 | Replace Windows 2nd Fl |  |  |  | 10 | 128 | 5 | 01-Aug-24 A | 07-Feb-25 | J: -71; M: Replace Windows 2nd Fl
STRUCTURE 2ND TO 3RD |  |  |  |  | 157 | 155 | 10 | 24-Jun-24 A | 25-Feb-25 | J: -170
B9L1-970 |  | Layup CMU @ Elev Hoistway 2nd to 3rd |  |  | 8 | 155 | 4 | 24-Jun-24 A | 17-Feb-25 | J: -164; A: Layup CMU @ Elev Hoistway 2nd to 3rd
B9L1-980 |  | Inst Steel Stair Structure & Deck 1st to 2nd @ Str A & B |  |  | 10 | 0 | 10 | 12-Feb-25 | 25-Feb-25 | J: -170; N: Inst Steel Stair Structure & Deck 1st to 2nd @ Str A & B
ROUGH IN LVL 2 |  |  |  |  | 186 | 155 | 100 | 24-Jun-24 A | 17-Jul-25 | J: -55
B9L2-230 | Ductwork OH Rough In | Lvl 2 |  |  | 20 | 155 | 19 | 24-Jun-24 A | 05-May-25 | J: -170; A: Ductwork OH Rough In; F: Lvl 2
B9L2-160 | Layout/Top Track Lvl 2 |  |  |  | 8 | 0 | 8 | 26-Feb-25 | 07-Mar-25 | J: -170; J: Layout/Top Track Lvl 2
B9L2-180 | Inst Hanger Duct Lvl 2 |  |  |  | 3 | 0 | 3 | 10-Mar-25 | 12-Mar-25 | J: -170; M: Inst Hanger Duct; O: Lvl 2
B9L2-200 | Inst Hanger Plumbing | Lvl 2 |  |  | 3 | 0 | 3 | 10-Mar-25 | 12-Mar-25 | J: -170; J: Inst Hanger Plumbing; N: Lvl 2
B9L2-190 | Inst HangerHVAC Piping | Lvl 2 |  |  | 3 | 0 | 3 | 10-Mar-25 | 12-Mar-25 | J: -170; J: Inst HangerHVAC Piping; D: Lvl 2
B9L2-210 | Inst Hanger Electrical Lvl 2 |  |  |  | 3 | 0 | 3 | 10-Mar-25 | 12-Mar-25 | J: -170; J: Inst Hanger Electrical Lvl 2
B9L2-2123 |  | Metal Framing @ Exterior Walls Lvl 2 |  |  | 5 | 0 | 5 | 10-Mar-25 | 14-Mar-25 | J: -101; A: Metal Framing @ Exterior Walls L vl 2
B9L2-170 | Fireproofing | Lvl 2 |  |  | 5 | 0 | 5 | 24-Mar-25 | 28-Mar-25 | J: -170; M: Fireproofing; S: Lvl 2
B9L2-220 |  | Metal Framing @ Corridors + Top 4'0 DW | Lv l 2 |  | 7 | 0 | 7 | 31-Mar-25 | 08-Apr-25 | J: -170; O: Metal Framing @ Corridors + Top 4'0 DW; M: Lv l 2
B9L2-240 | Mechanical Equipment | Lvl 2 |  |  | 20 | 0 | 20 | 09-Apr-25 | 06-May-25 | J: -143; A: Mechanical Equipment; J: Lvl 2
B9L2-250 | HVAC Pipe OH Rough In | Lvl 2 |  |  | 20 | 0 | 20 | 09-Apr-25 | 06-May-25 | J: -170; A: HVAC Pipe OH Rough In; F: Lvl 2
B9L2-260 | Plumbing OH Rough In | Lvl 2 |  |  | 20 | 0 | 20 | 16-Apr-25 | 13-May-25 | J: -153; A: Plumbing OH Rough In; F: Lvl 2
B9L2-280 | Electrical OH Rough In | Lvl 2 |  |  | 20 | 0 | 20 | 21-Apr-25 | 16-May-25 | J: -170; A: Electrical OH Rough In; F: Lvl 2
B9L2-300 | Metal Framing @ Rooms | Lvl 2 |  |  | 8 | 0 | 8 | 24-Apr-25 | 05-May-25 | J: -156; A: Metal Framing @ Rooms; F: Lvl 2
B9L2-320 |  | In Wall Mechanical / Contr ols Rou gh In | Lv l 2 |  | 15 | 0 | 15 | 25-Apr-25 | 15-May-25 | J: -140; N: In Wall Mechanical / Contr ols Rough In; J: Lv l 2
B9L2-330 |  | In Wall Plumbing Rough In L vl 2 |  |  | 15 | 0 | 15 | 28-Apr-25 | 16-May-25 | J: -149; O: In Wall Plumbing Rough In Lvl 2
B9L2-340 |  | In Wall Electrical Rough In Lv l 2 |  |  | 15 | 0 | 15 | 28-Apr-25 | 16-May-25 | J: -151; O: In Wall Electrical Rough In Lv l 2
B9L2-344 | Power In Wall Branc h Lv l 2 |  |  |  | 10 | 0 | 10 | 28-Apr-25 | 09-May-25 | J: -156; A: Power In Wall Branc h; J: Lv l 2
B9L2-270 | Controls OH Rough In Lvl 2 |  |  |  | 20 | 0 | 20 | 30-Apr-25 | 28-May-25 | J: -155; O: Controls OH Rough In Lvl 2
B9L2-290 | Fire Protection OH Rough In | Lvl 2 |  |  | 15 | 0 | 15 | 30-Apr-25 | 20-May-25 | J: -150; O: Fire Protection OH Rough In; M: Lvl 2
B9L2-342 | Distribution Panels Install | Lvl 2 |  |  | 10 | 0 | 10 | 01-May-25 | 14-May-25 | J: -149; S: Distribution Panels Install; F: Lvl 2
B9L2-346 | Lighting In Wall Branch | L vl 2 |  |  | 10 | 0 | 10 | 05-May-25 | 16-May-25 | J: -156; A: Lighting In Wall Branch; F: Lvl 2
B9L2-380 | Spray Foam Insulation | Lvl 2 |  |  | 5 | 0 | 5 | 06-May-25 | 12-May-25 | J: -137; A: Spray Foam Insulation; J: Lvl 2
B9L2-350 | OH Mechanical Test/Inspections | Lvl 2 |  |  | 3 | 0 | 3 | 07-May-25 | 09-May-25 | J: -143; O: OH Mechanical Test/Inspections; A: Lvl 2
B9L2-360 |  | Insulate OH Mechanical Piping w/Duct | Lvl 2 |  | 10 | 0 | 10 | 12-May-25 | 23-May-25 | J: -143; N: Insulate OH Mechanical Piping w/Duct; J: Lvl 2
B9L2-348 | Fire Alarm In Wall Conduits | Lvl 2 |  |  | 10 | 0 | 10 | 12-May-25 | 23-May-25 | J: -156; S: Fire Alarm In Wall Conduits; M: Lvl 2
B9L2-352 | Security In Wall Conduits | Lvl 2 |  |  | 10 | 0 | 10 | 12-May-25 | 23-May-25 | J: -156; S: Security In Wall Conduits; F: Lvl 2
Remaining Level of Effort |  | Actual Work |  | Critical Remaining Work |  |  |  | Page 30 of 46 |  | J: TASK filter: Activity Status.
Actual Level of Effort |  | Remaining Work |  | Milestone | [5 empty] | D: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  |  | Original | Actual | Remaining | Start | Finish | J: Total Float; J: 2025; J: 2026; M: 2027
[5 empty] | Duration | Duration | Duration | [30 empty] | M
[10 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
B9L2-354 | Data In Wall C ondu its | Lv l 2 |  |  | 10 | 0 | 10 | 12-May-25 | 23-May-25 | J: -156; S: Data In Wall C onduits; J: Lv l 2
B9L2-282 | Electrical Power Conduits | Lvl 2 |  |  | 10 | 0 | 10 | 19-May-25 | 02-Jun-25 | J: -170; O: Electrical Power Conduits; M: Lvl 2
B9L2-292 | Cable Tray | Lvl 2 |  |  | 10 | 0 | 10 | 19-May-25 | 02-Jun-25 | J: -141; A: Cable Tray; O: Lvl 2
B9L2-310 | OH FP Test/Inspections - | Lvl 2 |  |  | 5 | 0 | 5 | 21-May-25 | 28-May-25 | J: -145; S: OH FP Test/Inspections -; M: Lvl 2
B9L2-420 |  | Plumbing Testing & Insp ection | Lvl 2 |  | 3 | 0 | 3 | 23-May-25 | 28-May-25 | J: -153; O: Plumbing Testing & Inspection; A: Lvl 2
B9L2-430 | Inspect In-Wall Electric al | Lvl 2 |  |  | 1 | 0 | 1 | 27-May-25 | 27-May-25 | J: -156; S: Inspect In-Wall Electric al; F: Lvl 2
B9L2-370 |  | Frame Soffits & Ceilings Lvl 2 |  |  | 10 | 0 | 10 | 29-May-25 | 11-Jun-25 | J: -155; N: Frame Soffits & Ceilings Lvl 2
B9L2-460 | Insulate Plumbing Piping | Lvl 2 |  |  | 8 | 0 | 8 | 29-May-25 | 09-Jun-25 | J: -153; O: Insulate Plumbing Piping; M: Lvl 2
B9L2-410 |  | Pull Control Wire to Devices- | Lvl 2 |  | 10 | 0 | 10 | 29-May-25 | 11-Jun-25 | J: -35; O: Pull Control Wire to Devices-; A: Lvl 2
B9L2-284 | Lighting Conduits | Lvl 2 |  |  | 10 | 0 | 10 | 03-Jun-25 | 16-Jun-25 | J: -170; S: Lighting Conduits; J: Lvl 2
B9L2-452 |  | Pull & Terminate Br anch W ire | Lvl 2 |  | 10 | 0 | 10 | 03-Jun-25 | 16-Jun-25 | J: -160; N: Pull & Terminate Br anch W ire; A: Lvl 2
B9L2-480 |  | Terminate Controls - Lvl 2 |  |  | 5 | 0 | 5 | 12-Jun-25 | 18-Jun-25 | J: -35; O: Terminate Controls - Lvl 2
B9L2-286 | Fire Alarm Conduits | Lvl 2 |  |  | 10 | 0 | 10 | 17-Jun-25 | 30-Jun-25 | J: -151; O: Fire Alarm Conduits; F: Lvl 2
B9L2-288 |  | Security Conduits/ J-Hooks/ Sleeves | Lvl 2 |  | 10 | 0 | 10 | 17-Jun-25 | 30-Jun-25 | J: -151; D: Security Conduits/ J-Hooks/ Sleeves; J: Lvl 2
B9L2-454 |  | Pull & Terminate Br anch Lighting | Lvl 2 |  | 10 | 0 | 10 | 17-Jun-25 | 30-Jun-25 | J: -170; D: Pull & Terminate Br anch Lighting; J: Lvl 2
B9L2-400 |  | Seal Penetrations Thru Fire Wall /Floors | Lvl 2 |  | 4 | 0 | 4 | 27-Jun-25 | 02-Jul-25 | J: -170; J: Seal Penetrations Thru Fire Wall /Floors; A: Lvl 2
B9L2-440 | OH Electrical Inspections - | Lvl 2 |  |  | 2 | 0 | 2 | 01-Jul-25 | 02-Jul-25 | J: -170; N: OH Electrical Inspections -; A: Lvl 2
B9L2-456 | Pull Fire Alarm | Lvl 2 |  |  | 10 | 0 | 10 | 01-Jul-25 | 15-Jul-25 | J: -151; S: Pull Fire Alarm; J: Lvl 2
B9L2-458 | Pull Data & Security | Lvl 2 |  |  | 10 | 0 | 10 | 01-Jul-25 | 15-Jul-25 | J: -151; O: Pull Data & Security; F: Lvl 2
B9L2-490 | OH Inspection - | Lvl 2 |  |  | 0 | 0 | 0 |  | 02-Jul-25 | J: -170; S: OH Inspection -; J: Lvl 2
B9L2-450 |  | Pull & Terminate Electrical Wires- | Lvl 2 |  | 10 | 0 | 10 | 03-Jul-25 | 17-Jul-25 | J: -91; D: Pull & Terminate Electrical Wires-; J: Lvl 2
FINISH LVL 2 |  |  |  |  | 134 | 0 | 134 | 06-May-25 | 12-Nov-25 | J: -120
B9L2-390 | Interior Windows | Lvl 2 |  |  | 5 | 0 | 5 | 06-May-25 | 12-May-25 | J: -137; A: Interior Windows; D: Lvl 2
B9L2-470 | Gypsum Board Walls | Lv l 2 |  |  | 10 | 0 | 10 | 29-May-25 | 11-Jun-25 | J: -148; S: Gypsum Board Walls; F: Lv l 2
B9L2-510 | Tape and Finish Walls | Lvl 2 |  |  | 15 | 0 | 15 | 05-Jun-25 | 25-Jun-25 | J: -148; O: Tape and Finish Walls; M: Lvl 2
B9L2-500 |  | Gypsum Board Soffits & Ceilings | Lvl 2 |  | 10 | 0 | 10 | 03-Jul-25 | 17-Jul-25 | J: -170; D: Gypsum Board Soffits & Ceilings; J: Lvl 2
B9L2-520 |  | Tape and Finish Soffit s & C eilings | Lvl 2 |  | 12 | 0 | 12 | 11-Jul-25 | 28-Jul-25 | J: -170; J: Tape and Finish Soffits & C eilings; J: Lvl 2
B9L2-564 | Terminate Security | Lvl 2 |  |  | 10 | 0 | 10 | 16-Jul-25 | 29-Jul-25 | J: -99; O: Terminate Security; M: Lvl 2
B9L2-566 | Terminate Fire Alarm | Lvl 2 |  |  | 10 | 0 | 10 | 16-Jul-25 | 29-Jul-25 | J: -99; N: Terminate Fire Alarm; M: Lvl 2
B9L2-562 | Install & Ter minate WAP | Lvl 2 |  |  | 10 | 0 | 10 | 18-Jul-25 | 31-Jul-25 | J: -91; N: Install & Ter minate WAP; M: Lvl 2
B9L2-530 | Prime Paint & 1st Coat | Lvl 2 |  |  | 10 | 0 | 10 | 29-Jul-25 | 11-Aug-25 | J: -170; D: Prime Paint & 1st Coat; A: Lvl 2
B9L2-540 | ACT Ceiling Grid | Lvl 2 |  |  | 8 | 0 | 8 | 12-Aug-25 | 21-Aug-25 | J: -170; N: ACT Ceiling Grid; M: Lvl 2
B9L2-532 | Install Specialty Doors | Lvl 2 |  |  | 10 | 0 | 10 | 12-Aug-25 | 25-Aug-25 | J: -167; D: Install Specialty Doors; M: Lvl 2
B9L2-534 | Install Security Doors | Lvl 2 |  |  | 10 | 0 | 10 | 12-Aug-25 | 25-Aug-25 | J: -167; D: Install Security Doors; A: Lvl 2
B9L2-550 | Mech OH Ceiling Finishes | Lvl 2 |  |  | 10 | 0 | 10 | 15-Aug-25 | 28-Aug-25 | J: -170; J: Mech OH Ceiling Finishes; J: Lvl 2
B9L2-560 | Electrical Ceiling Finishes | Lvl 2 |  |  | 10 | 0 | 10 | 15-Aug-25 | 28-Aug-25 | J: -170; J: Electrical Ceiling Finishes; J: Lvl 2
B9L2-570 |  | Fire Protection Ceiling Finishes | Lvl 2 |  | 10 | 0 | 10 | 15-Aug-25 | 28-Aug-25 | J: -170; J: Fire Protection Ceiling Finishes; J: Lvl 2
B9L2-580 | Resinous Flooring | Lvl 2 |  |  | 10 | 0 | 10 | 29-Aug-25 | 12-Sep-25 | J: -170; D: Resinous Flooring; A: Lvl 2
B9L2-590 | Terrazzo Flooring | Lvl 2 |  |  | 10 | 0 | 10 | 29-Aug-25 | 12-Sep-25 | J: -170; D: Terrazzo Flooring; A: Lvl 2
B9L2-600 | Ceramic Tile | Lvl 2 |  |  | 9 | 0 | 9 | 29-Aug-25 | 11-Sep-25 | J: -169; N: Ceramic Tile; M: Lvl 2
B9L2-620 | Doors and Hardware | Lvl 2 |  |  | 20 | 0 | 20 | 15-Sep-25 | 10-Oct-25 | J: -107; J: Doors and Hardware; J: Lvl 2
B9L2-610 | Mill Work | Lvl 2 |  |  | 20 | 0 | 20 | 15-Sep-25 | 10-Oct-25 | J: -170; D: Mill Work; M: Lvl 2
B9L2-630 | Final Paint | Lvl 2 |  |  | 10 | 0 | 10 | 29-Sep-25 | 10-Oct-25 | J: -170; D: Final Paint; M: Lvl 2
B9L2-640 | Plumbing Finishes | Lvl 2 |  |  | 10 | 0 | 10 | 06-Oct-25 | 17-Oct-25 | J: -123; J: Plumbing Finishes; J: Lvl 2
B9L2-650 | Electrical Wall F inis hes | Lv l 2 |  |  | 10 | 0 | 10 | 06-Oct-25 | 17-Oct-25 | J: -146; F: Electrical Wall F inis hes; J: Lv l 2
B9L2-652 | Fire Alarm Devices | Lvl 2 |  |  | 10 | 0 | 10 | 06-Oct-25 | 17-Oct-25 | J: -146; J: Fire Alarm Devices; J: Lvl 2
B9L2-654 | Security Devices | Lvl 2 |  |  | 10 | 0 | 10 | 06-Oct-25 | 17-Oct-25 | J: -146; J: Security Devices; M: Lvl 2
B9L2-656 | Data Devices | Lvl 2 |  |  | 10 | 0 | 10 | 06-Oct-25 | 17-Oct-25 | J: -146; J: Data Devices; A: Lvl 2
| Remaining Level of Effort | Actual Work |  | Critical Remaining Work |  |  |  | Page 31 of 46 |  | J: TASK filter: Activity Status.
| Actual Level of Effort | Remaining Work |  | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  | Original | Actual | Remaining | Start | Finish | Total Float | M: 2025; J: 2026; F: 2027
|  |  |  | Duration | Duration | Duration
[9 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | AM
B9L2-660 | Visual Displays | Lvl 2 |  | 5 | 0 | 5 | 13-Oct-25 | 17-Oct-25 | J: -112; D: Visual Displays; A: Lvl 2
B9L2-670 | Wall and Co rner Protection | Lvl 2 |  | 5 | 0 | 5 | 13-Oct-25 | 17-Oct-25 | J: -112; F: Wall a nd Corner Protection; A: Lvl 2
B9L2-690 | Window Shades | Lvl 2 |  | 5 | 0 | 5 | 13-Oct-25 | 17-Oct-25 | J: -102; D: Window Shades; M: Lvl 2
B9L2-680 | Signage Lvl 2 |  |  | 5 | 0 | 5 | 13-Oct-25 | 17-Oct-25 | J: -112; D: Signage Lvl 2
B9L2-710 | Ceiling Tiles | Lvl 2 |  | 8 | 0 | 8 | 20-Oct-25 | 29-Oct-25 | J: -120; D: Ceiling Tiles; A: Lvl 2
B9L2-720 | Carpet/VCT | Lvl 2 |  | 10 | 0 | 10 | 30-Oct-25 | 12-Nov-25 | J: -120; J: Carpet/VCT; A: Lvl 2
| FINISHES COMMON SPACES LVL 2 |  |  | 51 | 0 | 51 | 13-Oct-25 | 23-Dec-25 | J: -148
B9L2-700 |  | Wall Prot ec tion/Trim Corridor/Lobby/ Waiting -Lvl 2 Common |  | 10 | 0 | 10 | 13-Oct-25 | 24-Oct-25 | J: -170; A: Wall Prot ec tion/Trim Corridor/Lobby/ Waiting -Lvl 2 Common
B9L2-730 |  | Inst Interior Glass/Glazing Corridor/Lobby/ Waiting --L vl 2 Common |  | 5 | 0 | 5 | 27-Oct-25 | 31-Oct-25 | J: -170; A: Inst Interior Glass/Glazing Corridor/Lobby/ Waiting --Lvl 2 Comm
B9L2-740 |  | Finish Coat Paint Corridor/Lobby/ Waiting - --Lvl 2 Common |  | 5 | 0 | 5 | 31-Oct-25 | 06-Nov-25 | J: -170; A: Finish Coat Paint Corridor/Lobby/ Waiting - --Lvl 2 Co mmon
B9L2-750 |  | Electrical Wall D ev ic es Corridor/Lobby/ Waiting -Lvl 2 Common |  | 5 | 0 | 5 | 06-Nov-25 | 12-Nov-25 | J: -170; A: Electrical Wall Dev ic es Corridor/Lobby/ Waiting -Lvl 2 Commo
B9L2-752 |  | Fire Alarm Devices -Corridor/Lobby/ Waiting -Lvl 2 Common |  | 5 | 0 | 5 | 06-Nov-25 | 12-Nov-25 | J: -125; A: Fire Alarm Devices -Corridor/Lobby/ Waiting -Lvl 2 Common
B9L2-754 |  | Security Devices -Corridor/Lobby/ Waiting - Lv l 2 Common |  | 5 | 0 | 5 | 06-Nov-25 | 12-Nov-25 | J: -125; A: Security Devices -Corridor/Lobby/ Waiting - Lv l 2 Common
B9L2-756 |  | Data Devices -Corridor/Lobby/ Waiting -Lvl 2 Co mmon |  | 5 | 0 | 5 | 06-Nov-25 | 12-Nov-25 | J: -125; J: Data Devices -Corridor/Lobby/ Waiting -L vl 2 Common
B9L2-2103 | Misc medical |  |  | 5 | 0 | 5 | 07-Nov-25 | 13-Nov-25 | J: -142; J: Misc medical
B9L2-760 |  | Ceiling Tile Install Corridor/Lobby/ Waiting --Lvl 2 Common |  | 8 | 0 | 8 | 07-Nov-25 | 18-Nov-25 | J: -145; A: Ceiling Tile Install Corridor/Lobby/ Waiting --Lvl 2 Common
B9L2-770 |  | Control Finishes Installation Lvl 2 Common |  | 5 | 0 | 5 | 07-Nov-25 | 13-Nov-25 | J: -165; J: Control Finishes Installation Lvl 2 Common
B9L2-2113 | Toilet Accessories |  |  | 28 | 0 | 28 | 13-Nov-25 | 23-Dec-25 | J: -169; M: Toilet Accessories
B9L2-780 |  | Wall Mount Accessories Corridor/Lobby/ Waiting - -Lvl 2 Common |  | 5 | 0 | 5 | 13-Nov-25 | 19-Nov-25 | J: -169; A: Wall Mount Accessories Corridor/Lobby/ Waiting - -Lvl 2 Com
B9L2-790 |  | Signage Corridor/Lobby/ Waiting - -Lv l 2 Common |  | 5 | 0 | 5 | 13-Nov-25 | 19-Nov-25 | J: -125; J: Signage Corridor/Lobby/ Waiting - -Lv l 2 Common
B9L2-800 |  | Flooring Finishes Corridor/Lobby/ Waiting --Lvl 2 Common |  | 5 | 0 | 5 | 19-Nov-25 | 25-Nov-25 | J: -129; A: Flooring Finishes Corridor/Lobby/ Waiting --Lvl 2 C ommon
| BLDG 9 3RD FL PH /ROOF |  |  | 478 | 454 | 150 | 21-Apr-23 A | 18-Sep-25 | J: -84
| GENERAL FLOOR ABAT EMENT/D EMO |  |  | 337 | 454 | 12 | 21-Apr-23 A | 05-Mar-25 | J: -12
B9L3-140 | Demo Louvers |  |  | 2 | 454 | 1 | 21-Apr-23 A | 03-Mar-25 | J: -24; M: Demo Louvers
B9L3-150 |  | Sawcut Floor Openings @ 3rd Fl |  | 2 | 208 | 1 | 09-Apr-24 A | 18-Feb-25 | J: -44; A: Sawcut Floor Openings @ 3rd Fl
B9L3-130 | Demo Exterior Walls |  |  | 10 | 26 | 1 | 26-Dec-24 A | 03-Mar-25 | J: -12; J: Demo Exterior Walls
B9L3-170 | Patch Masonry for Openings |  |  | 5 | 24 | 2 | 30-Dec-24 A | 05-Mar-25 | J: -12; J: Patch Masonry for Openings
B9L3-400 |  | Form & Place Conc Curb @ Hoistway |  | 3 | 0 | 3 | 19-Feb-25 | 21-Feb-25 | J: -24; S: Form & Place Conc Curb @ Hoistway
B9L3-410 | CMU Bondbeam @ Hoistway |  |  | 2 | 0 | 2 | 24-Feb-25 | 25-Feb-25 | J: -24; J: CMU Bondbeam @ Hoistway
B9L3-420 |  | Form & Place Hoistway Cap Slab |  | 3 | 0 | 3 | 26-Feb-25 | 28-Feb-25 | J: -24; A: Form & Place Hoistway Cap Slab
| STRUCTURE 3RD FLOOR |  |  | 10 | 0 | 10 | 26-Feb-25 | 11-Mar-25 | J: -54
B9L3-450 | Inst Steel Stairs for Stair C |  |  | 5 | 0 | 5 | 26-Feb-25 | 04-Mar-25 | J: -54; J: Inst Steel Stairs for Stair C
B9L3-460 | Inst Steel Stair for Stair D |  |  | 5 | 0 | 5 | 05-Mar-25 | 11-Mar-25 | J: -54; J: Inst Steel Stair for Stair D
| LVL 3 ROUGH/FINISH PH & ROOF |  |  | 169 | 199 | 69 | 22-Apr-24 A | 18-Sep-25 | J: -84
B9L3-220 | Duct Rough In Lvl 3 |  |  | 25 | 199 | 10 | 22-Apr-24 A | 05-Aug-25 | J: -119; D: Duct Rough In Lvl 3
B9L3-310 | HVAC Insulation Lvl 3 |  |  | 10 | 184 | 9 | 13-May-24 A | 04-Aug-25 | J: -93; D: HVAC Insulation Lvl 3
B9L3-192 |  | Electrical Power Conduits Lvl 3 |  | 15 | 159 | 10 | 18-Jun-24 A | 07-Aug-25 | J: -111; D: Electrical Power Conduits Lvl 3
B9L3-194 | Lighting Conduits Lvl 3 |  |  | 15 | 159 | 12 | 18-Jun-24 A | 11-Aug-25 | J: -111; D: Lighting Conduits Lvl 3
B9L3-196 |  | Mechanical Equipment Electrical Conduits Lvl 3 |  | 15 | 159 | 13 | 18-Jun-24 A | 12-Aug-25 | J: -111; M: Mechanical Equipment Electrical Conduits Lvl 3
B9L3-198 |  | Security/ Data/ FA Conduits Lvl 3 |  | 15 | 159 | 14 | 18-Jun-24 A | 13-Aug-25 | J: -89; J: Security/ Data/ FA Conduits Lvl 3
B9L3-240 | Plumbing Rough In Lvl 3 |  |  | 10 | 92 | 3 | 23-Sep-24 A | 24-Jul-25 | J: -119; D: Plumbing Rough In Lvl 3
B9L3-160 | Shaft Wall Inst all Lvl 3 |  |  | 10 | 0 | 10 | 12-Jun-25 | 25-Jun-25 | J: -119; O: Shaft Wall Inst all Lvl 3
B9L3-180 |  | 4" Fire Treated Insulated Fl Pnl Lvl 3 |  | 15 | 0 | 15 | 26-Jun-25 | 17-Jul-25 | J: -113; D: 4" Fire Treated Insulated Fl Pnl Lvl 3
B9L3-260 | HVAC Piping Rough In Lvl 3 |  |  | 15 | 0 | 15 | 26-Jun-25 | 17-Jul-25 | J: -93; D: HVAC Piping Rough In Lvl 3
B9L3-250 | Controls Rough In Lvl 3 |  |  | 15 | 0 | 15 | 26-Jun-25 | 17-Jul-25 | J: -81; N: Controls Rough In Lvl 3
B9L3-210 | Mechanical Equipment Lvl 3 |  |  | 4 | 0 | 4 | 17-Jul-25 | 22-Jul-25 | J: -119; D: Mechanical Equipment Lvl 3
B9L3-300 | HVAC Pipe Testing Lvl 3 |  |  | 3 | 0 | 3 | 18-Jul-25 | 22-Jul-25 | J: -93; D: HVAC Pipe Testing Lvl 3
B9L3-190 | Electrical OH Rough In Lvl 3 |  |  | 20 | 0 | 20 | 18-Jul-25 | 14-Aug-25 | J: -113; D: Electrical OH Rough In Lvl 3
B9L3-200 |  | Fire Protection OH Rough In Lvl 3 |  | 20 | 0 | 20 | 18-Jul-25 | 14-Aug-25 | J: -60; J: Fire Protection OH Rough In Lvl 3
| Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 32 of 46 |  | J: TASK filter: Activity Status.
| Actual Level of Effort | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  | Original | Actual | Remaining | Start | Finish | Total Float | M: 2025; M: 2026; F: 2027
|  |  | Duration | Duration | Duration | bar: AM
[8 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
B9L3-270 | Plumbing Testing Lvl 3 |  | 3 | 0 | 3 | 25-Jul-25 | 29-Jul-25 | J: -94; N: Plumbing Testing Lvl 3
B9L3-290 | Plumbing Insulation Rough In Lvl 3 |  | 5 | 0 | 5 | 30-Jul-25 | 05-Aug-25 | J: -94; J: Plumbing Insulation Rough In Lvl 3
B9L3-320 | Louvers Lvl 3 |  | 10 | 0 | 10 | 06-Aug-25 | 19-Aug-25 | J: -119; O: Louvers Lvl 3
B9L3-230 | Electrical Connections to Equipment Lvl 3 |  | 12 | 0 | 12 | 15-Aug-25 | 02-Sep-25 | J: -113; M: Electrical Connections to Equipment Lvl 3
B9L3-330 | Duct Final Connections Lvl 3 |  | 15 | 0 | 15 | 20-Aug-25 | 10-Sep-25 | J: -119; F: Duct Final Connections Lvl 3
B9L3-280 | Electrical Systems Finishes- Lighting/FA/Security Lvl 3 |  | 12 | 0 | 12 | 03-Sep-25 | 18-Sep-25 | J: -102; M: Electrical Systems Finishes- Lighting/FA/Security Lvl 3
STAIR FINISHES |  |  | 155 | 141 | 155 | 15-Jul-24 A | 25-Sep-25 | J: -107
STAIR A FINISHES |  |  | 105 | 141 | 66 | 15-Jul-24 A | 15-Sep-25 | J: -99
B9ST-410 | Inst Windows @ Str A |  | 2 | 141 | 1 | 15-Jul-24 A | 16-Jul-25 | J: -77; O: Inst Windows @ Str A
B9ST-300 | Frame Walls @ Str A |  | 8 | 0 | 8 | 12-Jun-25 | 23-Jun-25 | J: -107; O: Frame Walls @ Str A
B9ST-310 | Framing Inspection @ Str A |  | 1 | 0 | 1 | 24-Jun-25 | 24-Jun-25 | J: -99; O: Framing Inspection @ Str A
B9ST-320 | MECH Rough @ Str A |  | 3 | 0 | 3 | 25-Jun-25 | 27-Jun-25 | J: -99; O: MECH Rough @ Str A
B9ST-800 | ELECT Rough @ Str A |  | 3 | 0 | 3 | 25-Jun-25 | 27-Jun-25 | J: -99; O: ELECT Rough @ Str A
B9ST-1030 | Fireprotection Rough @ Str A |  | 3 | 0 | 3 | 25-Jun-25 | 27-Jun-25 | J: -99; N: Fireprotection Rough @ Str A
B9ST-330 | MEP Inspection @ Str A |  | 1 | 0 | 1 | 30-Jun-25 | 30-Jun-25 | J: -99; O: MEP Inspection @ Str A
B9ST-340 | Insulate & Inspect @ Str A |  | 2 | 0 | 2 | 01-Jul-25 | 02-Jul-25 | J: -99; N: Insulate & Inspect @ Str A
B9ST-350 | Hang DW/Shaftwall @ Str A |  | 8 | 0 | 8 | 03-Jul-25 | 15-Jul-25 | J: -99; N: Hang DW/Shaftwall @ Str A
B9ST-360 | Finish DW @ Str A |  | 8 | 0 | 8 | 11-Jul-25 | 22-Jul-25 | J: -99; O: Finish DW @ Str A
B9ST-1080 | Inst Louvers @ Str A |  | 2 | 0 | 2 | 16-Jul-25 | 17-Jul-25 | J: -78; O: Inst Louvers @ Str A
B9ST-370 | Paint 1st Coat Walls @ Str A |  | 5 | 0 | 5 | 23-Jul-25 | 29-Jul-25 | J: -99; D: Paint 1st Coat Walls @ Str A
B9ST-390 | Inst Railings & Posts @ Str A |  | 8 | 0 | 8 | 30-Jul-25 | 08-Aug-25 | J: -99; D: Inst Railings & Posts @ Str A
B9ST-430 | Welding/Steel Insp @ Str A |  | 1 | 0 | 1 | 11-Aug-25 | 11-Aug-25 | J: -99; D: Welding/Steel Insp @ Str A
B9ST-280 | Paint Steel - 1st Coat @ Str A |  | 2 | 0 | 2 | 12-Aug-25 | 13-Aug-25 | J: -87; J: Paint Steel - 1st Coat @ Str A
B9ST-440 | DW Touc h Up @ Str A |  | 1 | 0 | 1 | 12-Aug-25 | 12-Aug-25 | J: -99; N: DW Touch Up @ Str A
B9ST-400 | Mechanical Finishes @ Str A |  | 3 | 0 | 3 | 13-Aug-25 | 15-Aug-25 | J: -99; J: Mechanical Finishes @ Str A
B9ST-1020 | Electrical Finishes @ Str A |  | 3 | 0 | 3 | 13-Aug-25 | 15-Aug-25 | J: -99; D: Electrical Finishes @ Str A
B9ST-1040 | Fire Protection Finishes @ Str A |  | 3 | 0 | 3 | 13-Aug-25 | 15-Aug-25 | J: -99; J: Fire Protection Finishes @ Str A
B9ST-420 | Inst Finish on Treads/Landings @ Str A |  | 10 | 0 | 10 | 18-Aug-25 | 29-Aug-25 | J: -99; M: Inst Finish on Treads/Landings @ Str A
B9ST-450 | Final Paint @ Str A |  | 5 | 0 | 5 | 02-Sep-25 | 08-Sep-25 | J: -99; D: Final Paint @ Str A
B9ST-460 | Final Clean @ Str A |  | 5 | 0 | 5 | 09-Sep-25 | 15-Sep-25 | J: -99; D: Final Clean @ Str A
STAIR B FINISHES |  |  | 105 | 141 | 66 | 15-Jul-24 A | 25-Sep-25 | J: -107
B9ST-910 | Inst Windows @ Str B |  | 2 | 141 | 1 | 15-Jul-24 A | 28-Jul-25 | J: -85; N: Inst Windows @ Str B
B9ST-830 | Frame Walls @ Str B |  | 8 | 0 | 8 | 24-Jun-25 | 03-Jul-25 | J: -107; O: Frame Walls @ Str B
B9ST-840 | Framing Inspection @ Str B |  | 1 | 0 | 1 | 07-Jul-25 | 07-Jul-25 | J: -107; N: Framing Inspection @ Str B
B9ST-1070 | Fireprotection Rough @ Str B |  | 3 | 0 | 3 | 07-Jul-25 | 09-Jul-25 | J: -103; N: Fireprotection Rough @ Str B
B9ST-820 | Paint Steel - 1st Coat @ Str B |  | 2 | 0 | 2 | 08-Jul-25 | 09-Jul-25 | J: -62; N: Paint Steel - 1st Coat @ Str B
B9ST-850 | MECH Rough @ Str B |  | 3 | 0 | 3 | 08-Jul-25 | 10-Jul-25 | J: -107; O: MECH Rough @ Str B
B9ST-860 | ELECT Rough @ Str B |  | 3 | 0 | 3 | 08-Jul-25 | 10-Jul-25 | J: -107; O: ELECT Rough @ Str B
B9ST-870 | MEP Inspection @ Str B |  | 1 | 0 | 1 | 11-Jul-25 | 11-Jul-25 | J: -107; N: MEP Inspection @ Str B
B9ST-880 | Insulate & Inspect @ Str B |  | 2 | 0 | 2 | 14-Jul-25 | 15-Jul-25 | J: -107; N: Insulate & Inspect @ Str B
B9ST-890 | Hang DW/Shaftwall @ Str B |  | 8 | 0 | 8 | 16-Jul-25 | 25-Jul-25 | J: -107; D: Hang DW/Shaftwall @ Str B
B9ST-900 | Finish DW @ Str B |  | 8 | 0 | 8 | 23-Jul-25 | 01-Aug-25 | J: -107; N: Finish DW @ Str B
B9ST-1090 | Inst Louvers @ Str B |  | 2 | 0 | 2 | 28-Jul-25 | 29-Jul-25 | J: -86; N: Inst Louvers @ Str B
B9ST-920 | Paint 1st Coat Walls @ Str B |  | 5 | 0 | 5 | 04-Aug-25 | 08-Aug-25 | J: -107; D: Paint 1st Coat Walls @ Str B
B9ST-930 | Inst Railings & Posts @ Str B |  | 8 | 0 | 8 | 11-Aug-25 | 20-Aug-25 | J: -107; J: Inst Railings & Posts @ Str B
B9ST-940 | Welding/Steel Insp @ Str B |  | 1 | 0 | 1 | 21-Aug-25 | 21-Aug-25 | J: -107; J: Welding/Steel Insp @ Str B
B9ST-950 | DW Touc h Up @ Str B |  | 1 | 0 | 1 | 22-Aug-25 | 22-Aug-25 | J: -107; D: DW Touch Up @ Str B
B9ST-960 | Mechanical Finishes @ Str B |  | 3 | 0 | 3 | 25-Aug-25 | 27-Aug-25 | J: -107; J: Mechanical Finishes @ Str B
B9ST-1050 | Electrical Finishes @ Str B |  | 3 | 0 | 3 | 25-Aug-25 | 27-Aug-25 | J: -107; J: Electrical Finishes @ Str B
Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 33 of 46 |  | J: TASK filter: Activity Status.
Actual Level of Effort | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  | Original | Actual | Remaining | Start | Finish | J: Total Float; J: 2025; J: 2026; M: 2027
|  |  | Duration | Duration | Duration | [30 empty] | M
[8 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
B9ST-1060 | Fire Protection Finishes @ Str B |  | 3 | 0 | 3 | 25-Aug-25 | 27-Aug-25 | J: -107; F: Fire Protection Finishes @ Str B
B9ST-970 | Inst Finish on Treads/Landings @ Str B |  | 10 | 0 | 10 | 28-Aug-25 | 11-Sep-25 | J: -107; M: Inst Finish on Treads/Landings @ Str B
B9ST-980 | Final Paint @ Str B |  | 5 | 0 | 5 | 12-Sep-25 | 18-Sep-25 | J: -107; J: Final Paint @ Str B
B9ST-990 | Final Clean @ Str B |  | 5 | 0 | 5 | 19-Sep-25 | 25-Sep-25 | J: -107; J: Final Clean @ Str B
STAIR C FINISHES |  |  | 84 | 141 | 32 | 15-Jul-24 A | 11-Aug-25 | J: -75
B9ST-690 | Inst Temp Glass @ Str C |  | 2 | 141 | 1 | 15-Jul-24 A | 11-Aug-25 | J: -75; D: Inst Te mp Glass @ Str C
B9ST-660 | Hang DW/Shaftwall @ Str C |  | 8 | 0 | 8 | 26-Jun-25 | 08-Jul-25 | J: -88; N: Hang DW/Shaftwall @ Str C
B9ST-670 | Finish DW @ Str C |  | 8 | 0 | 8 | 03-Jul-25 | 15-Jul-25 | J: -75; O: Finish DW @ Str C
B9ST-680 | Paint 1st Coat Walls @ Str C |  | 5 | 0 | 5 | 16-Jul-25 | 22-Jul-25 | J: -75; D: Paint 1st Coat Walls @ Str C
B9ST-710 | DW Touc h Up @ Str C |  | 1 | 0 | 1 | 23-Jul-25 | 23-Jul-25 | J: -73; N: DW Touch Up @ Str C
B9ST-700 | Inst Railings & Posts @ Str C |  | 8 | 0 | 8 | 23-Jul-25 | 01-Aug-25 | J: -75; D: Inst Railings & Posts @ Str C
B9ST-720 | Final Paint @ Str C |  | 5 | 0 | 5 | 24-Jul-25 | 30-Jul-25 | J: -73; O: Final Paint @ Str C
B9ST-1000 | Inst Epoxy Terrazo Finis h on Treads/Landings @ Str C |  | 5 | 0 | 5 | 04-Aug-25 | 08-Aug-25 | J: -75; A: Inst Epoxy Terrazo Finis h on Treads/Landings @ Str C
STAIR D FINISHES |  |  | 136 | 0 | 136 | 18-Feb-25 | 28-Aug-25 | J: -88
B9ST-1010 | Tooth in Masonry @ Str D |  | 5 | 0 | 5 | 18-Feb-25 | 24-Feb-25 | J: 6; J: Tooth in Masonry @ Str D
B9ST-730 | Hang DW/Shaftwall @ Str D |  | 8 | 0 | 8 | 09-Jul-25 | 18-Jul-25 | J: -88; D: Hang DW/Shaftwall @ Str D
B9ST-740 | Finish DW @ Str D |  | 8 | 0 | 8 | 16-Jul-25 | 25-Jul-25 | J: -88; O: Finish DW @ Str D
B9ST-750 | Paint 1st Coat Walls @ Str D |  | 5 | 0 | 5 | 28-Jul-25 | 01-Aug-25 | J: -88; D: Paint 1st Coat Walls @ Str D
B9ST-760 | Inst Railings & Posts @ Str D |  | 8 | 0 | 8 | 04-Aug-25 | 13-Aug-25 | J: -88; J: Inst Railings & Posts @ Str D
B9ST-780 | DW Touc h Up @ Str D |  | 1 | 0 | 1 | 14-Aug-25 | 14-Aug-25 | J: -88; D: DW Touch Up @ Str D
B9ST-770 | Inst Finish on Treads/Landings @ Str D |  | 5 | 0 | 5 | 15-Aug-25 | 21-Aug-25 | J: -88; M: Inst Finish on Treads/Landings @ Str D
B9ST-790 | Final Paint |  | 5 | 0 | 5 | 22-Aug-25 | 28-Aug-25 | J: -88; O: Final Paint
ROOF AND EXTERIOR FACADE |  |  | 338 | 141 | 239 | 15-Jul-24 A | 26-Jan-26 | J: -137
ROOF |  |  | 147 | 141 | 47 | 15-Jul-24 A | 24-Apr-25 | J: 20
B9LR-430 | Pull Feeders From Transformer to Elec Room @ Bldg 9 |  | 8 | 141 | 2 | 15-Jul-24 A | 27-Feb-25 | J: 27; N: Pull Feeders From Transformer to Elec Room @ Bldg 9
B9LR-200 | Inst Tapered Insulation |  | 5 | 79 | 3 | 26-Aug-24 A | 12-Mar-25 | J: -3; J: Inst Tapered Insulation
B9LR-180 | New Roof Drains & Vent Stack |  | 5 | 92 | 3 | 23-Sep-24 A | 28-Feb-25 | J: -3; J: New Roof Drains & Vent Stack
B9LR-140 | Clean Rpt/Clear Asbestos |  | 5 | 0 | 5 | 19-Feb-25 | 25-Feb-25 | J: -3; J: Clean Rpt/Clear Asbestos
B9LR-290 | Expansion Joint Installation |  | 3 | 0 | 3 | 26-Feb-25 | 28-Feb-25 | J: 35; J: Expansion Joint Installation
B9LR-220 | Inst Roof Membrane |  | 5 | 0 | 5 | 13-Mar-25 | 20-Mar-25 | J: -3; J: Inst Roof Membrane
B9LR-250 | Inst New Lights |  | 5 | 0 | 5 | 21-Mar-25 | 27-Mar-25 | J: -3; J: Inst New Lights
B9LR-280 | Inst Exhaust Fans |  | 5 | 0 | 5 | 21-Mar-25 | 27-Mar-25 | J: -3; J: Inst Exhaust Fans
B9LR-230 | New Perimeter Edge Flashing |  | 5 | 0 | 5 | 24-Mar-25 | 31-Mar-25 | J: 16; A: New Perimeter Edge Flashing
B9LR-210 | Inst Scuppers & Down Spouts |  | 5 | 0 | 5 | 01-Apr-25 | 08-Apr-25 | J: 16; A: Inst Scuppers & Down Spouts
B9LR-240 | Clean Out Existing Roof Drains |  | 5 | 0 | 5 | 09-Apr-25 | 16-Apr-25 | J: 16; S: Clean Out Existing Roof Drains
B9LR-260 | Inst New Roof Strainers over Scuppers |  | 5 | 0 | 5 | 17-Apr-25 | 24-Apr-25 | J: 16; O: Inst New Roof Strainers over Scuppers
EXTERIOR FACADE |  |  | 289 | 136 | 213 | 22-Jul-24 A | 17-Dec-25 | J: -111
B9LR-310 | Caulk/seal all new windows |  | 10 | 136 | 1 | 22-Jul-24 A | 18-Feb-25 | J: 43; J: Caulk/seal all new windows
B9LR-330 | Remove screen/frame & other Items to be removed |  | 4 | 0 | 4 | 04-Mar-25 | 10-Mar-25 | J: 23; O: Remove screen/frame & other Items to be removed
B9LR-420 | Patch & Infill at MEP Service Entrances |  | 10 | 0 | 10 | 06-Mar-25 | 19-Mar-25 | J: 22; S: Patch & Infill at MEP Service Entrances
B9LR-300 | Repointing of brick |  | 20 | 0 | 20 | 20-Mar-25 | 23-Apr-25 | J: 17; J: Repointing of brick
B9LR-320 | Seal mechanical & Electrical penetrations |  | 5 | 0 | 5 | 20-Aug-25 | 26-Aug-25 | J: -65; M: Seal mechanical & Electrical penetrations
B9LR-350 | Install intelligent system control & card readers |  | 5 | 0 | 5 | 19-Nov-25 | 25-Nov-25 | J: -132; J: Install intelligent system control & card readers
B9LR-360 | Install exterior signage |  | 3 | 0 | 3 | 04-Dec-25 | 08-Dec-25 | J: -137; A: Install exterior signage
B9LR-340 | Remote annunciator panel |  | 5 | 0 | 5 | 11-Dec-25 | 17-Dec-25 | J: -111; A: Remote annunciator panel
EXTERIOR PUNCHLIST BLDG 9 |  |  | 33 | 0 | 33 | 09-Dec-25 | 26-Jan-26 | J: -137
B9L3-490 | PHB - Roof & Exterior Punchlist |  | 5 | 0 | 5 | 09-Dec-25 | 15-Dec-25 | J: -137; M: PHB - Roof & Exterior Punchlist
B9L3-500 | Subcontract Punch Work -Roof & Exterior |  | 10 | 0 | 10 | 16-Dec-25 | 30-Dec-25 | J: -137; J: Subcontract Punch Work -Roof & Exterior
B9L3-510 | Phase 02 - Final Clean -Roof & Exterior |  | 5 | 0 | 5 | 31-Dec-25 | 07-Jan-26 | J: -137; J: Phase 02 - Final Clean -Roof & Exterior
Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 34 of 46 |  | J: TASK filter: Activity Status.
Actual Level of Effort | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  | Original | Actual | Remaining | Start | J: Finish; F: Total Float; J: 2025; A: 2026; A: 2027
|  |  |  | Duration | Duration | Duration | [30 empty] | M
[9 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
B9L3-520 | Owner / Architect Punch -Roof & Exterior |  |  | 5 | 0 | 5 | 08-Jan-26 | 14-Jan-26 | J: -137; J: Owner / Architect Punch -Roof & Exterior
B9L3-530 | Subs Complete Owner/AE Punch -Roof & Exterior |  |  | 8 | 0 | 8 | 15-Jan-26 | 26-Jan-26 | J: -137; S: Subs Complete Owner/AE Punch -Roof & Exterior
| BLDG 9 START UP/TEST/COMMISSION PH2 |  |  | 243 | 243 | 186 | 20-Feb-24 A | 12-Mar-26 | J: -170
B9TRN-110 | Switchgear / Piping & Wire |  |  | 20 | 243 | 16 | 20-Feb-24 A | 05-Dec-25 | J: -170; A: Switchgear / Piping & Wire
B9TRN-300 | Submit Conrols Testing Plan |  |  | 5 | 0 | 5 | 19-Jun-25 | 25-Jun-25 | J: -28; N: Submit Conrols Testing Plan
B9TRN-310 | Controls Test ing |  |  | 5 | 0 | 5 | 01-Jul-25 | 08-Jul-25 | J: -31; O: Controls Test ing
B9TRN-100 | Plumbing Systems Tie In & Test |  |  | 20 | 0 | 20 | 20-Oct-25 | 14-Nov-25 | J: -123; A: Plumbing Systems Tie In & Test
B9TRN-230 | Inst Elevator |  |  | 30 | 0 | 30 | 13-Nov-25 | 26-Dec-25 | J: -122; M: Inst Elevator
B9TRN-140 | Mechanical Systems Tie-In & Test |  |  | 20 | 0 | 20 | 14-Nov-25 | 12-Dec-25 | J: -165; M: Mechanical Systems Tie-In & Test
B9TRN-130 | Electrical Systems Tie In & Test Fire Alarm |  |  | 20 | 0 | 20 | 19-Nov-25 | 17-Dec-25 | J: -168; J: Electrical Systems Tie In & Test Fire Alarm
B9TRN-150 | Sprinkler System Tie In & Test |  |  | 15 | 0 | 15 | 04-Dec-25 | 24-Dec-25 | J: -137; M: Sprinkler System Tie In & Test
B9TRN-120 | Start Up & Test Equipment |  |  | 20 | 0 | 20 | 08-Dec-25 | 06-Jan-26 | J: -170; M: Start Up & Test Equipment
B9TRN-360 | HVAC Commissioning |  |  | 15 | 0 | 15 | 18-Dec-25 | 09-Jan-26 | J: -145; M: HVAC Commissioning
B9TRN-240 | Start Up and Test Elevator |  |  | 5 | 0 | 5 | 29-Dec-25 | 05-Jan-26 | J: -122; M: Start Up and Test Elevator
B9TRN-200 | Phase - 02 Commissioning Electrical |  |  | 20 | 0 | 20 | 31-Dec-25 | 28-Jan-26 | J: -170; J: Phase - 02 Commissioning Electrical
B9TRN-180 | Balance / Test HVAC Systems |  |  | 20 | 0 | 20 | 31-Dec-25 | 28-Jan-26 | J: -170; J: Balance / Test HVAC Systems
B9TRN-320 | Air & Water Balancing |  |  | 10 | 0 | 10 | 29-Jan-26 | 11-Feb-26 | J: -170; M: Air & Water Balancing
B9TRN-390 | Performance Verification Testing |  |  | 10 | 0 | 10 | 12-Feb-26 | 25-Feb-26 | J: -168; J: Performance Verification Testing
B9TRN-460 | Government Furniture/IT Installation @ Bldg 9 |  |  | 5 | 0 | 5 | 12-Feb-26 | 16-Feb-26 | J: -245; S: Government Furniture/IT Installation @ Bldg 9
| CLEAN / PUNCH 1ST FLOOR |  |  | 75 | 0 | 75 | 25-Nov-25 | 12-Mar-26 | J: -170
B9L1-800 | Rough Clean Lvl 1 |  |  | 3 | 0 | 3 | 25-Nov-25 | 28-Nov-25 | J: -149; M: Rough Clean Lvl 1
B9L1-810 | PHB 1STFloor Punchlist |  |  | 5 | 0 | 5 | 03-Dec-25 | 09-Dec-25 | J: -133; A: PHB 1STFloor Punchlist
B9L1-820 | Subcontract Punch Work -Lvl 1 |  |  | 10 | 0 | 10 | 10-Dec-25 | 23-Dec-25 | J: -133; M: Subcontract Punch Work -Lvl 1
B9L1-830 | Phase 02 - Final Clean -1 Lvl |  |  | 5 | 0 | 5 | 17-Feb-26 | 23-Feb-26 | J: -170; J: Phase 02 - Final Clean -1 Lvl
B9L1-840 | Owner / Architect Punch -Lvl 1 |  |  | 5 | 0 | 5 | 24-Feb-26 | 02-Mar-26 | J: -170; J: Owner / Architect Punch -Lvl 1
B9L1-850 | Subs Complete Owner/AE Punch -Lvl 1 |  |  | 8 | 0 | 8 | 03-Mar-26 | 12-Mar-26 | J: -170; S: Subs Complete Owner/AE Punch -Lvl 1
| CLEAN / PUNCH GROUND FLOOR |  |  | 85 | 0 | 85 | 11-Nov-25 | 12-Mar-26 | J: -170
B9LG-1010 | Rough Clean Lvl G |  |  | 3 | 0 | 3 | 11-Nov-25 | 13-Nov-25 | J: -139; F: Rough Clean Lvl G
B9LG-1060 | PHB Lvl-G Floor Punchlist |  |  | 5 | 0 | 5 | 20-Nov-25 | 26-Nov-25 | J: -125; A: PHB Lvl-G Floor Punchlist
B9LG-1070 | Subcontract Punch Work -Lvl G |  |  | 10 | 0 | 10 | 28-Nov-25 | 11-Dec-25 | J: -125; M: Subcontract Punch Work -Lvl G
B9LG-1080 | Phase 02 - Final Clean -G Lvl |  |  | 5 | 0 | 5 | 17-Feb-26 | 23-Feb-26 | J: -170; J: Phase 02 - Final Clean -G Lvl
B9LG-1090 | Owner / Architect Punch -Lvl G |  |  | 5 | 0 | 5 | 24-Feb-26 | 02-Mar-26 | J: -170; J: Owner / Architect Punch -Lvl G
B9LG-1100 | Subs Complete Owner/AE Punch -Lvl G |  |  | 8 | 0 | 8 | 03-Mar-26 | 12-Mar-26 | J: -170; S: Subs Complete Owner/AE Punch -Lvl G
| CLEAN / PUNCH 2ND FLOOR |  |  | 55 | 0 | 55 | 24-Dec-25 | 12-Mar-26 | J: -170
B9L2-810 | Rough Clean Lvl 2 |  |  | 3 | 0 | 3 | 24-Dec-25 | 29-Dec-25 | J: -169; A: Rough Clean Lvl 2
B9L2-820 | PHB Lvl 2 Floor Punchlist |  |  | 5 | 0 | 5 | 30-Dec-25 | 06-Jan-26 | J: -151; M: PHB Lvl 2 Floor Punchlist
B9L2-830 | Subcontract Punch Work -Lvl 2 |  |  | 10 | 0 | 10 | 07-Jan-26 | 20-Jan-26 | J: -151; J: Subcontract Punch Work -Lvl 2
B9L2-840 | Phase 02 - Final Clean -Lvl 2 |  |  | 5 | 0 | 5 | 17-Feb-26 | 23-Feb-26 | J: -170; J: Phase 02 - Final Clean -Lvl 2
B9L2-850 | Owner / Architect Punch -Lvl 2 |  |  | 5 | 0 | 5 | 24-Feb-26 | 02-Mar-26 | J: -170; J: Owner / Architect Punch -Lvl 2
B9L2-860 | Subs Complete Owner/AE Punch -Lvl 2 |  |  | 8 | 0 | 8 | 03-Mar-26 | 12-Mar-26 | J: -170; S: Subs Complete Owner/AE Punch -Lvl 2
| CLEAN / PUNCH PENTHOUSE |  |  | 36 | 0 | 36 | 19-Sep-25 | 07-Nov-25 | J: -84
B9L3-340 | Rough Clean Lvl 3 |  |  | 3 | 0 | 3 | 19-Sep-25 | 23-Sep-25 | J: -102; D: Rough Clean Lvl 3
B9L3-350 | PHB - Floor Punchlist Lvl 3 |  |  | 5 | 0 | 5 | 24-Sep-25 | 30-Sep-25 | J: -84; F: PHB - Floor Punchlist Lvl 3
B9L3-360 | Subcontract Punch Work -Lvl 3 |  |  | 10 | 0 | 10 | 01-Oct-25 | 14-Oct-25 | J: -84; M: Subcontract Punch Work -Lvl 3
B9L3-370 | Phase 02 - Final Clean -3 Lvl |  |  | 5 | 0 | 5 | 15-Oct-25 | 21-Oct-25 | J: -84; M: Phase 02 - Final Clean -3 Lvl
B9L3-380 | Owner / Architect Punch -Lvl 3 |  |  | 5 | 0 | 5 | 22-Oct-25 | 28-Oct-25 | J: -84; A: Owner / Architect Punch -Lvl 3
B9L3-390 | Subs Complete Owner/AE Punch -Lvl 3 |  |  | 8 | 0 | 8 | 29-Oct-25 | 07-Nov-25 | J: -84; M: Subs Complete Owner/AE Punch -Lvl 3
| BLDG 9 COMMISSION / TURNOVER |  |  | 65 | 0 | 65 | 19-Jan-26 | 18-Apr-26 | J: -108
B9TRN-250 | Red Zone Meeting |  |  | 60 | 0 | 60 | 19-Jan-26 | 20-Mar-26 | J: -126; J: Red Zone Meeting
| Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 35 of 46 |  | J: TASK filter: Activity Status.
| Actual Level of Effort | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  |  | Original | Actual | Remaining | Start | J: Finish; F: Total Float; J: 2025; J: 2026; A: 2027
[5 empty] | Duration | Duration | Duration | [30 empty] | M
[10 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
B9TRN-170 | CORP 30 Day Notice of Turnover |  |  |  | 30 | 0 | 30 | 11-Feb-26 | 13-Mar-26 | J: -119; A: CORP 30 Day Notice of Turnover
B9TRN-190 | Phase - 02 Commissioning |  |  |  | 20 | 0 | 20 | 18-Feb-26 | 17-Mar-26 | J: -168; J: Phase - 02 Commissioning
B9TRN-400 | SUBSTANTIAL COMPLETION |  |  |  | 0 | 0 | 0 |  | 02-Mar-26 | J: -162; J: SUBSTANTIAL COMPLETION
B9TRN-440 | Final Inspections |  |  |  | 5 | 0 | 5 | 13-Mar-26 | 19-Mar-26 | J: -170; J: Final Inspections
B9TRN-450 | READY FOR OCCUPANCY - BLDG 9 |  |  |  | 0 | 0 | 0 |  | 19-Mar-26 | J: -170; S: READY FOR OCCUPANCY - BLDG 9
B9TRN-220 | Owner Move To Bldg 9 |  |  |  | 30 | 0 | 30 | 20-Mar-26 | 18-Apr-26 | J: -243; A: Owner Move To Bldg 9
PHASE-2: BUILDING 3 |  |  |  |  | 385 | 202 | 332 | 17-Apr-24 A | 20-May-26 | J: -131
BLDG 3 GROUND FLOOR |  |  |  |  | 272 | 82 | 219 | 07-Oct-24 A | 10-Dec-25 | J: -59
FOOTINGS/STRUCTURE GND TO 1ST |  |  |  |  | 63 | 82 | 10 | 07-Oct-24 A | 14-Feb-25 | J: 120
B3LG-230 |  | Inst Steel @ Underside 1st Fl Openings Lvl G |  |  | 15 | 82 | 2 | 07-Oct-24 A | 04-Feb-25 | J: -94; S: Inst Steel @ Underside 1st Fl Openings Lvl G
NEW ELEVATOR |  |  |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: 120
B3LG-710 | Waterproof Membr ane |  |  |  | 4 | 0 | 4 | 03-Feb-25 | 06-Feb-25 | J: 126; M: Waterpro of Me mbr ane
B3LG-720 |  | Inst Shaft Walls From Ground to 1st Fl @ Eleva tor |  |  | 7 | 0 | 7 | 03-Feb-25 | 11-Feb-25 | J: -99; O: Inst Shaft Walls From Ground to 1st Fl @ Ele vator
B3LG-730 | Inst Pit Ladder and Sump Cover |  |  |  | 3 | 0 | 3 | 12-Feb-25 | 14-Feb-25 | J: 120; J: Inst Pit Ladder and Sump Cover
ROUGH IN LVL G |  |  |  |  | 137 | 82 | 89 | 07-Oct-24 A | 06-Jun-25 | J: 51
B3LG-240 | Layout/Top Track | Lvl G |  |  | 8 | 82 | 1 | 07-Oct-24 A | 03-Feb-25 | J: -127; A: Layout/Top Track; S: Lvl G
B3LG-410 | Metal Framing @ Rooms | Lvl G |  |  | 23 | 77 | 22 | 14-Oct-24 A | 25-Apr-25 | J: -127; A: Metal Framing @ Rooms; J: Lvl G
B3LG-2403 | Metal Framing @ Exterior Walls | Lv l G |  |  | 5 | 42 | 1 | 03-Dec-24 A | 03-Feb-25 | J: -68; J: Metal Framing @ Exterior Walls; D: Lv l G
B3LG-560 | Spray Foam Insulation | Lvl G |  |  | 10 | 32 | 7 | 17-Dec-24 A | 06-May-25 | J: -127; A: Spray Foam Insulation; J: Lvl G
B3LG-340 | Ductwork OH Rough In | Lvl G |  |  | 25 | 10 | 15 | 20-Jan-25 A | 24-Feb-25 | J: -127; J: Ductwork OH Rough In; N: Lvl G
B3LG-288 | Security OH Conduits | Lvl G |  |  | 10 | 0 | 10 | 03-Feb-25 | 14-Feb-25 | J: -106; J: Security OH Conduits; O: Lvl G
B3LG-350 | Mechanical Equipment | Lvl G |  |  | 30 | 0 | 30 | 04-Feb-25 | 17-Mar-25 | J: -97; J: Mechanical Equipment; N: Lvl G
B3LG-360 | HVAC Pipe OH Rough In | Lvl G |  |  | 25 | 0 | 25 | 04-Feb-25 | 10-Mar-25 | J: -127; J: HVAC Pipe OH Rough In; D: Lvl G
B3LG-370 | Plumbing OH Rough In | Lvl G |  |  | 30 | 0 | 30 | 04-Feb-25 | 17-Mar-25 | J: -127; J: Plumbing OH Rough In; D: Lvl G
B3LG-380 | Controls OH Rough In | Lvl G |  |  | 30 | 0 | 30 | 04-Feb-25 | 17-Mar-25 | J: -127; J: Controls OH Rough In; N: Lvl G
B3LG-390 | Electrical OH Rough In | Lvl G |  |  | 25 | 0 | 25 | 11-Feb-25 | 17-Mar-25 | J: -127; J: Electrical OH Rough In; D: Lvl G
B3LG-400 | Fire Protection OH Rough In | Lvl G |  |  | 20 | 0 | 20 | 11-Feb-25 | 10-Mar-25 | J: -122; J: Fire Protection OH Rough In; D: Lvl G
B3LG-292 | Cable Tray Lvl G |  |  |  | 10 | 0 | 10 | 11-Feb-25 | 24-Feb-25 | J: -105; M: Cable Tray Lvl G
B3LG-330 |  | Metal Framing @ Corridors + Top 4'0 DW | Lv l G |  | 7 | 0 | 7 | 18-Mar-25 | 26-Mar-25 | J: -127; O: Metal Framing @ Corridors + Top 4'0 DW; M: Lv l G
B3LG-510 | OH Mechanical Test/Inspections Lvl G |  |  |  | 3 | 0 | 3 | 18-Mar-25 | 20-Mar-25 | J: -97; O: OH Mechanical Test/Inspections Lvl G
B3LG-282 | Electrical Power Conduits Lvl G |  |  |  | 15 | 0 | 15 | 18-Mar-25 | 07-Apr-25 | J: -122; S: Electrical Power Conduits Lvl G
B3LG-458 | Pull Data & Security | Lvl G |  |  | 10 | 0 | 10 | 19-Mar-25 | 01-Apr-25 | J: -45; J: Pull Data & Security; N: Lvl G
B3LG-610 | Insulate OH Mechanical Piping w/Duct |  | Lvl G |  | 15 | 0 | 15 | 21-Mar-25 | 10-Apr-25 | J: -97; O: Insulate OH Mechanical Piping w/Duct; M: Lvl G
B3LG-2133 | Install Door Frames | Lvl G |  |  | 10 | 0 | 10 | 27-Mar-25 | 09-Apr-25 | J: 24; J: Install Door Frames; N: Lvl G
B3LG-2123 | Install Blocking @ Rooms | Lvl G |  |  | 12 | 0 | 12 | 27-Mar-25 | 11-Apr-25 | J: -110; A: Install Blocking @ Rooms; J: Lvl G
B3LG-440 | In Wall Mechanical / Contr ols Rou gh In |  | Lv l G |  | 15 | 0 | 15 | 27-Mar-25 | 16-Apr-25 | J: -104; O: In Wall Mechanical / Contr ols Rough In; M: Lv l G
B3LG-450 | In Wall Plumbing Rough In | Lv l G |  |  | 15 | 0 | 15 | 27-Mar-25 | 16-Apr-25 | J: -116; A: In Wall Plumbing Rough In; J: Lv l G
B3LG-460 | In Wall Electrical Rough In | Lv l G |  |  | 15 | 0 | 15 | 27-Mar-25 | 16-Apr-25 | J: -117; A: In Wall Electrical Rough In; J: Lv l G
B3LG-342 | Distribution Panels Install | Lvl G |  |  | 15 | 0 | 15 | 27-Mar-25 | 16-Apr-25 | J: -117; A: Distribution Panels Install; J: Lvl G
B3LG-344 | Power In Wall Branc h | Lv l G |  |  | 15 | 0 | 15 | 27-Mar-25 | 16-Apr-25 | J: -127; J: Power In Wall Branc h; D: Lv l G
B3LG-564 | Terminate Security | Lvl G |  |  | 10 | 0 | 10 | 02-Apr-25 | 15-Apr-25 | J: 0; J: Terminate Security; N: Lvl G
B3LG-346 | Lighting In Wall Branch | L vl G |  |  | 15 | 0 | 15 | 03-Apr-25 | 23-Apr-25 | J: -127; A: Lighting In Wall Bran ch; D: L vl G
B3LG-284 | Lighting Conduits | Lvl G |  |  | 15 | 0 | 15 | 08-Apr-25 | 28-Apr-25 | J: -122; J: Lighting Conduits; N: Lvl G
B3LG-348 | Fire Alarm In Wall Conduits | Lvl G |  |  | 15 | 0 | 15 | 10-Apr-25 | 30-Apr-25 | J: -127; S: Fire Alarm In Wall Conduits; F: Lvl G
B3LG-352 | Security In Wall Conduits | Lvl G |  |  | 15 | 0 | 15 | 10-Apr-25 | 30-Apr-25 | J: -127; S: Security In Wall Conduits; J: L vl G
B3LG-354 | Data In Wall C ondu its | Lv l G |  |  | 15 | 0 | 15 | 10-Apr-25 | 30-Apr-25 | J: -127; A: Data In Wall C onduits; D: Lv l G
B3LG-580 | Plumbing Testing & Insp ection | Lvl G |  |  | 3 | 0 | 3 | 17-Apr-25 | 21-Apr-25 | J: -116; S: Plumbing Testing & Inspection; M: Lvl G
B3LG-570 | Pull Control Wire to Devices- | Lvl G |  |  | 15 | 0 | 15 | 17-Apr-25 | 07-May-25 | J: 44; O: Pull Control Wire to Devices-; M: Lvl G
Remaining Level of Effort |  | Actual Work |  | Critical Remaining Work |  |  |  | Page 36 of 46 |  | J: TASK filter: Activity Status.
Actual Level of Effort |  | Remaining Work |  | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  |  |  | Original | Actual | Remaining | Start | J: Finish; F: Total Float; J: 2025; A: 2026; A: 2027
[6 empty] | Duration | Duration | Duration | [30 empty] | M
[11 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
B3LG-2213 |  | In Wall Mechanical Test/Inspections Lvl G |  |  |  | 3 | 0 | 3 | 17-Apr-25 | 21-Apr-25 | J: -104; N: In Wall Mechanical Test/Inspections Lvl G
B3LG-630 | Insulate Plumbing Piping | Lvl G |  |  |  | 12 | 0 | 12 | 22-Apr-25 | 07-May-25 | J: -116; A: Insulate Plumbing Piping; F: Lvl G
B3LG-2223 | Test and Balance Lvl G |  |  |  |  | 2 | 0 | 2 | 22-Apr-25 | 23-Apr-25 | J: 82; J: Test and Balance; N: Lvl G
B3LG-520 | Frame Soffits & Ceilings | Lvl G |  |  |  | 10 | 0 | 10 | 28-Apr-25 | 09-May-25 | J: -118; A: Frame Soffits & Ceilings; F: Lvl G
B3LG-2203 | VIF Millwork | Lvl G |  |  |  | 2 | 0 | 2 | 28-Apr-25 | 29-Apr-25 | J: -25; J: VIF Millwork; O: Lvl G
B3LG-286 | Fire Alarm Conduits Lvl G |  |  |  |  | 15 | 0 | 15 | 29-Apr-25 | 19-May-25 | J: -89; S: Fire Alarm Conduits Lvl G
B3LG-600 | Inspect In-Wall Electric al | Lvl G |  |  |  | 3 | 0 | 3 | 01-May-25 | 05-May-25 | J: -127; A: Inspect In-Wall Electric al; F: Lvl G
B3LG-452 |  | Pull & Terminate Br anch W ire | Lvl G |  |  | 10 | 0 | 10 | 06-May-25 | 19-May-25 | J: -127; O: Pull & Terminate Br anch W ire; A: Lvl G
B3LG-454 |  | Pull & Terminate Br anch Lighting | Lvl G |  |  | 10 | 0 | 10 | 06-May-25 | 19-May-25 | J: -127; O: Pull & Terminate Br anch Lighting; M: Lvl G
B3LG-680 | Terminate Controls - | Lvl G |  |  |  | 10 | 0 | 10 | 08-May-25 | 21-May-25 | J: 44; A: Terminate Controls -; J: Lvl G
B3LG-530 |  | Seal Penetrations Thru Fire Wall /Floors |  | Lvl G |  | 5 | 0 | 5 | 16-May-25 | 22-May-25 | J: -127; N: Seal Penetrations Thru Fire Wall /Floors; J: Lvl G
B3LG-590 | OH Electrical Inspections - |  | Lvl G |  |  | 3 | 0 | 3 | 20-May-25 | 22-May-25 | J: -127; S: OH Electrical Inspections -; M: Lvl G
B3LG-456 | Pull Fire Alarm | Lvl G |  |  |  | 10 | 0 | 10 | 20-May-25 | 03-Jun-25 | J: -89; A: Pull Fire Alarm; D: Lvl G
B3LG-690 | OH Inspection - | Lvl G |  |  |  | 0 | 0 | 0 |  | 22-May-25 | J: -127; A: OH Inspection -; D: Lvl G
B3LG-620 |  | Pull & Terminate Electrical Wires- | Lvl G |  |  | 10 | 0 | 10 | 23-May-25 | 06-Jun-25 | J: -37; N: Pull & Terminate Electrical Wires-; J: Lvl G
FINISH LVL G | [5 empty] | 152 | 0 | 152 | 07-May-25 | 10-Dec-25 | J: -59
B3LG-540 | Gypsum Board Walls | Lvl G |  |  |  | 20 | 0 | 20 | 07-May-25 | 04-Jun-25 | J: -127; S: Gypsum Board Walls; F: Lvl G
B3LG-670 | Tape and Finish Walls | Lvl G |  |  |  | 25 | 0 | 25 | 14-May-25 | 18-Jun-25 | J: -100; O: Tape and Finish Walls; M: Lvl G
B3LG-2243 |  | Install Fire-Retardant Plywood for Telec om Room |  |  | Lvl G | 5 | 0 | 5 | 14-May-25 | 20-May-25 | J: -100; J: Install Fire-Retardant Plywood for Telec om Room; S: Lvl G
B3LG-2253 |  | Install Wire Mesh Partitions for Telec om Room Lvl G |  |  |  | 5 | 0 | 5 | 21-May-25 | 28-May-25 | J: -100; F: Install Wire Mesh Partitions for Telec om Room Lvl G
B3LG-700 |  | Gypsum Board Soffits & Ceilings | Lvl G |  |  | 15 | 0 | 15 | 23-May-25 | 13-Jun-25 | J: -127; N: Gypsum Board Soffits & Ceilings; M: Lvl G
B3LG-740 |  | Tape and Finish Soffit s & C eilings | Lvl G |  |  | 20 | 0 | 20 | 02-Jun-25 | 27-Jun-25 | J: -107; D: Tape and Finish Soffit s & C eilings; J: Lvl G
B3LG-566 | Terminate Fire Alarm | Lvl G |  |  |  | 10 | 0 | 10 | 04-Jun-25 | 17-Jun-25 | J: -44; S: Terminate Fire Alarm; F: Lvl G
B3LG-780 | Prime Paint & 1st Coat | Lvl G |  |  |  | 15 | 0 | 15 | 09-Jun-25 | 27-Jun-25 | J: -107; O: Prime Paint & 1st Coat; M: Lvl G
B3LG-562 | Install & Ter minate WAP | Lvl G |  |  |  | 10 | 0 | 10 | 09-Jun-25 | 20-Jun-25 | J: -37; O: Install & Ter minate WAP; M: Lvl G
B3LG-800 | ACT Ceiling Grid Lvl G |  |  |  |  | 20 | 0 | 20 | 30-Jun-25 | 28-Jul-25 | J: -107; O: ACT Ceiling Grid; F: Lvl G
B3LG-930 | Electrical Wall F inis hes | Lv l G |  |  |  | 10 | 0 | 10 | 30-Jun-25 | 14-Jul-25 | J: -85; N: Electrical Wall F inis hes; A: Lv l G
B3LG-652 | Fire Alarm Devices | Lvl G |  |  |  | 10 | 0 | 10 | 30-Jun-25 | 14-Jul-25 | J: -52; O: Fire Alarm Devices; M: Lvl G
B3LG-654 | Security Devices | Lvl G |  |  |  | 10 | 0 | 10 | 30-Jun-25 | 14-Jul-25 | J: -52; O: Security Devices; F: Lvl G
B3LG-656 | Data Devices | Lvl G |  |  |  | 10 | 0 | 10 | 30-Jun-25 | 14-Jul-25 | J: 18; S: Data Devices; J: Lvl G
B3LG-784 | Install Security Doors | Lvl G |  |  |  | 10 | 0 | 10 | 30-Jun-25 | 14-Jul-25 | J: -32; N: Install Security Doors; M: Lvl G
B3LG-830 | Mech OH Ceiling Finishes |  | Lvl G |  |  | 20 | 0 | 20 | 15-Jul-25 | 11-Aug-25 | J: -107; D: Mech OH Ceiling Finishes; J: Lvl G
B3LG-840 | Electrical Ceiling Finishes |  | Lvl G |  |  | 20 | 0 | 20 | 15-Jul-25 | 11-Aug-25 | J: -107; D: Electrical Ceiling Finishes; M: Lvl G
B3LG-2263 | Install Lockers | Lvl G |  |  |  | 3 | 0 | 3 | 15-Jul-25 | 17-Jul-25 | J: -85; O: Install Lockers; J: Lvl G
B3LG-2273 | Patient Lift Systems | Lvl G |  |  |  | 5 | 0 | 5 | 18-Jul-25 | 24-Jul-25 | J: -85; N: Patient Lift Systems; M: Lvl G
B3LG-850 |  | Fire Protection Ceiling Finishes | Lvl G |  |  | 10 | 0 | 10 | 29-Jul-25 | 11-Aug-25 | J: -107; J: Fire Protection Ceiling Finishes; J: Lvl G
B3LG-880 | Ceramic Tile | Lvl G |  |  |  | 10 | 0 | 10 | 12-Aug-25 | 25-Aug-25 | J: -107; N: Ceramic Tile; F: Lvl G
B3LG-890 |  | Mill Work & Countertops Lvl G |  |  |  | 15 | 0 | 15 | 26-Aug-25 | 16-Sep-25 | J: -107; F: Mill Work & Countertops Lvl G
B3LG-900 | Doors and Hardware | Lvl G |  |  |  | 20 | 0 | 20 | 26-Aug-25 | 23-Sep-25 | J: -82; J: Doors and Hardware; J: Lvl G
B3LG-940 | Wall and Co rner Protection |  | Lvl G |  |  | 10 | 0 | 10 | 17-Sep-25 | 30-Sep-25 | J: -87; F: Wall and Corner Protection; J: Lvl G
B3LG-920 | Plumbing Finishes Lvl G |  |  |  |  | 10 | 0 | 10 | 17-Sep-25 | 30-Sep-25 | J: -107; F: Plumbing Finishes Lvl G
B3LG-1000 | Ceiling Tiles | Lvl G |  |  |  | 10 | 0 | 10 | 01-Oct-25 | 14-Oct-25 | J: -107; D: Ceiling Tiles; A: Lvl G
B3LG-2283 |  | Patch Ceiling Inside Pool Area | Lvl G |  |  | 10 | 0 | 10 | 15-Oct-25 | 28-Oct-25 | J: -29; M: Patch Ceiling Inside Pool Area; S: Lvl G
B3LG-2293 |  | Install Cubicle Curtains Lvl G |  |  |  | 15 | 0 | 15 | 15-Oct-25 | 04-Nov-25 | J: -79; M: Install Cubicle Curtains; J: Lvl G
B3LG-2303 |  | Patch Floor Transitions to Tunnels Lvl G |  |  |  | 5 | 0 | 5 | 15-Oct-25 | 21-Oct-25 | J: -87; M: Patch Floor Transitions to Tunnels Lvl G
B3LG-2313 |  | Prep/Patch Floors for Flooring Install Lvl G |  |  |  | 10 | 0 | 10 | 15-Oct-25 | 28-Oct-25 | J: -107; M: Prep/Patch Floors for Flooring Install Lvl G
B3LG-2383 | Install Tile Flooring | Lvl G |  |  |  | 15 | 0 | 15 | 29-Oct-25 | 18-Nov-25 | J: -107; F: Install Tile Flooring; J: Lvl G
B3LG-2373 | Composite Flooring | Lvl G |  |  |  | 15 | 0 | 15 | 29-Oct-25 | 18-Nov-25 | J: -107; M: Composite Flooring; J: Lvl G
| Remaining Level of Effort | Actual Work |  |  | Critical Remaining Work |  |  |  | Page 37 of 46 |  | J: TASK filter: Activity Status.
| Actual Level of Effort |  | Remaining Work |  | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  |  | Original | Actual | Remaining | Start | Finish | Total Float | M: 2025; M: 2026; F: 2027
[5 empty] | Duration | Duration | Duration | bar: A
[10 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
B3LG-1050 | Carpet/VCT | Lvl G |  |  | 15 | 0 | 15 | 29-Oct-25 | 18-Nov-25 | J: -107; F: Carpet/VCT; A: Lvl G
B3LG-910 | Final Paint | Lvl G |  |  | 10 | 0 | 10 | 19-Nov-25 | 03-Dec-25 | J: -107; F: Final Paint; A: Lvl G
B3LG-2393 |  | Install Kitchen Equipment Lvl G |  |  | 2 | 0 | 2 | 02-Dec-25 | 03-Dec-25 | J: -99; A: Install Kitchen Equipment Lvl G
B3LG-1430 | Toilet Accessories |  |  |  | 4 | 0 | 4 | 02-Dec-25 | 05-Dec-25 | J: -104; F: Toilet Accessories
B3LG-2343 | Window Shades Lvl G |  |  |  | 4 | 0 | 4 | 02-Dec-25 | 05-Dec-25 | J: -101; M: Window Shades Lvl G
B3LG-950 | Signage | Lvl G |  |  | 5 | 0 | 5 | 04-Dec-25 | 10-Dec-25 | J: -87; F: Signage; A: Lvl G
B3LG-320 | Replace Glazing GND Fl |  |  |  | 5 | 0 | 5 | 04-Dec-25 | 10-Dec-25 | J: -107; M: Replace Glazing GND Fl
B3LG-2233 | Interior Windows/Film | Lvl G |  |  | 5 | 0 | 5 | 04-Dec-25 | 10-Dec-25 | J: -87; M: Interior Windows/Film; A: Lvl G
B3LG-2323 | Install Mirrors |  |  |  | 2 | 0 | 2 | 08-Dec-25 | 09-Dec-25 | J: -103; F: Install Mirrors
B3LG-2333 |  | Install Fire Extinguisher Cabinets |  |  | 3 | 0 | 3 | 08-Dec-25 | 10-Dec-25 | J: -104; M: Install Fire Extinguisher Cabinets
BLDG 3 1ST FLOOR |  |  |  |  | 283 | 202 | 250 | 17-Apr-24 A | 26-Jan-26 | J: -110
| GENERAL FLOOR ABAT EMENT /DEMO |  |  |  | 49 | 52 | 17 | 18-Nov-24 A | 25-Feb-25 | J: 95
B3L1-120 |  | Sawcut Floor & Rmv Fl @ 1st Floor |  |  | 5 | 52 | 4 | 18-Nov-24 A | 17-Feb-25 | J: -99; A: Sawcut Floor & Rmv Fl @ 1st Floor
B3L1-150 |  | Inst Steel @ Underside of Fl 2 @ New Openings |  |  | 15 | 49 | 1 | 21-Nov-24 A | 18-Feb-25 | J: -75; S: Inst Steel @ Underside of Fl 2 @ New Openings
B3L1-2193 |  | Sawcut/Seal Conduits in Floor Slab |  |  | 7 | 42 | 3 | 03-Dec-24 A | 05-Feb-25 | J: -91; J: Sawcut/Seal Conduits in Floor Slab
B3L1-2173 |  | Demo Exterior Roof Landings |  |  | 5 | 0 | 5 | 19-Feb-25 | 25-Feb-25 | J: 95; J: Demo Exterior Roof Landings
STRUCTURE 1ST TO 2ND |  |  |  |  | 10 | 0 | 10 | 18-Feb-25 | 03-Mar-25 | J: -84
B3L1-900 |  | Install Shaft Walls @ Elev Hoistway 1s t to 2nd |  |  | 10 | 0 | 10 | 18-Feb-25 | 03-Mar-25 | J: -84; S: Install Shaft Walls @ Elev Hoistway 1s t to 2nd
B3L1-930 |  | Infill Concrete @ Lvl 1 Floor |  |  | 5 | 0 | 5 | 18-Feb-25 | 24-Feb-25 | J: -99; J: Infill Concrete @ Lvl 1 Floor
ROUGH IN LVL 1 |  |  |  |  | 133 | 202 | 100 | 17-Apr-24 A | 23-Jun-25 | J: 40
B3L1-342 |  | Distribution Panels Install | 1-1 |  | 15 | 202 | 7 | 17-Apr-24 A | 08-May-25 | J: -118; A: Distribution Panels Install; F: 1-1
B3L1-160 | Layout/Top Track Lvl 1 |  |  |  | 8 | 72 | 3 | 21-Oct-24 A | 05-Feb-25 | J: -131; M: Layout/Top Track; A: Lvl 1
B3L1-2343 |  | Metal Framing @ Exterior Walls | 1-1 |  | 5 | 38 | 1 | 09-Dec-24 A | 06-Feb-25 | J: -54; J: Metal Framing @ Exterior Walls; D: 1-1
B3L1-170 | Fireproofing | Lvl 1 |  |  | 5 | 0 | 5 | 03-Feb-25 | 07-Feb-25 | J: -133; A: Fireproofing; J: Lvl 1
B3L1-230 | Ductwork OH Rough In | 1-1 |  |  | 25 | 0 | 25 | 10-Feb-25 | 14-Mar-25 | J: -133; J: Ductwork OH Rough In; N: 1-1
B3L1-240 | Mechanical Equipment | 1-1 |  |  | 30 | 0 | 30 | 17-Feb-25 | 28-Mar-25 | J: -91; J: Mechanical Equipment; N: 1-1
B3L1-250 | HVAC Pipe OH Rough In |  | 1-1 |  | 25 | 0 | 25 | 17-Feb-25 | 21-Mar-25 | J: -133; J: HVAC Pipe OH Rough In; D: 1-1
B3L1-280 | Electrical OH Rough In | 1-1 |  |  | 20 | 0 | 20 | 24-Feb-25 | 21-Mar-25 | J: -118; J: Electrical OH Rough In; N: 1-1
B3L1-290 |  | Fire Protection OH Rough In | 1-1 |  | 15 | 0 | 15 | 24-Feb-25 | 14-Mar-25 | J: -113; A: Fire Protection OH Rough In; J: 1-1
B3L1-260 | Plumbing OH Rough In | 1-1 |  |  | 25 | 0 | 25 | 03-Mar-25 | 04-Apr-25 | J: -128; A: Plumbing OH Rough In; D: 1-1
B3L1-270 | Controls OH Rough In | 1-1 |  |  | 25 | 0 | 25 | 10-Mar-25 | 11-Apr-25 | J: -133; A: Controls OH Rough In; D: 1-1
B3L1-340 |  | OH FP Test/Inspections - | 1-1 |  | 5 | 0 | 5 | 17-Mar-25 | 21-Mar-25 | J: -68; A: OH FP Test/Inspections -; D: 1-1
B3L1-282 |  | Electrical Power Conduits | 1-1 |  | 15 | 0 | 15 | 24-Mar-25 | 11-Apr-25 | J: -111; A: Electrical Power Conduits; J: 1-1
B3L1-292 | Cable Tray | 1-1 |  |  | 10 | 0 | 10 | 24-Mar-25 | 04-Apr-25 | J: -58; J: Cable Tray; A: 1-1
B3L1-350 |  | OH Mechanical Test/Inspections | 1-1 |  | 3 | 0 | 3 | 31-Mar-25 | 02-Apr-25 | J: -91; A: OH Mechanical Test/Inspections; F: 1-1
B3L1-360 |  | Insulate OH Mechanical Piping w/Duct | 1-1 |  | 15 | 0 | 15 | 03-Apr-25 | 23-Apr-25 | J: -91; O: Insulate OH Mechanical Piping w/Duct; M: 1-1
B3L1-220 |  | Metal Framing @ Corridors + Top 4'0 DW | 1-1 |  | 7 | 0 | 7 | 14-Apr-25 | 22-Apr-25 | J: -133; N: Metal Framing @ Corridors + Top 4'0 DW; M: 1-1
B3L1-284 | Lighting Conduits | 1-1 |  |  | 15 | 0 | 15 | 14-Apr-25 | 02-May-25 | J: -111; A: Lighting Conduits; N: 1-1
B3L1-300 |  | Metal Framing @ Rooms | 1-1 |  | 23 | 0 | 23 | 23-Apr-25 | 23-May-25 | J: -133; S: Metal Framing @ Rooms; F: 1-1
B3L1-310 |  | In Wall Mechanical / Contr ols Rou gh In | 1-1 |  | 15 | 0 | 15 | 24-Apr-25 | 14-May-25 | J: -113; N: In Wall Mechanical / Contr ols Rou gh In; M: 1-1
B3L1-2233 | Test and Balance | 1-1 |  |  | 2 | 0 | 2 | 24-Apr-25 | 25-Apr-25 | J: 80; A: Test and Balance; N: 1-1
B3L1-330 |  | In Wall Electrical Rough In | 1 -1 |  | 15 | 0 | 15 | 25-Apr-25 | 15-May-25 | J: -123; S: In Wall Electrical Rough In; F: 1-1
B3L1-344 | Power In Wall Branc h | 1- 1 |  |  | 15 | 0 | 15 | 25-Apr-25 | 15-May-25 | J: -133; A: Power In Wall Branc h; J: 1- 1
B3L1-320 |  | In Wall Plumbing Rough In | 1 -1 |  | 15 | 0 | 15 | 25-Apr-25 | 15-May-25 | J: -126; S: In Wall Plumbing Rough In; F: 1-1
B3L1-346 | Lighting In Wall Branch | 1 -1 |  |  | 15 | 0 | 15 | 02-May-25 | 22-May-25 | J: -133; A: Lighting In Wall Branch; F: 1-1
B3L1-286 | Fire Alarm Conduits | 1-1 |  |  | 15 | 0 | 15 | 05-May-25 | 23-May-25 | J: -83; A: Fire Alarm Conduits; J: 1-1
B3L1-288 |  | Security Conduits/ J-Hooks/ Sleeves | 1-1 |  | 10 | 0 | 10 | 05-May-25 | 16-May-25 | J: -78; N: Security Conduits/ J-Hooks/ Sleeves; M: 1-1
B3L1-348 |  | Fire Alarm In Wall Conduits | 1-1 |  | 15 | 0 | 15 | 09-May-25 | 30-May-25 | J: -133; O: Fire Alarm In Wall Conduits; F: 1-1
B3L1-352 | Security In Wall Conduits |  | 1-1 |  | 15 | 0 | 15 | 09-May-25 | 30-May-25 | J: -133; S: Security In Wall Conduits; F: 1-1
Remaining Level of Effort |  |  | Actual Work | Critical Remaining Work |  |  |  | Page 38 of 46 |  | J: TASK filter: Activity Status.
Actual Level of Effort |  |  | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  |  |  | Original | Actual | Remaining | Start | J: Finish; F: Total Float; J: 2025; A: 2026; A: 2027
[6 empty] | Duration | Duration | Duration | [30 empty] | M
[11 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
B3L1-354 | Data In Wall C ondu its | 1- 1 |  |  |  | 15 | 0 | 15 | 09-May-25 | 30-May-25 | J: -133; S: Data In Wall C onduits; J: 1- 1
B3L1-410 |  | Pull Control Wire to Devices- | 1-1 |  |  | 15 | 0 | 15 | 15-May-25 | 05-Jun-25 | J: -36; O: Pull Control Wire to Devices-; A: 1-1
B3L1-420 |  | Plumbing Testing & Insp ection | 1-1 |  |  | 3 | 0 | 3 | 16-May-25 | 20-May-25 | J: -122; O: Plumbing Testing & Insp ection; A: 1-1
B3L1-2223 |  | Install Blocking @ Rooms Lvl 1 |  |  |  | 12 | 0 | 12 | 16-May-25 | 03-Jun-25 | J: -126; O: Install Blocking @ Rooms Lvl 1
B3L1-458 | Pull Data & Security | 1-1 |  |  |  | 10 | 0 | 10 | 19-May-25 | 02-Jun-25 | J: -78; S: Pull Data & Security; J: 1-1
B3L1-460 |  | Insulate Plumbing Piping | 1-1 |  |  | 12 | 0 | 12 | 21-May-25 | 06-Jun-25 | J: -122; S: Insulate Plumbing Piping; M: 1-1
B3L1-2143 | Install Door Frames | 1-1 |  |  |  | 10 | 0 | 10 | 27-May-25 | 09-Jun-25 | J: -18; S: Install Door Frames; J: 1-1
B3L1-380 | Spray Foam Insulation | 1-1 |  |  |  | 10 | 0 | 10 | 27-May-25 | 09-Jun-25 | J: -130; S: Spray Foam Insulation; F: 1-1
B3L1-370 |  | Frame Soffits & Ceilings | 1-1 |  |  | 10 | 0 | 10 | 27-May-25 | 09-Jun-25 | J: -123; S: Frame Soffits & Ceilings; F: 1-1
B3L1-456 | Pull Fire Alarm | 1-1 |  |  |  | 10 | 0 | 10 | 27-May-25 | 09-Jun-25 | J: -83; A: Pull Fire Alarm; N: 1-1
B3L1-2213 | VIF Millwork | 1-1 |  |  |  | 2 | 0 | 2 | 27-May-25 | 28-May-25 | J: -35; A: VIF Millwork; O: 1-1
B3L1-430 |  | Inspect In-Wall Electric al | 1-1 |  |  | 3 | 0 | 3 | 02-Jun-25 | 04-Jun-25 | J: -133; S: Inspect In-Wall Electric al; M: 1-1
B3L1-450 |  | Pull & Terminate Electrical Wires- | 1-1 |  |  | 10 | 0 | 10 | 05-Jun-25 | 18-Jun-25 | J: -133; N: Pull & Terminate Electrical Wires-; J: 1-1
B3L1-452 |  | Pull & Terminate Br anch W ire | 1-1 |  |  | 10 | 0 | 10 | 05-Jun-25 | 18-Jun-25 | J: -133; O: Pull & Terminate Br anch W ire; A: 1-1
B3L1-454 |  | Pull & Terminate Br anch Lighting | 1-1 |  |  | 10 | 0 | 10 | 05-Jun-25 | 18-Jun-25 | J: -133; N: Pull & Terminate Br anch Lighting; M: 1-1
B3L1-480 | Terminate Controls - | 1-1 |  |  |  | 10 | 0 | 10 | 06-Jun-25 | 19-Jun-25 | J: -36; S: Terminate Controls -; F: 1-1
B3L1-400 |  | Seal Penetrations Thru Fire Wall /Floors |  | 1-1 |  | 5 | 0 | 5 | 17-Jun-25 | 23-Jun-25 | J: -133; D: Seal Penetrations Thru Fire Wall /Floors; J: 1-1
B3L1-440 |  | OH Electrical Inspections - | 1-1 |  |  | 3 | 0 | 3 | 19-Jun-25 | 23-Jun-25 | J: -133; O: OH Electrical Inspections -; A: 1-1
B3L1-490 | OH Inspection - | 1-1 |  |  |  | 0 | 0 | 0 |  | 23-Jun-25 | J: -190; S: OH Inspection -; J: 1-1
FINISH LVL 1 | [5 empty] | 165 | 0 | 165 | 03-Jun-25 | 26-Jan-26 | J: -118
B3L1-564 | Terminate Security | 1-1 |  |  |  | 10 | 0 | 10 | 03-Jun-25 | 16-Jun-25 | J: -43; S: Terminate Security; J: 1-1
B3L1-470 | Gypsum Board Walls | 1-1 |  |  |  | 25 | 0 | 25 | 10-Jun-25 | 15-Jul-25 | J: -130; O: Gypsum Board Walls; M: 1-1
B3L1-566 | Terminate Fire Alarm | 1-1 |  |  |  | 10 | 0 | 10 | 10-Jun-25 | 23-Jun-25 | J: -48; S: Terminate Fire Alarm; F: 1-1
B3L1-510 | Tape and Finish Walls | 1-1 |  |  |  | 25 | 0 | 25 | 17-Jun-25 | 22-Jul-25 | J: -108; O: Tape and Finish Walls; M: 1-1
B3L1-2243 |  | Install Fire-Retardant Plywood for Telec om Room |  |  |  | 5 | 0 | 5 | 17-Jun-25 | 23-Jun-25 | J: -108; F: Install Fire-Retardant Plywood for Telec om Room
B3L1-562 |  | Install & Ter minate WAP | 1-1 |  |  | 10 | 0 | 10 | 19-Jun-25 | 02-Jul-25 | J: -45; O: Install & Ter minate WAP; M: 1-1
B3L1-500 |  | Gypsum Board Soffits & Ceilings | 1-1 |  |  | 15 | 0 | 15 | 24-Jun-25 | 15-Jul-25 | J: -133; D: Gypsum Board Soffits & Ceilings; J: 1-1
B3L1-520 |  | Tape and Finish Soffit s & C eilings | 1-1 |  |  | 20 | 0 | 20 | 01-Jul-25 | 29-Jul-25 | J: -133; J: Tape and Finish Soffit s & C eilings; J: 1-1
B3L1-530 | Prime Paint & 1st Coat |  | 1-1 |  |  | 15 | 0 | 15 | 30-Jul-25 | 19-Aug-25 | J: -133; D: Prime Paint & 1st Coat; M: 1-1
B3L1-640 |  | Electrical Wall F inis hes | 1-1 |  |  | 10 | 0 | 10 | 20-Aug-25 | 03-Sep-25 | J: -111; D: Electrical Wall F in is hes; M: 1-1
B3L1-540 | ACT Ceiling Grid | 1-1 |  |  |  | 20 | 0 | 20 | 20-Aug-25 | 17-Sep-25 | J: -133; D: ACT Ceiling Grid; A: 1-1
B3L1-652 | Fire Alarm Devices | 1-1 |  |  |  | 10 | 0 | 10 | 20-Aug-25 | 03-Sep-25 | J: -88; D: Fire Alarm Devices; A: 1-1
B3L1-654 | Security Devices | 1-1 |  |  |  | 10 | 0 | 10 | 20-Aug-25 | 03-Sep-25 | J: -88; N: Security Devices; A: 1-1
B3L1-656 | Data Devices | 1-1 |  |  |  | 10 | 0 | 10 | 20-Aug-25 | 03-Sep-25 | J: -18; N: Data Devices; M: 1-1
B3L1-534 | Install Security Doors | 1-1 |  |  |  | 10 | 0 | 10 | 20-Aug-25 | 03-Sep-25 | J: -68; D: Install Security Doors; M: 1-1
B3L1-550 |  | Mech OH Ceiling Finishes | 1-1 |  |  | 10 | 0 | 10 | 04-Sep-25 | 17-Sep-25 | J: -123; J: Mech OH Ceiling Finishes; J: 1-1
B3L1-560 |  | Electrical Ceiling Finishes | 1-1 |  |  | 10 | 0 | 10 | 04-Sep-25 | 17-Sep-25 | J: -123; J: Electrical Ceiling Finishes; J: 1-1
B3L1-2253 | Install Lockers | 1-1 |  |  |  | 3 | 0 | 3 | 04-Sep-25 | 08-Sep-25 | J: -111; N: Install Lockers; M: 1-1
B3L1-2263 | Patient Lift Systems | 1-1 |  |  |  | 5 | 0 | 5 | 09-Sep-25 | 15-Sep-25 | J: -111; D: Patient Lift Systems; M: 1-1
B3L1-570 |  | Fire Protection Ceiling Finishes | 1-1 |  |  | 10 | 0 | 10 | 18-Sep-25 | 01-Oct-25 | J: -133; M: Fire Protection Ceiling Finishes; A: 1-1
B3L1-580 | Ceramic Tile | 1-1 |  |  |  | 10 | 0 | 10 | 02-Oct-25 | 15-Oct-25 | J: -133; D: Ceramic Tile; M: 1-1
B3L1-610 | Doors and Hardware | 1-1 |  |  |  | 20 | 0 | 20 | 16-Oct-25 | 12-Nov-25 | J: -118; M: Doors and Hardware; J: 1-1
B3L1-600 | Mill Work | 1-1 |  |  |  | 10 | 0 | 10 | 16-Oct-25 | 29-Oct-25 | J: -133; D: Mill Work; M: 1-1
B3L1-660 |  | Wall and Co rner Protection | 1-1 |  |  | 10 | 0 | 10 | 30-Oct-25 | 12-Nov-25 | J: -118; A: Wall a nd Corner Protectio n; A: 1-1
B3L1-630 | Plumbing Finishes | 1-1 |  |  |  | 5 | 0 | 5 | 30-Oct-25 | 05-Nov-25 | J: -133; F: Plumbing Finishes; J: 1-1
B3L1-700 | Ceiling Tiles | 1-1 |  |  |  | 10 | 0 | 10 | 06-Nov-25 | 19-Nov-25 | J: -133; J: Ceiling Tiles; A: 1-1
B3L1-2283 |  | Prep/Patch Floors for Flooring Install |  |  |  | 10 | 0 | 10 | 20-Nov-25 | 04-Dec-25 | J: -133; J: Prep/Patch Floors for Flooring Install
B3L1-2323 | Install Walk -Off Mats | 1-1 |  |  |  | 5 | 0 | 5 | 05-Dec-25 | 11-Dec-25 | J: -123; A: Install Walk -Off Mats; J: 1-1
Remaining Level of Effort |  |  | Actual Work |  | Critical Remaining Work |  |  |  | Page 39 of 46 |  | J: TASK filter: Activity Status.
Actual Level of Effort |  |  | Remaining Work |  | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  |  | Original | Actual | Remaining | Start | Finish | Total Float | A: 2025; M: 2026; F: 2027
[5 empty] | Duration | Duration | Duration | bar: A
[10 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
B3L1-720 | Carpet/VCT | 1-1 |  |  | 15 | 0 | 15 | 05-Dec-25 | 26-Dec-25 | J: -133; M: Carpet/VCT; J: 1-1
B3L1-2333 |  | Composite Flooring 1-1 |  |  | 15 | 0 | 15 | 05-Dec-25 | 26-Dec-25 | J: -133; A: Composite Flooring 1-1
B3L1-620 | Final Paint | 1-1 |  |  | 15 | 0 | 15 | 29-Dec-25 | 19-Jan-26 | J: -133; M: Final Paint; J: 1-1
B3L1-890 |  | Inst Toilet Accessories |  |  | 5 | 0 | 5 | 15-Jan-26 | 21-Jan-26 | J: -132; M: Inst Toilet Accessories
B3L1-2313 |  | Install Kitchen Equipment | 1-1 |  | 2 | 0 | 2 | 16-Jan-26 | 19-Jan-26 | J: -130; M: Install Kitchen Equipment; O: 1-1
B3L1-670 | Window Shades | 1-1 |  |  | 5 | 0 | 5 | 20-Jan-26 | 26-Jan-26 | J: -118; A: Window Shades; A: 1-1
B3L1-680 | Signage | 1-1 |  |  | 5 | 0 | 5 | 20-Jan-26 | 26-Jan-26 | J: -118; M: Signage; M: 1-1
B3L1-390 |  | Interior Windows/Film | 1-1 |  | 5 | 0 | 5 | 20-Jan-26 | 26-Jan-26 | J: -118; M: Interior Windows/Film; S: 1-1
B3L1-880 |  | Replace Glazing 1st Fl |  |  | 5 | 0 | 5 | 20-Jan-26 | 26-Jan-26 | J: -118; M: Replace Glazing 1st Fl
B3L1-2293 |  | Install Fire Extinguisher Cabinets |  |  | 3 | 0 | 3 | 20-Jan-26 | 22-Jan-26 | J: -133; J: Install Fire Extinguisher Cabinets
BLDG 3 2ND FLOOR |  |  |  |  | 267 | 202 | 245 | 17-Apr-24 A | 19-Jan-26 | J: -105
| GENERAL FLOOR ABAT EMENT /DEMO |  |  |  | 57 | 57 | 35 | 11-Nov-24 A | 21-Mar-25 | J: 77
B3L2-960 |  |  | Inst Steel @ Underside of Fl 3 @ New Openings |  | 15 | 57 | 6 | 11-Nov-24 A | 14-Mar-25 | J: -21; O: Inst Steel @ Underside of Fl 3 @ New Openings
B3L2-130 |  | Sawcut Floor @ Openings 2nd |  |  | 5 | 42 | 3 | 03-Dec-24 A | 06-Mar-25 | J: -84; J: Sawcut Floor @ Openings 2nd
B3L2-1040 |  | Sawcut/Seal Conduits in Floor Slab |  |  | 7 | 42 | 3 | 03-Dec-24 A | 05-Feb-25 | J: -63; J: Sawcut/Seal Conduits in Floor Slab
B3L2-1020 |  | Demo Exterior Roof Landings |  |  | 5 | 0 | 5 | 17-Mar-25 | 21-Mar-25 | J: 77; A: Demo Exterior Roof Landings
STRUCTURE 2ND TO 3RD |  |  |  |  | 10 | 0 | 10 | 07-Mar-25 | 20-Mar-25 | J: -25
B3L2-970 |  | Install Shaft Walls @ Elev Hoistway 2nd to 3rd |  |  | 10 | 0 | 10 | 07-Mar-25 | 20-Mar-25 | J: -25; O: Install Shaft Walls @ Elev Hoistway 2nd to 3rd
B3L2-1000 |  | Infill Concrete @ Lvl 2 Floor |  |  | 5 | 0 | 5 | 07-Mar-25 | 13-Mar-25 | J: -84; J: Infill Concrete @ Lvl 2 Floor
ROUGH IN LVL 2 |  |  |  |  | 155 | 202 | 133 | 17-Apr-24 A | 08-Aug-25 | J: 7
B3L2-342 |  | Distribution Panels Install | Lvl 2 |  | 15 | 202 | 7 | 17-Apr-24 A | 11-Jun-25 | J: -113; O: Distribution Panels Install; M: Lvl 2
B3L2-160 |  | Layout/Top Track Lvl 2 |  |  | 8 | 67 | 6 | 28-Oct-24 A | 10-Feb-25 | J: -106; M: Layout/Top Track Lvl 2
B3L2-2323 |  | Metal Framing @ Exterior Walls | Lv l 2 |  | 5 | 30 | 1 | 19-Dec-24 A | 11-Feb-25 | J: -27; J: Metal Framing @ Exterior Walls; J: Lv l 2
B3L2-170 | Fireproofing | Lvl 2 |  |  | 8 | 0 | 8 | 12-Feb-25 | 21-Feb-25 | J: -115; A: Fireproofing; J: Lvl 2
B3L2-230 |  | Ductwork OH Rough In | Lvl 2 |  | 25 | 0 | 25 | 24-Feb-25 | 28-Mar-25 | J: -115; J: Ductwork OH Rough In; D: Lvl 2
B3L2-240 |  | Mechanical Equipment | Lvl 2 |  | 30 | 0 | 30 | 03-Mar-25 | 11-Apr-25 | J: -73; J: Mechanical Equipment; D: Lvl 2
B3L2-250 |  | HVAC Pipe OH Rough In | Lvl 2 |  | 25 | 0 | 25 | 03-Mar-25 | 04-Apr-25 | J: -115; J: HVAC Pipe OH Rough In; J: Lvl 2
B3L2-260 |  | Plumbing OH Rough In | Lvl 2 |  | 25 | 0 | 25 | 10-Mar-25 | 11-Apr-25 | J: -105; J: Plumbing OH Rough In; D: Lvl 2
B3L2-280 |  | Electrical OH Rough In Lvl 2 |  |  | 20 | 0 | 20 | 13-Mar-25 | 09-Apr-25 | J: -103; J: Electrical OH Rough In; D: Lvl 2
B3L2-270 |  | Controls OH Rough In Lvl 2 |  |  | 25 | 0 | 25 | 24-Mar-25 | 25-Apr-25 | J: -115; S: Controls OH Rough In Lvl 2
B3L2-290 |  | Fire Protection OH Rough In | Lvl 2 |  | 15 | 0 | 15 | 24-Mar-25 | 11-Apr-25 | J: -105; A: Fire Protection OH Rough In; F: Lvl 2
B3L2-282 |  | Electrical Power Conduits | Lvl 2 |  | 15 | 0 | 15 | 10-Apr-25 | 30-Apr-25 | J: -96; A: Electrical Power Conduits; F: Lvl 2
B3L2-292 | Cable Tray | Lvl 2 |  |  | 10 | 0 | 10 | 10-Apr-25 | 23-Apr-25 | J: -68; J: Cable Tray; S: Lvl 2
B3L2-310 |  | OH FP Test/Inspections - | Lvl 2 |  | 5 | 0 | 5 | 14-Apr-25 | 18-Apr-25 | J: -60; A: OH FP Test/Inspections -; F: Lvl 2
B3L2-350 |  | OH Mechanical Test/Inspections | Lvl 2 |  | 3 | 0 | 3 | 14-Apr-25 | 16-Apr-25 | J: -73; S: OH Mechanical Test/Inspections; A: Lvl 2
B3L2-360 |  | Insulate OH Mechanical Piping w/Duct | Lvl 2 |  | 15 | 0 | 15 | 17-Apr-25 | 07-May-25 | J: -73; N: Insulate OH Mechanical Piping w/Duct; J: Lvl 2
B3L2-220 |  | Metal Framing @ Corridors + Top 4'0 DW | Lv l 2 |  | 7 | 0 | 7 | 28-Apr-25 | 06-May-25 | J: -115; N: Metal Framing @ Corridors + Top 4'0 DW; J: Lv l 2
B3L2-284 |  | Lighting Conduits Lvl 2 |  |  | 15 | 0 | 15 | 01-May-25 | 21-May-25 | J: -96; A: Lighting Conduits; D: Lvl 2
B3L2-1080 |  | Test and Balance Lvl 2 |  |  | 2 | 0 | 2 | 08-May-25 | 09-May-25 | J: 70; A: Test and Balance Lvl 2
B3L2-286 |  | Fire Alarm Conduits | Lvl 2 |  | 15 | 0 | 15 | 22-May-25 | 12-Jun-25 | J: -93; S: Fire Alarm Conduits; F: Lvl 2
B3L2-288 |  | Security Conduits/ J-Hooks/ Sleeves | Lvl 2 |  | 10 | 0 | 10 | 22-May-25 | 05-Jun-25 | J: -88; N: Security Conduits/ J-Hooks/ Sleeves; J: Lvl 2
B3L2-300 |  | Metal Framing @ Rooms | Lvl 2 |  | 23 | 0 | 23 | 27-May-25 | 26-Jun-25 | J: -128; O: Metal Framing @ Rooms; A: Lvl 2
B3L2-320 |  | In Wall Mechanical / Contr ols Rou gh In | Lv l 2 |  | 15 | 0 | 15 | 28-May-25 | 17-Jun-25 | J: -111; D: In Wall Mechanical / Contr ols Rough In; J: Lv l 2
B3L2-330 |  | In Wall Plumbing Rough In L vl 2 |  |  | 15 | 0 | 15 | 29-May-25 | 18-Jun-25 | J: -124; N: In Wall Plumbing Rough In L vl 2
B3L2-340 |  | In Wall Electrical Rough In Lv l 2 |  |  | 15 | 0 | 15 | 29-May-25 | 18-Jun-25 | J: -118; N: In Wall Electrical Rough In Lv l 2
B3L2-344 |  | Power In Wall Branc h | Lv l 2 |  | 15 | 0 | 15 | 29-May-25 | 18-Jun-25 | J: -128; O: Power In Wall Branc h; F: Lv l 2
B3L2-346 |  | Lighting In Wall Branch | L vl 2 |  | 15 | 0 | 15 | 05-Jun-25 | 25-Jun-25 | J: -128; O: Lighting In Wall Bran ch; M: L vl 2
B3L2-348 |  | Fire Alarm In Wall Conduits | Lvl 2 |  | 15 | 0 | 15 | 12-Jun-25 | 02-Jul-25 | J: -128; N: Fire Alarm In Wall Conduits; A: Lvl 2
B3L2-352 |  | Security In Wall Conduits | Lvl 2 |  | 15 | 0 | 15 | 12-Jun-25 | 02-Jul-25 | J: -128; O: Security In Wall Conduits; A: L vl 2
Remaining Level of Effort |  |  | Actual Work | Critical Remaining Work |  |  |  | Page 40 of 46 |  | J: TASK filter: Activity Status.
Actual Level of Effort |  |  | Remaining Work | Milestone | [5 empty] | J: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  |  | Original | Actual | Remaining | Start | Finish | J: Total Float; J: 2025; J: 2026; M: 2027
[5 empty] | Duration | Duration | Duration | [30 empty] | M
[10 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
B3L2-354 | Data In Wall C ondu its | Lv l 2 |  |  | 15 | 0 | 15 | 12-Jun-25 | 02-Jul-25 | J: -128; O: Data In Wall C onduits; M: Lv l 2
B3L2-410 | Pull Control Wire to Devices- |  | Lvl 2 |  | 15 | 0 | 15 | 18-Jun-25 | 09-Jul-25 | J: -81; N: Pull Control Wire to Devices-; J: Lvl 2
B3L2-420 |  | Plumbing Testing & Insp ection | Lvl 2 |  | 3 | 0 | 3 | 19-Jun-25 | 23-Jun-25 | J: -117; N: Plumbing Testing & Inspection; M: Lvl 2
B3L2-1070 |  | Install Blocking @ Rooms Lvl 2 |  |  | 12 | 0 | 12 | 19-Jun-25 | 07-Jul-25 | J: -124; D: Install Blocking @ Rooms Lvl 2
B3L2-460 |  | Insulate Plumbing Piping Lvl 2 |  |  | 12 | 0 | 12 | 24-Jun-25 | 10-Jul-25 | J: -117; D: Insulate Plumbing Piping Lvl 2
B3L2-880 | Install Door Frames | Lvl 2 |  |  | 10 | 0 | 10 | 27-Jun-25 | 11-Jul-25 | J: -38; O: Install Door Frames; F: Lvl 2
B3L2-380 |  | Spray Foam Insulation Lvl 2 |  |  | 10 | 0 | 10 | 27-Jun-25 | 11-Jul-25 | J: -123; N: Spray Foam Insulation Lvl 2
B3L2-370 |  | Frame Soffits & Ceilings Lvl 2 |  |  | 10 | 0 | 10 | 27-Jun-25 | 11-Jul-25 | J: -118; N: Frame Soffits & Ceilings Lvl 2
B3L2-1060 | VIF Millwork |  |  |  | 2 | 0 | 2 | 27-Jun-25 | 30-Jun-25 | J: -55; A: VIF Millwork
B3L2-430 | Inspect In-Wall Electric al | Lvl 2 |  |  | 3 | 0 | 3 | 03-Jul-25 | 08-Jul-25 | J: -128; O: Inspect In-Wall Elect ric al; A: Lvl 2
B3L2-452 | Pull & Terminate Br anch W ire |  | Lvl 2 |  | 10 | 0 | 10 | 09-Jul-25 | 22-Jul-25 | J: -128; D: Pull & Terminate Br anch W ire; J: Lvl 2
B3L2-454 |  | Pull & Terminate Br anch Lighting | Lvl 2 |  | 10 | 0 | 10 | 09-Jul-25 | 22-Jul-25 | J: -128; D: Pull & Terminate Br anch L ighting; J: Lvl 2
B3L2-456 | Pull Fire Alarm | Lvl 2 |  |  | 10 | 0 | 10 | 09-Jul-25 | 22-Jul-25 | J: -110; S: Pull Fire Alarm; J: Lvl 2
B3L2-458 | Pull Data & Security | Lvl 2 |  |  | 10 | 0 | 10 | 09-Jul-25 | 22-Jul-25 | J: -110; O: Pull Data & Security; M: Lvl 2
B3L2-480 | Terminate Controls - | Lvl 2 |  |  | 10 | 0 | 10 | 10-Jul-25 | 23-Jul-25 | J: -81; O: Terminate Controls -; M: Lvl 2
B3L2-400 |  | Seal Penetrations Thru Fire Wall /Floors | Lvl 2 |  | 5 | 0 | 5 | 21-Jul-25 | 25-Jul-25 | J: -128; J: Seal Penetrations Thru Fire Wall /Floors; S: Lvl 2
B3L2-440 | OH Electrical Inspections - | Lvl 2 |  |  | 3 | 0 | 3 | 23-Jul-25 | 25-Jul-25 | J: -128; N: OH Electrical Inspections -; M: Lvl 2
B3L2-490 | OH Inspection - | Lvl 2 |  |  | 0 | 0 | 0 |  | 25-Jul-25 | J: -180; O: OH Inspection -; F: Lvl 2
B3L2-450 |  | Pull & Terminate Electrical Wires- | Lvl 2 |  | 10 | 0 | 10 | 28-Jul-25 | 08-Aug-25 | J: -103; J: Pull & Terminate Electrical Wires-; A: Lvl 2
FINISH LVL 2 |  |  |  |  | 130 | 0 | 130 | 16-Jul-25 | 19-Jan-26 | J: -113
B3L2-470 | Gypsum Board Walls | Lv l 2 |  |  | 20 | 0 | 20 | 16-Jul-25 | 12-Aug-25 | J: -130; N: Gypsum Board Walls; A: Lv l 2
B3L2-510 | Tape and Finish Walls | Lvl 2 |  |  | 25 | 0 | 25 | 23-Jul-25 | 26-Aug-25 | J: -125; D: Tape and Finish Walls; M: Lvl 2
B3L2-564 | Terminate Security | Lvl 2 |  |  | 10 | 0 | 10 | 23-Jul-25 | 05-Aug-25 | J: -100; O: Terminate Security; M: Lvl 2
B3L2-566 | Terminate Fire Alarm | Lvl 2 |  |  | 10 | 0 | 10 | 23-Jul-25 | 05-Aug-25 | J: -90; N: Terminate Fire Alarm; A: Lvl 2
B3L2-1090 |  | Install Fire-Retardant Plywood for Telec om Room |  |  | 5 | 0 | 5 | 23-Jul-25 | 29-Jul-25 | J: -125; M: Install Fire-Retardant Plywood for Telec om Room
B3L2-500 |  | Gypsum Board Soffits & Ceilings | Lvl 2 |  | 15 | 0 | 15 | 30-Jul-25 | 19-Aug-25 | J: -130; J: Gypsum Board Soffits & Ceilings; A: Lvl 2
B3L2-1100 |  | Install Wire Mesh Partitions for Telec om Room |  |  | 5 | 0 | 5 | 30-Jul-25 | 05-Aug-25 | J: -125; M: Install Wire Mesh Partitions for Telec om Room
B3L2-520 |  | Tape and Finish Soffit s & C eilings | Lvl 2 |  | 20 | 0 | 20 | 06-Aug-25 | 03-Sep-25 | J: -130; F: Tape and Finish Soffit s & C eilings; A: Lvl 2
B3L2-562 | Install & Ter minate WAP | Lvl 2 |  |  | 10 | 0 | 10 | 11-Aug-25 | 22-Aug-25 | J: -103; D: Install & Ter minate WAP; J: Lvl 2
B3L2-530 | Prime Paint & 1st Coat | Lvl 2 |  |  | 15 | 0 | 15 | 13-Aug-25 | 03-Sep-25 | J: -130; D: Prime Paint & 1st Coat; J: Lvl 2
B3L2-540 | ACT Ceiling Grid | Lvl 2 |  |  | 20 | 0 | 20 | 20-Aug-25 | 17-Sep-25 | J: -130; D: ACT Ceiling Grid; A: Lvl 2
B3L2-550 | Mech OH Ceiling Finishes | Lvl 2 |  |  | 10 | 0 | 10 | 04-Sep-25 | 17-Sep-25 | J: -120; J: Mech OH Ceiling Finishes; J: Lvl 2
B3L2-650 | Electrical Wall F inis hes | Lv l 2 |  |  | 10 | 0 | 10 | 04-Sep-25 | 17-Sep-25 | J: -120; J: Electrical Wall F inis hes; J: Lv l 2
B3L2-560 | Electrical Ceiling Finishes | Lvl 2 |  |  | 10 | 0 | 10 | 04-Sep-25 | 17-Sep-25 | J: -120; J: Electrical Ceiling Finishes; J: Lvl 2
B3L2-652 | Fire Alarm Devices | Lvl 2 |  |  | 10 | 0 | 10 | 04-Sep-25 | 17-Sep-25 | J: -95; D: Fire Alarm Devices; M: Lvl 2
B3L2-654 | Security Devices | Lvl 2 |  |  | 10 | 0 | 10 | 04-Sep-25 | 17-Sep-25 | J: -120; D: Security Devices; A: Lvl 2
B3L2-656 | Data Devices | Lvl 2 |  |  | 10 | 0 | 10 | 04-Sep-25 | 17-Sep-25 | J: -90; N: Data Devices; M: Lvl 2
B3L2-534 | Install Security Doors | Lvl 2 |  |  | 10 | 0 | 10 | 04-Sep-25 | 17-Sep-25 | J: -75; D: Install Security Doors; M: Lvl 2
B3L2-570 |  | Fire Protection Ceiling Finishes | Lvl 2 |  | 10 | 0 | 10 | 18-Sep-25 | 01-Oct-25 | J: -130; M: Fire Protection Ceiling Finishes; A: Lvl 2
B3L2-600 | Ceramic Tile | Lvl 2 |  |  | 10 | 0 | 10 | 02-Oct-25 | 15-Oct-25 | J: -130; D: Ceramic Tile; A: Lvl 2
B3L2-620 | Doors and Hardware | Lvl 2 |  |  | 20 | 0 | 20 | 16-Oct-25 | 12-Nov-25 | J: -115; F: Doors and Hardware; J: Lvl 2
B3L2-610 | Mill Work | Lvl 2 |  |  | 10 | 0 | 10 | 16-Oct-25 | 29-Oct-25 | J: -130; D: Mill Work; M: Lvl 2
B3L2-670 | Wall and Co rner Protection | Lvl 2 |  |  | 10 | 0 | 10 | 30-Oct-25 | 12-Nov-25 | J: -115; M: Wall a nd Corner Protectio n; S: Lvl 2
B3L2-640 | Plumbing Finishes Lvl 2 |  |  |  | 5 | 0 | 5 | 30-Oct-25 | 05-Nov-25 | J: -130; M: Plumbing Finishes Lvl 2
B3L2-710 | Ceiling Tiles | Lvl 2 |  |  | 10 | 0 | 10 | 06-Nov-25 | 19-Nov-25 | J: -130; J: Ceiling Tiles; M: Lvl 2
B3L2-1110 |  | Install Ladder to New Floor Hatch | Lvl 2 |  | 3 | 0 | 3 | 13-Nov-25 | 17-Nov-25 | J: -98; M: Install Ladder to New Floor Hatch; O: Lvl 2
B3L2-1120 |  | Install New Stairs to Mech Level | Lvl 2 |  | 10 | 0 | 10 | 18-Nov-25 | 02-Dec-25 | J: -98; M: Install New Stairs to Mech Level; O: Lvl 2
B3L2-1130 |  | Prep/Patch Floors for Flooring Install | Lvl 2 |  | 10 | 0 | 10 | 20-Nov-25 | 04-Dec-25 | J: -130; J: Prep/Patch Floors for Flooring Install; D: Lvl 2
Remaining Level of Effort |  | Actual Work |  | Critical Remaining Work |  |  |  | Page 41 of 46 |  | J: TASK filter: Activity Status.
Actual Level of Effort |  | Remaining Work |  | Milestone | [5 empty] | D: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  | Original | Actual | Remaining | Start | Finish | Total Float | M: 2025; J: 2026; F: 2027
|  |  |  | Duration | Duration | Duration | bar: A
[9 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
B3L2-720 | Carpet/VCT | Lvl 2 |  | 15 | 0 | 15 | 05-Dec-25 | 26-Dec-25 | J: -130; F: Carpet/VCT; J: Lvl 2
B3L2-2313 | Composite Flooring | Lvl 2 |  | 15 | 0 | 15 | 05-Dec-25 | 26-Dec-25 | J: -130; M: Composite Flooring; A: Lvl 2
B3L2-630 | Final Paint Lvl 2 |  |  | 10 | 0 | 10 | 29-Dec-25 | 12-Jan-26 | J: -130; M: Final Paint; J: Lvl 2
B3L2-2153 | Inst Toilet Accessories |  |  | 5 | 0 | 5 | 13-Jan-26 | 19-Jan-26 | J: -130; M: Inst Toilet Accessories
B3L2-940 | Replace Glazing 2nd Fl |  |  | 5 | 0 | 5 | 13-Jan-26 | 19-Jan-26 | J: -113; M: Replace Glazing 2nd Fl
B3L2-690 | Window Shades Lvl 2 |  |  | 5 | 0 | 5 | 13-Jan-26 | 19-Jan-26 | J: -113; M: Window Shades Lvl 2
B3L2-680 | Signage | Lvl 2 |  | 5 | 0 | 5 | 13-Jan-26 | 19-Jan-26 | J: -113; F: Signage; J: Lvl 2
B3L2-390 | Interior Windows/Film | Lvl 2 |  | 5 | 0 | 5 | 13-Jan-26 | 19-Jan-26 | J: -113; M: Interior Windows/Film; O: Lvl 2
B3L2-2303 |  | Install Fire Extinguisher Cabinets |  | 3 | 0 | 3 | 13-Jan-26 | 15-Jan-26 | J: -128; J: Install Fire Extinguisher Cabinets
BLDG 3 3RD FL PH |  |  |  | 243 | 157 | 206 | 20-Jun-24 A | 12-Jan-26 | J: -100
| GENERAL FLOOR ABAT EMENT/D EMO |  |  | 71 | 47 | 34 | 25-Nov-24 A | 07-May-25 | J: 37
B3L3-150 |  | Sawcut Floor Openings @ 3rd Fl |  | 2 | 47 | 1 | 25-Nov-24 A | 21-Mar-25 | J: -25; A: Sawcut Floor Openings @ 3rd Fl
B3L3-400 |  | Form & Place Conc Curb @ Hoistway |  | 3 | 0 | 3 | 24-Mar-25 | 26-Mar-25 | J: -13; S: Form & Place Conc Curb @ Hoistway
B3L3-410 |  | CMU Bondbeam @ Hoistway |  | 2 | 0 | 2 | 27-Mar-25 | 28-Mar-25 | J: -13; A: CMU Bondbeam @ Hoistway
B3L3-420 |  | Form & Place Hoistway Cap Slab |  | 3 | 0 | 3 | 31-Mar-25 | 02-Apr-25 | J: -13; S: Form & Place Hoistway Cap Slab
B3L3-170 |  | Patch Masonry for Openings |  | 15 | 0 | 15 | 03-Apr-25 | 23-Apr-25 | J: 9; S: Patch Masonry for Openings
B3L3-570 |  | Sawcut/Seal Conduits in Floor Slab |  | 7 | 0 | 7 | 24-Apr-25 | 02-May-25 | J: 37; O: Sawcut/Seal Conduits in Floor Slab
B3L3-580 |  | Demo Floor for New Stairwell |  | 3 | 0 | 3 | 05-May-25 | 07-May-25 | J: 37; O: Demo Floor for New Stairwell
STRUCTURE 3RD FLOOR |  |  |  | 8 | 0 | 8 | 03-Apr-25 | 14-Apr-25 | J: -13
B3L3-480 |  | Inst Steel for HVAC Supports |  | 8 | 0 | 8 | 03-Apr-25 | 14-Apr-25 | J: -13; S: Inst Steel for HVAC Supports
LVL 3 ROUGH/FINISH PH |  |  |  | 189 | 157 | 189 | 20-Jun-24 A | 12-Jan-26 | J: -100
B3L3-220 | Duct Rough In Lvl 3 |  |  | 25 | 157 | 17 | 20-Jun-24 A | 19-Sep-25 | J: -95; D: Duct Rough In Lvl 3
B3L3-240 | Plumbing Rough In Lvl 3 |  |  | 10 | 99 | 3 | 12-Sep-24 A | 29-Aug-25 | J: -64; D: Plumbing Rough In Lvl 3
B3L3-540 | Set AHU (3-AHU-1) |  |  | 4 | 0 | 4 | 15-Apr-25 | 18-Apr-25 | J: -13; J: Set AHU (3-AHU-1)
B3L3-550 | Set AHU (3-AHU-3) |  |  | 4 | 0 | 4 | 21-Apr-25 | 24-Apr-25 | J: -13; J: Set AHU (3-AHU-3)
B3L3-560 | Set AHU (3-AHU-2) |  |  | 4 | 0 | 4 | 25-Apr-25 | 30-Apr-25 | J: -13; A: Set AHU (3-AHU-2)
B3L3-160 | Shaft Wall Inst all Lvl 3 |  |  | 10 | 0 | 10 | 13-Aug-25 | 26-Aug-25 | J: -125; D: Shaft Wall Inst all Lvl 3
B3L3-180 |  | 4" Fire Treated Insulated Fl Pnl Lvl 3 |  | 15 | 0 | 15 | 27-Aug-25 | 17-Sep-25 | J: -125; F: 4" Fire Treated Insulated Fl Pnl Lvl 3
B3L3-260 |  | HVAC Piping Rough In Lvl 3 |  | 15 | 0 | 15 | 27-Aug-25 | 17-Sep-25 | J: -81; J: HVAC Piping Rough In Lvl 3
B3L3-250 | Controls Rough In Lvl 3 |  |  | 15 | 0 | 15 | 27-Aug-25 | 17-Sep-25 | J: -68; J: Controls Rough In Lvl 3
B3L3-610 |  | Install Vapor Retarder on Floor Lvl 3 |  | 5 | 0 | 5 | 27-Aug-25 | 03-Sep-25 | J: -38; F: Install Vapor Retarder on Floor Lvl 3
B3L3-270 | Plumbing Testing Lvl 3 |  |  | 3 | 0 | 3 | 02-Sep-25 | 04-Sep-25 | J: -64; D: Plumbing Testing Lvl 3
B3L3-620 | Install Floor Drains Lvl 3 |  |  | 3 | 0 | 3 | 04-Sep-25 | 08-Sep-25 | J: -38; J: Install Floor Drains Lvl 3
B3L3-290 |  | Plumbing Insulation Rough In Lvl 3 |  | 5 | 0 | 5 | 05-Sep-25 | 11-Sep-25 | J: -64; F: Plumbing Insulation Rough In Lvl 3
B3L3-300 | HVAC Pipe Testing Lvl 3 |  |  | 3 | 0 | 3 | 18-Sep-25 | 22-Sep-25 | J: -81; J: HVAC Pipe Testing Lvl 3
B3L3-190 |  | Electrical OH Rough In Lvl 3 |  | 20 | 0 | 20 | 18-Sep-25 | 15-Oct-25 | J: -125; F: Electrical OH Rough In Lvl 3
B3L3-200 |  | Fire Protection OH Rough In Lvl 3 |  | 20 | 0 | 20 | 18-Sep-25 | 15-Oct-25 | J: -113; M: Fire Protection OH Rough In Lvl 3
B3L3-320 | Louvers Lvl 3 |  |  | 10 | 0 | 10 | 22-Sep-25 | 03-Oct-25 | J: -95; D: Louvers Lvl 3
B3L3-310 | HVAC Insulation Lvl 3 |  |  | 10 | 0 | 10 | 23-Sep-25 | 06-Oct-25 | J: -81; J: HVAC Insulation Lvl 3
B3L3-192 |  | Electrical Power Conduits Lvl 3 |  | 15 | 0 | 15 | 25-Sep-25 | 15-Oct-25 | J: -125; M: Electrical Power Conduits Lvl 3
B3L3-194 | Lighting Conduits Lvl 3 |  |  | 15 | 0 | 15 | 02-Oct-25 | 22-Oct-25 | J: -125; F: Lighting Conduits Lvl 3
B3L3-330 |  | Duct Final Connections Lvl 3 |  | 15 | 0 | 15 | 06-Oct-25 | 24-Oct-25 | J: -95; M: Duct Final Connections Lvl 3
B3L3-196 |  | Mechanical Equipment Electrical Conduits Lvl 3 |  | 15 | 0 | 15 | 16-Oct-25 | 05-Nov-25 | J: -125; J: Mechanical Equipment Electrical Conduits Lvl 3
B3L3-640 |  | Distribution Panels Install Lvl 3 |  | 10 | 0 | 10 | 16-Oct-25 | 29-Oct-25 | J: -108; M: Distribution Panels Install Lvl 3
B3L3-650 |  | OH FP Test/Inspections Lvl 3 |  | 5 | 0 | 5 | 16-Oct-25 | 22-Oct-25 | J: -113; M: OH FP Test/Inspections Lvl 3
B3L3-198 |  | Security/ Data/ FA Conduits Lvl 3 |  | 15 | 0 | 15 | 23-Oct-25 | 12-Nov-25 | J: -118; A: Security/ Data/ FA Conduits Lvl 3
B3L3-660 |  | Install Door Frames Lvl 3 |  | 10 | 0 | 10 | 23-Oct-25 | 05-Nov-25 | J: -105; F: Install Door Frames Lvl 3
B3L3-680 |  | OH Electrical Inspections Lvl 3 |  | 3 | 0 | 3 | 23-Oct-25 | 27-Oct-25 | J: -118; M: OH Electrical Inspections Lvl 3
B3L3-700 |  | Fire Protection Ceilling Finishes Lvl 3 |  | 10 | 0 | 10 | 23-Oct-25 | 05-Nov-25 | J: -113; A: Fire Protection Ceilling Finishes Lvl 3
Remaining Level of Effort |  | Actual Work | Critical Remaining Work |  |  |  | Page 42 of 46 |  | J: TASK filter: Activity Status.
Actual Level of Effort |  | Remaining Work | Milestone | [5 empty] | D: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  | Original | Actual | Remaining | Start | Finish | Total Float | M: 2025; J: 2026; F: 2027
|  |  | Duration | Duration | Duration | bar: A
[8 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
B3L3-230 | Electrical Connections to Equipment Lvl 3 |  | 12 | 0 | 12 | 06-Nov-25 | 21-Nov-25 | J: -125; J: Electrical Connections to Equipment Lvl 3
B3L3-670 | Doors and Hardware Lvl 3 |  | 10 | 0 | 10 | 06-Nov-25 | 19-Nov-25 | J: -105; A: Doors and Hardware Lvl 3
B3L3-690 | Test and Balance Lvl 3 |  | 2 | 0 | 2 | 06-Nov-25 | 07-Nov-25 | J: -57; M: Test and Balance Lvl 3
B3L3-750 | Composite Flooring Lvl 3 |  | 10 | 0 | 10 | 20-Nov-25 | 04-Dec-25 | J: -105; A: Composite Flooring Lvl 3
B3L3-280 | Electrical Systems Finishes- Lighting/FA/Security Lvl 3 |  | 12 | 0 | 12 | 24-Nov-25 | 10-Dec-25 | J: -125; A: Electrical Systems Finishes- Lighting/FA/Security Lvl 3
B3L3-710 | Install New Floor Hatch Lvl 3 |  | 3 | 0 | 3 | 11-Dec-25 | 15-Dec-25 | J: -125; M: Install New Floor Hatch Lvl 3
B3L3-720 | Install New Stairs to Mech Level Lvl 3 |  | 10 | 0 | 10 | 16-Dec-25 | 30-Dec-25 | J: -125; J: Install New Stairs to Mech Level Lvl 3
B3L3-730 | Install Fire Extinguishers Lvl 3 |  | 3 | 0 | 3 | 31-Dec-25 | 05-Jan-26 | J: -125; J: Install Fire Extinguishers Lvl 3
B3L3-740 | Signage Lvl 3 |  | 5 | 0 | 5 | 06-Jan-26 | 12-Jan-26 | J: -125; M: Signage Lvl 3
STAIR FINISHES |  |  | 84 | 0 | 84 | 14-Jul-25 | 07-Nov-25 | J: -82
STAIR A FINISHES |  |  | 76 | 0 | 76 | 14-Jul-25 | 28-Oct-25 | J: -74
B3ST-300 | Frame Walls @ Str A |  | 8 | 0 | 8 | 14-Jul-25 | 23-Jul-25 | J: -82; N: Frame Walls @ Str A
B3ST-310 | Framing Inspection @ Str A |  | 1 | 0 | 1 | 24-Jul-25 | 24-Jul-25 | J: -74; D: Framing Inspection @ Str A
B3ST-320 | MECH Rough @ Str A |  | 3 | 0 | 3 | 25-Jul-25 | 29-Jul-25 | J: -74; N: MECH Rough @ Str A
B3ST-800 | ELECT Rough @ Str A |  | 3 | 0 | 3 | 25-Jul-25 | 29-Jul-25 | J: -74; N: ELECT Rough @ Str A
B3ST-1030 | Fireprotection Rough @ Str A |  | 3 | 0 | 3 | 25-Jul-25 | 29-Jul-25 | J: -74; D: Fireprotection Rough @ Str A
B3ST-330 | MEP Inspection @ Str A |  | 1 | 0 | 1 | 30-Jul-25 | 30-Jul-25 | J: -74; D: MEP Inspection @ Str A
B3ST-340 | Insulate & Inspect @ Str A |  | 2 | 0 | 2 | 31-Jul-25 | 01-Aug-25 | J: -74; D: Insulate & Inspect @ Str A
B3ST-350 | Hang DW/Shaftwall @ Str A |  | 8 | 0 | 8 | 04-Aug-25 | 13-Aug-25 | J: -74; J: Hang DW/Shaftwall @ Str A
B3ST-360 | Finish DW @ Str A |  | 8 | 0 | 8 | 11-Aug-25 | 20-Aug-25 | J: -74; D: Finish DW @ Str A
B3ST-370 | Paint 1st Coat Walls @ Str A |  | 5 | 0 | 5 | 21-Aug-25 | 27-Aug-25 | J: -74; J: Paint 1st Coat Walls @ Str A
B3ST-390 | Inst Railings & Posts @ Str A |  | 8 | 0 | 8 | 28-Aug-25 | 09-Sep-25 | J: -74; F: Inst Railings & Posts @ Str A
B3ST-280 | Paint Steel - 1st Coat @ Str A |  | 2 | 0 | 2 | 04-Sep-25 | 05-Sep-25 | J: -47; F: Paint Steel - 1st Coat @ Str A
B3ST-430 | Welding/Steel Insp @ Str A |  | 1 | 0 | 1 | 10-Sep-25 | 10-Sep-25 | J: -74; J: Welding/Steel Insp @ Str A
B3ST-440 | DW Touc h Up @ Str A |  | 1 | 0 | 1 | 11-Sep-25 | 11-Sep-25 | J: -74; J: DW Touch Up @ Str A
B3ST-400 | Mechanical Finishes @ Str A |  | 3 | 0 | 3 | 12-Sep-25 | 16-Sep-25 | J: -74; F: Mechanical Finishes @ Str A
B3ST-1020 | Electrical Finishes @ Str A |  | 3 | 0 | 3 | 12-Sep-25 | 16-Sep-25 | J: -74; F: Electrical Finishes @ Str A
B3ST-1040 | Fire Protection Finishes @ Str A |  | 3 | 0 | 3 | 12-Sep-25 | 16-Sep-25 | J: -74; F: Fire Protection Finishes @ Str A
B3ST-1100 | Patch Plaster Ceiling @ Str A |  | 8 | 0 | 8 | 12-Sep-25 | 23-Sep-25 | J: -59; F: Patch Plaster Ceiling @ Str A
B3ST-420 | Prep and Inst Finish on Treads/Landings @ Str A |  | 20 | 0 | 20 | 17-Sep-25 | 14-Oct-25 | J: -74; J: Prep and Inst Finish on Treads/Landings @ Str A
B3ST-450 | Final Paint @ Str A |  | 5 | 0 | 5 | 15-Oct-25 | 21-Oct-25 | J: -74; F: Final Paint @ Str A
B3ST-460 | Final Clean @ Str A |  | 5 | 0 | 5 | 22-Oct-25 | 28-Oct-25 | J: -74; F: Final Clean @ Str A
STAIR B FINISHES |  |  | 76 | 0 | 76 | 24-Jul-25 | 07-Nov-25 | J: -82
B3ST-830 | Frame Walls @ Str B |  | 8 | 0 | 8 | 24-Jul-25 | 04-Aug-25 | J: -82; N: Frame Walls @ Str B
B3ST-840 | Framing Inspection @ Str B |  | 1 | 0 | 1 | 05-Aug-25 | 05-Aug-25 | J: -82; D: Framing Inspection @ Str B
B3ST-1070 | Fireprotection Rough @ Str B |  | 3 | 0 | 3 | 05-Aug-25 | 07-Aug-25 | J: -78; J: Fireprotection Rough @ Str B
B3ST-850 | MECH Rough @ Str B |  | 3 | 0 | 3 | 06-Aug-25 | 08-Aug-25 | J: -82; D: MECH Rough @ Str B
B3ST-860 | ELECT Rough @ Str B |  | 3 | 0 | 3 | 06-Aug-25 | 08-Aug-25 | J: -82; D: ELECT Rough @ Str B
B3ST-870 | MEP Inspection @ Str B |  | 1 | 0 | 1 | 11-Aug-25 | 11-Aug-25 | J: -82; D: MEP Inspection @ Str B
B3ST-880 | Insulate & Inspect @ Str B |  | 2 | 0 | 2 | 12-Aug-25 | 13-Aug-25 | J: -82; D: Insulate & Inspect @ Str B
B3ST-890 | Hang DW/Shaftwall @ Str B |  | 8 | 0 | 8 | 14-Aug-25 | 25-Aug-25 | J: -82; J: Hang DW/Shaftwall @ Str B
B3ST-900 | Finish DW @ Str B |  | 8 | 0 | 8 | 21-Aug-25 | 02-Sep-25 | J: -82; D: Finish DW @ Str B
B3ST-920 | Paint 1st Coat Walls @ Str B |  | 5 | 0 | 5 | 03-Sep-25 | 09-Sep-25 | J: -82; F: Paint 1st Coat Walls @ Str B
B3ST-820 | Paint Steel - 1st Coat @ Str B |  | 2 | 0 | 2 | 04-Sep-25 | 05-Sep-25 | J: -47; F: Paint Steel - 1st Coat @ Str B
B3ST-930 | Inst Railings & Posts @ Str B |  | 8 | 0 | 8 | 10-Sep-25 | 19-Sep-25 | J: -82; F: Inst Railings & Posts @ Str B
B3ST-940 | Welding/Steel Insp @ Str B |  | 1 | 0 | 1 | 22-Sep-25 | 22-Sep-25 | J: -82; F: Welding/Steel Insp @ Str B
B3ST-950 | DW Touc h Up @ Str B |  | 1 | 0 | 1 | 23-Sep-25 | 23-Sep-25 | J: -82; J: DW Touch Up @ Str B
B3ST-960 | Mechanical Finishes @ Str B |  | 3 | 0 | 3 | 24-Sep-25 | 26-Sep-25 | J: -82; F: Mechanical Finishes @ Str B
Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 43 of 46 |  | J: TASK filter: Activity Status.
Actual Level of Effort | Remaining Work | Milestone | [5 empty] | D: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  | Original | Actual | Remaining | Start | Finish | J: Total Float; J: 2025; J: 2026; M: 2027
|  |  | Duration | Duration | Duration | [30 empty] | M
[8 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A
B3ST-1050 | Electrical Finishes @ Str B |  | 3 | 0 | 3 | 24-Sep-25 | 26-Sep-25 | J: -82; F: Electrical Finishes @ Str B
B3ST-1060 | Fire Protection Finishes @ Str B |  | 3 | 0 | 3 | 24-Sep-25 | 26-Sep-25 | J: -82; M: Fire Protection Finishes @ Str B
B3ST-1110 | Patch Plaster Ceiling @ Str B |  | 8 | 0 | 8 | 24-Sep-25 | 03-Oct-25 | J: -67; M: Patch Plaster Ceiling @ Str B
B3ST-970 | Prep and Inst Finish on Treads/Landings @ Str B |  | 20 | 0 | 20 | 29-Sep-25 | 24-Oct-25 | J: -82; J: Prep and Inst Finish on Treads/Landings @ Str B
B3ST-980 | Final Paint @ Str B |  | 5 | 0 | 5 | 27-Oct-25 | 31-Oct-25 | J: -82; F: Final Paint @ Str B
B3ST-990 | Final Clean @ Str B |  | 5 | 0 | 5 | 03-Nov-25 | 07-Nov-25 | J: -82; F: Final Clean @ Str B
ROOF A ND EXTERIOR FACADE |  |  | 308 | 141 | 308 | 15-Jul-24 A | 16-Apr-26 | J: -143
ROOF |  |  | 280 | 141 | 280 | 15-Jul-24 A | 09-Mar-26 | J: -143
B3LR-550 | Pull Feeders from Transformer to Elec Room @ Bldg 3 |  | 8 | 141 | 2 | 15-Jul-24 A | 04-Feb-25 | J: 100; O: Pull Feeders from Transformer to Elec Room @ Bldg 3
B3LR-280 | Inst Exhaust Fans |  | 5 | 118 | 4 | 15-Aug-24 A | 30-Jan-26 | J: -162; A: Inst Exhaust Fans
B3LR-100 | Post Abatement Signage |  | 10 | 0 | 10 | 02-Feb-25 | 11-Feb-25 | J: 57; J: Post Abatement Signage
B3LR-130 | Select Abatement |  | 5 | 0 | 5 | 12-Feb-25 | 18-Feb-25 | J: 41; M: Select Abatement
B3LR-140 | Clean Rpt/Clear Asbestos |  | 5 | 0 | 5 | 19-Feb-25 | 25-Feb-25 | J: 41; J: Clean Rpt/Clear Asbestos
B3LR-160 | Remove Roofs Stair A & B |  | 10 | 0 | 10 | 26-Feb-25 | 11-Mar-25 | J: 51; J: Remove Roofs Stair A & B
B3LR-170 | Remove Remaining Roofs |  | 10 | 0 | 10 | 26-Feb-25 | 11-Mar-25 | J: 41; J: Remove Remaining Roofs
B3LR-270 | Inst Blocking @ Perimeter |  | 5 | 0 | 5 | 12-Mar-25 | 18-Mar-25 | J: 41; J: Inst Blocking @ Perimeter
B3LR-190 | Install Blocking / Curbs for new Roof Top Units |  | 5 | 0 | 5 | 19-Mar-25 | 25-Mar-25 | J: 41; O: Install Blocking / Curbs for new Roof Top Units
B3LR-180 | New Roof Drains & Vent Stack |  | 5 | 0 | 5 | 26-Mar-25 | 01-Apr-25 | J: 41; A: New Roof Drains & Vent Stack
B3LR-200 | Inst Tapered Insulation |  | 5 | 0 | 5 | 26-Mar-25 | 01-Apr-25 | J: 41; J: Inst Ta pered Insulation
B3LR-470 | Patch Roof Around Demoed Roof Vents |  | 5 | 0 | 5 | 02-Apr-25 | 08-Apr-25 | J: 41; O: Patch Roof Around Demoed Roof Vents
B3LR-220 | Inst Roof Membrane |  | 5 | 0 | 5 | 20-Jan-26 | 26-Jan-26 | J: -162; M: Inst Roof Membrane
B3LR-230 | New Perimeter Edge Flashing |  | 5 | 0 | 5 | 27-Jan-26 | 02-Feb-26 | J: -143; J: New Perimeter Edge Flashing
B3LR-210 | Inst Scuppers & Down Spouts |  | 5 | 0 | 5 | 03-Feb-26 | 09-Feb-26 | J: -143; J: Inst Scuppers & Down Spouts
B3LR-240 | Clean Out Existing Roof Drains |  | 5 | 0 | 5 | 10-Feb-26 | 16-Feb-26 | J: -143; J: Clean Out Existing Roof Drains
B3LR-260 | Inst New Roof Strainers over Scuppers |  | 5 | 0 | 5 | 17-Feb-26 | 23-Feb-26 | J: -143; A: Inst New Roof Strainers over Scuppers
B3LR-480 | Install Lightning Protection |  | 10 | 0 | 10 | 24-Feb-26 | 09-Mar-26 | J: -143; J: Install Lightning Protection
EXTERIOR FACADE |  |  | 186 | 0 | 186 | 24-Apr-25 | 16-Jan-26 | J: -107
B3LR-420 | Patch & Infill at MEP Service Entrances |  | 15 | 0 | 15 | 24-Apr-25 | 14-May-25 | J: 29; N: Patch & Infill at MEP Service Entrances
B3LR-300 | Repointing of brick |  | 20 | 0 | 20 | 15-May-25 | 12-Jun-25 | J: 29; S: Repointing of brick
B3LR-450 | Install New Concrete Stairs and Retain. Walls |  | 10 | 0 | 10 | 13-Jun-25 | 26-Jun-25 | J: 29; J: Install New Concrete Stairs and Retain. Walls
B3LR-440 | Install New Exterior Galv. Metal Stairs |  | 10 | 0 | 10 | 13-Jun-25 | 26-Jun-25 | J: 29; D: Install New Exterior Galv. Metal Stairs
B3LR-430 | Prep and Paint Exterior Metal Railings |  | 5 | 0 | 5 | 27-Jun-25 | 03-Jul-25 | J: 29; J: Prep and Paint Exterior Metal Railings
B3LR-350 | Install intelligent system control & card readers |  | 5 | 0 | 5 | 18-Sep-25 | 24-Sep-25 | J: -31; A: Install intelligent system control & card readers
B3LR-320 | Seal mechanical & Electrical penetrations |  | 5 | 0 | 5 | 06-Oct-25 | 10-Oct-25 | J: -40; A: Seal mechanical & Electrical penetrations
B3LR-340 | Remote annunciator panel |  | 5 | 0 | 5 | 09-Oct-25 | 15-Oct-25 | J: -90; M: Remote annunciator panel
B3LR-360 | Install exterior signage |  | 3 | 0 | 3 | 16-Oct-25 | 20-Oct-25 | J: -46; F: Install exterior signage
B3LR-490 | Replace Cast Stone Pieces @ Ext Elevations |  | 7 | 0 | 7 | 16-Oct-25 | 24-Oct-25 | J: -90; M: Replace Cast Stone Pieces @ Ext Elevations
B3LR-500 | Refinish Existing Doors @ Ext Elevations |  | 5 | 0 | 5 | 27-Oct-25 | 31-Oct-25 | J: -90; M: Refinish Existing Doors @ Ext Elevations
B3LR-510 | Terra Cotta Repair @ East Elevation |  | 10 | 0 | 10 | 03-Nov-25 | 14-Nov-25 | J: -90; A: Terra Cotta Repair @ East Elevation
B3LR-520 | Site Restoration |  | 5 | 0 | 5 | 11-Dec-25 | 17-Dec-25 | J: -107; M: Site Restoration
B3LR-530 | Demo Mechanicals Outside 5 ft Building Footprint |  | 10 | 0 | 10 | 18-Dec-25 | 02-Jan-26 | J: -107; A: Demo Mechanicals Outside 5 ft Building Footprint
B3LR-540 | Reconnect Building to Storm Drainage System |  | 10 | 0 | 10 | 05-Jan-26 | 16-Jan-26 | J: -107; A: Reconnect Building to Storm Drainage System
EXTERIOR PUNCHLIST BLDG 3 |  |  | 28 | 0 | 28 | 10-Mar-26 | 16-Apr-26 | J: -143
B3L3-490 | PHB - Roof & Exterior Punchlist |  | 5 | 0 | 5 | 10-Mar-26 | 16-Mar-26 | J: -143; A: PHB - Roof & Exterior Punchlist
B3L3-500 | Subcontract Punch Work -Roof & Exterior |  | 10 | 0 | 10 | 17-Mar-26 | 30-Mar-26 | J: -143; O: Subcontract Punch Work -Roof & Exterior
B3L3-520 | Owner / Architect Punch -Roof & Exterior |  | 5 | 0 | 5 | 31-Mar-26 | 06-Apr-26 | J: -143; O: Owner / Architect Punch -Roof & Exterior
B3L3-530 | Subs Complete Owner/AE Punch -Roof & Exterior |  | 8 | 0 | 8 | 07-Apr-26 | 16-Apr-26 | J: -143; N: Subs Complete Owner/AE Punch -Roof & E
| BLDG 3 START UP/TEST/COMMISSION PH2 |  | 206 | 0 | 206 | 24-Jul-25 | 13-May-26 | J: -162
B3TRN-310 | Controls Test ing |  | 5 | 0 | 5 | 24-Jul-25 | 30-Jul-25 | J: 14; O: Controls Test ing
Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 44 of 46 |  | J: TASK filter: Activity Status.
Actual Level of Effort | Remaining Work | Milestone | [5 empty] | D: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name |  |  | Original | Actual | Remaining | Start | J: Finish; F: Total Float; A: 2025; A: 2026; A: 2027
|  |  |  | Duration | Duration | Duration
[9 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | AM
B3TRN-110 | Switchgear / Piping & Wire |  |  | 20 | 0 | 20 | 11-Aug-25 | 08-Sep-25 | J: -73; J: Switchgear / Piping & Wire
B3TRN-230 | Inst Elevator |  |  | 30 | 0 | 30 | 25-Aug-25 | 06-Oct-25 | J: -13; D: Inst Elevator
B3TRN-130 | Electrical Systems Tie In & Test Fire Alarm |  |  | 20 | 0 | 20 | 18-Sep-25 | 15-Oct-25 | J: -90; M: Electrical Systems Tie In & Test Fire Alarm
B3TRN-150 | Sprinkler System Tie In & Test |  |  | 15 | 0 | 15 | 16-Oct-25 | 05-Nov-25 | J: -46; M: Sprinkler System Tie In & Test
B3TRN-240 | Start Up and Test Elevator |  |  | 5 | 0 | 5 | 16-Oct-25 | 22-Oct-25 | J: -20; F: Start Up and Test Elevator
B3TRN-100 | Plumbing Systems Tie In & Test |  |  | 20 | 0 | 20 | 06-Nov-25 | 04-Dec-25 | J: -77; M: Plumbing Systems Tie In & Test
B3TRN-460 | Pool Tes ting/Turnover |  |  | 5 | 0 | 5 | 05-Dec-25 | 11-Dec-25 | J: -55; M: Pool Tes ting/Turnover
B3TRN-140 | Mechanical Systems Tie-In & Test |  |  | 20 | 0 | 20 | 02-Feb-26 | 27-Feb-26 | J: -162; A: Mechanical Systems Tie-In & Test
B3TRN-120 | Start Up & Test Equipment |  |  | 20 | 0 | 20 | 16-Feb-26 | 13-Mar-26 | J: -162; J: Start Up & Test Equipment
B3TRN-360 | HVAC Commissioning |  |  | 15 | 0 | 15 | 02-Mar-26 | 20-Mar-26 | J: -134; J: HVAC Commissioning
B3TRN-200 | Bldg 3 Commissioning Electrical |  |  | 15 | 0 | 15 | 10-Mar-26 | 30-Mar-26 | J: -162; S: Bldg 3 Commissioning Electrical
B3TRN-180 | Balance / Test HVAC Systems |  |  | 15 | 0 | 15 | 10-Mar-26 | 30-Mar-26 | J: -162; A: Balance / Test HVAC Systems
B3TRN-320 | Air & Water Balancing |  |  | 10 | 0 | 10 | 31-Mar-26 | 13-Apr-26 | J: -162; A: Air & Water Balancing
B3TRN-390 | Performance Verification Testing |  |  | 10 | 0 | 10 | 14-Apr-26 | 27-Apr-26 | J: -150; S: Performance Verification Testing
B3TRN-470 | Government Furniture/IT Installation @ Bldg 3 |  |  | 5 | 0 | 5 | 14-Apr-26 | 18-Apr-26 | J: -233; N: Government Furniture/IT Installation @ Bldg
| CLEAN / PUNCH 1ST FLOOR |  |  | 79 | 0 | 79 | 23-Jan-26 | 13-May-26 | J: -162
B3L1-800 | Rough Clean Lvl 1 |  |  | 3 | 0 | 3 | 23-Jan-26 | 27-Jan-26 | J: -133; M: Rough Clean Lvl 1
B3L1-810 | PHB Lvl 1 Floor Punchlist |  |  | 5 | 0 | 5 | 28-Jan-26 | 03-Feb-26 | J: -119; J: PHB Lvl 1 Floor Punchlist
B3L1-820 | Subcontract Punch Work -Lvl 1 |  |  | 10 | 0 | 10 | 04-Feb-26 | 17-Feb-26 | J: -119; J: Subcontract Punch Work -Lvl 1
B3L1-830 | Phase 02 - Final Clean -1 Lvl |  |  | 5 | 0 | 5 | 20-Apr-26 | 24-Apr-26 | J: -162; S: Phase 02 - Final Clean -1 Lvl
B3L1-840 | Owner / Architect Punch -Lvl 1 |  |  | 5 | 0 | 5 | 27-Apr-26 | 01-May-26 | J: -162; S: Owner / Architect Punch -Lvl 1
B3L1-850 | Subs Complete Owner/AE Punch -Lvl 1 |  |  | 8 | 0 | 8 | 04-May-26 | 13-May-26 | J: -162; N: Subs Complete Owner/AE Punch -Lvl 1
| CLEAN / PUNCH GROUND FLOOR |  |  | 108 | 0 | 108 | 11-Dec-25 | 13-May-26 | J: -162
B3LG-1010 | Rough Clean Lvl G |  |  | 3 | 0 | 3 | 11-Dec-25 | 15-Dec-25 | J: -104; M: Rough Clean Lvl G
B3LG-1060 | PHB Lvl-G Floor Punchlist |  |  | 5 | 0 | 5 | 16-Dec-25 | 22-Dec-25 | J: -90; M: PHB Lvl-G Floor Punchlist
B3LG-1070 | Subcontract Punch Work -Lvl G |  |  | 10 | 0 | 10 | 23-Dec-25 | 07-Jan-26 | J: -90; J: Subcontract Punch Work -Lvl G
B3LG-1080 | Phase 02 - Final Clean -G Lvl |  |  | 5 | 0 | 5 | 20-Apr-26 | 24-Apr-26 | J: -162; S: Phase 02 - Final Clean -G Lvl
B3LG-1090 | Owner / Architect Punch -Lvl G |  |  | 5 | 0 | 5 | 27-Apr-26 | 01-May-26 | J: -162; S: Owner / Architect Punch -Lvl G
B3LG-1100 | Subs Complete Owner/AE Punch -Lvl G |  |  | 8 | 0 | 8 | 04-May-26 | 13-May-26 | J: -162; N: Subs Complete Owner/AE Punch -Lvl G
| CLEAN / PUNCH 2ND FLOOR |  |  | 82 | 0 | 82 | 20-Jan-26 | 13-May-26 | J: -162
B3L2-810 | Rough Clean Lvl 2 |  |  | 3 | 0 | 3 | 20-Jan-26 | 22-Jan-26 | J: -130; A: Rough Clean Lvl 2
B3L2-820 | PHB Lvl 2 Floor Punchlist |  |  | 5 | 0 | 5 | 23-Jan-26 | 29-Jan-26 | J: -116; M: PHB Lvl 2 Floor Punchlist
B3L2-830 | Subcontract Punch Work -Lvl 2 |  |  | 10 | 0 | 10 | 30-Jan-26 | 12-Feb-26 | J: -116; J: Subcontract Punch Work -Lvl 2
B3L2-840 | Phase 02 - Final Clean -Lvl 2 |  |  | 5 | 0 | 5 | 20-Apr-26 | 24-Apr-26 | J: -162; S: Phase 02 - Final Clean -Lvl 2
B3L2-850 | Owner / Architect Punch -Lvl 2 |  |  | 5 | 0 | 5 | 27-Apr-26 | 01-May-26 | J: -162; S: Owner / Architect Punch -Lvl 2
B3L2-860 | Subs Complete Owner/AE Punch -Lvl 2 |  |  | 8 | 0 | 8 | 04-May-26 | 13-May-26 | J: -162; N: Subs Complete Owner/AE Punch -Lvl 2
| CLEAN / PUNCH PENTHOUSE |  |  | 36 | 0 | 36 | 13-Jan-26 | 03-Mar-26 | J: -111
B3L3-340 | Rough Clean Lvl 3 |  |  | 3 | 0 | 3 | 13-Jan-26 | 15-Jan-26 | J: -125; A: Rough Clean Lvl 3
B3L3-350 | PHB - Floor Punchlist Lvl 3 |  |  | 5 | 0 | 5 | 16-Jan-26 | 22-Jan-26 | J: -111; M: PHB - Floor Punchlist Lvl 3
B3L3-360 | Subcontract Punch Work -Lvl 3 |  |  | 10 | 0 | 10 | 23-Jan-26 | 05-Feb-26 | J: -111; J: Subcontract Punch Work -Lvl 3
B3L3-370 | Phase 02 - Final Clean -3 Lvl |  |  | 5 | 0 | 5 | 06-Feb-26 | 12-Feb-26 | J: -111; J: Phase 02 - Final Clean -3 Lvl
B3L3-380 | Owner / Architect Punch -Lvl 3 |  |  | 5 | 0 | 5 | 13-Feb-26 | 19-Feb-26 | J: -111; J: Owner / Architect Punch -Lvl 3
B3L3-390 | Subs Complete Owner/AE Punch -Lvl 3 |  |  | 8 | 0 | 8 | 20-Feb-26 | 03-Mar-26 | J: -111; S: Subs Complete Owner/AE Punch -Lvl 3
| BLDG 3 COMMISSION / TURNOVER |  |  | 43 | 0 | 43 | 22-Mar-26 | 20-May-26 | J: -131
B3TRN-250 | Red Zone Meeting |  |  | 60 | 0 | 60 | 22-Mar-26 | 20-May-26 | J: -188; A: Red Zone Meeting
B3TRN-170 | CORP 30 Day Notice of Turnover |  |  | 30 | 0 | 30 | 21-Apr-26 | 20-May-26 | J: -188; O: CORP 30 Day Notice of Turnover
B3TRN-400 | SUBSTANTIAL COMPLETION |  |  | 0 | 0 | 0 |  | 01-May-26 | J: -154; S: SUBSTANTIAL COMPLETION
B3TRN-440 | Final Inspections |  |  | 5 | 0 | 5 | 14-May-26 | 20-May-26 | J: -162; A: Final Inspections
B3TRN-450 | READY FOR OCCUPANCY - BLDG 3 |  |  | 0 | 0 | 0 |  | 20-May-26 | J: -162; N: READY FOR OCCUPANCY - BLDG 3
| Remaining Level of Effort | Actual Work | Critical Remaining Work |  |  |  | Page 45 of 46 |  | J: TASK filter: Activity Status.
| Actual Level of Effort | Remaining Work | Milestone | [5 empty] | D: © Primavera Systems, Inc.
DATA DATE 31-Jan-25
USACE CVACLC - PU59 1-31-25_acceleration draft_NO man power
logic_fireproofing multiple crews | CURRENT DATE: 29-Jan-25
Activity ID | Activity Name | Original | Actual | Remaining | Start | Finish | Total Float |  | M: 2025; M: 2026; F: 2027
|  | Duration | Duration | Duration
[8 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | AM
| DEMOBILIZATION & CLOSEOUT | 211 | 0 | 211 | 17-Sep-25 | 15-Jul-26 | -169
SU-212 | Install Site Signage | 5 | 0 | 5 | 17-Sep-25 | 23-Sep-25 | 15 | D: Install Site Signage
PS1120 | SWPPP Control - Notice of Termination | 1 | 0 | 1 | 07-Oct-25 | 07-Oct-25 | 6 | A: SWPPP Control - Notice of Termination
CLOS100 | Submission/Approval Closeout Docs - O&M Manuals | 40 | 0 | 40 | 18-Feb-26 | 14-Apr-26 | -105 | N: Submission/Approval Closeout Docs - O&M
CLOS110 | Submission/Approval Closeout Docs - As-Built Drawings | 40 | 0 | 40 | 18-Feb-26 | 14-Apr-26 | -105 | N: Submission/Approval Closeout Docs - As-Bu
DCO-1010 | Demo Temporar y Buildings / Walkways / Restore Site - Phase 2 | 40 | 0 | 40 | 20-Apr-26 | 15-Jun-26 | -170 | D: Demo Temporar y Buildings / Walkwa
DEMOB-1010 | Demobilization | 30 | 0 | 30 | 16-Jun-26 | 15-Jul-26 | -244 | S: Demobilization
Remaining Level of Effort | Actual Work | Critical Remaining Work | Page 46 of 46 | TASK filter: Activity Status.
Actual Level of Effort | Remaining Work | Milestone |  |  | © Primavera Systems, Inc.